## Timeline
site | date | evidence type | observation | source URL / file | confidence
Vineland NJ | 2024-02 | Zoning | City zoning officer determination: data center is a permitted use under redevelopment plan (per city solicitor, Aug 2026 hearing) | https://www.nj.com/business/2026/08/you-sold-us-out-nj-town-approves-next-phase-of-massive-ai-data-center-as-residents-erupt.html | medium
Vineland NJ | 2024-06 | Planning | Original site plan (June 2024) approved later in 2024; amended 2025 | https://www.burlingtoncountytimes.com/story/money/business/2026/08/20/vineland-planning-board-hearing-vote-dataone-lincoln-avenue-data-center-new-site-plan/91338935007/ | medium
Vineland NJ | 2024-09 | Utility | City/Vineland Municipal Electric commissioned Atlantic City Electric (ACE) study for 300 MW; VMEU "not able to accommodate the Service Request" (peak system load 164 MW) | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center (secondary, cites ACE deposit request Mar 2025) | medium
Vineland NJ | 2025-02 | Utility | ACE offered temporary 50 MW at 138 kV via tap off Lincoln-Union line to customer-owned substation (~$6.2M +/-50%); 300 MW "under study" | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center (secondary) | medium
Vineland NJ | 2025-02-26 | Land | NEP Real Estate (Northeast Precast affiliate) transferred campus lots to DataOne; groundbreaking Feb 2025 | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center (secondary, county deed records) | medium
Vineland NJ | 2025-03-25 | Imagery | Active earthworks/sand grading across campus; first steel visible NW corner | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ vineland_nj_2025-03-25.png | medium
Vineland NJ | 2025-06-03 | Imagery | First large white roof (Phase 1 building, NW of campus) visible | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ vineland_nj_2025-06-03.png | medium
Vineland NJ | 2025-07 | Power (temp) | Rented Caterpillar gas generators begin arriving on site (DataOne letter to NJDEP) | https://floodlightnews.org/vineland-nj-data-center-air-pollution/ | high
Vineland NJ | 2025-08-30 | Mgmt/Developer | DataOne CEO concedes build ~2 months behind schedule | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center (secondary) | medium
Vineland NJ | 2025-09-23 | Imagery | Phase 1 roof plus second roof segment; bright-roof in crop ~4.9 ha (incl. pre-existing NE Precast roofs ~3-4 ha) | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ vineland_nj_2025-09-23.png | medium
Vineland NJ | 2025-10 | Power (temp) | 16 generators start operating (~31.7 MW nameplate) -> energization of Phase 1 on temporary power | https://floodlightnews.org/vineland-nj-data-center-air-pollution/ | high
Vineland NJ | 2025-11 | Mgmt | Microsoft tranche 1 delivered (Nebius); MSFT payment obligations begin early Nov 2025 | site_list.csv / Nebius Q3-25 letter | high
Vineland NJ | 2025-11-24 | Utility (gas) | DataOne-South Jersey Gas 15-yr firm gas transport agreement (Jul 2026-Jun 2041) sized for up to 125 MW generation; filed with NJBPU Feb 2 2026, still pending Aug 12 2026 | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center (secondary, NJBPU docket) | medium
Vineland NJ | 2025-12-22 | Imagery | Rows of grey units appear E/SE of building (consistent with generator rows; not resolvable as individual units at 10 m) | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ vineland_nj_2025-12-22.png | low
Vineland NJ | 2026-01-13 | Utility | City Council authorizes alternative ACE study at Northeast Precast request (request reduced to 49 MW) | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center (secondary) | medium
Vineland NJ | 2026-02 | Power (temp) | +16 generators online (32 total, ~63 MW nameplate); city inspection report "Phase 1 generators are online"; ~50 MW energized by tranche 2 (Feb 2026) | https://floodlightnews.org/vineland-nj-data-center-air-pollution/ ; measuredai (secondary) | high
Vineland NJ | 2026-02 | Mgmt | Microsoft tranche 2 delivered (Nebius) | site_list.csv / Nebius filings | high
Vineland NJ | 2026-03-10 | Regulatory | Cumberland County Health Dept Notice of Violation: night noise >50 dBA (generators/construction) | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center (secondary) | medium
Vineland NJ | 2026-05 | Permit | DataOne withdraws air-permit application for 32 Bergen gas engines after NJDEP found deficiencies | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center ; https://www.theguardian.com/environment/2026/aug/27/new-jersey-vineland-datacenter-permits | medium
Vineland NJ | 2026-05-14 | Contract | Nebius-Bloom agreement: ~250 MW guaranteed / 328 MW installed fuel cells (ES6.5) | https://www.enr.com/articles/63695-inside-the-vineland-data-center-power-dispute | high
Vineland NJ | 2026-06 | Power (temp) | All 62 generators fired up (122.9 MW nameplate); Floodlight thermal: ~25 running late June | https://floodlightnews.org/vineland-nj-data-center-air-pollution/ ; https://www.theguardian.com/environment/2026/aug/27/new-jersey-vineland-datacenter-permits | high
Vineland NJ | 2026-06-03 | Imagery | Bright roof in crop jumps to ~8.8 ha (from ~6 ha Apr 2026): large Phase 2 roof closed in | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ vineland_nj_2026-06-03.png | medium
Vineland NJ | 2026-06 | Jobs | Nebius "Data Center Technician - Vineland NJ colocation" posted Jun 27 2026 (reposted Aug 20 2026); text references H200 cluster (template) | https://meterwork.com/job/data-center-technician_at_nebius_QHp5B ; https://haystackapp.io/jobs/d272c86f-d7b1-42c5-bdff-69a6f9a604fd | medium
Vineland NJ | 2026-04-20..09-19 | Shipping | ImportYeti: 18 sea shipments to consignee "Nebius, Vineland NJ": Schroff racks/enclosures Apr-Jul; Bergen Engines components Aug 14-28; Ingeteam power gear Aug 28; Guntner coolers (12 containers) Sep 19 | https://www.importyeti.com/company/nebius | medium
Vineland NJ | 2026-07-08 | Planning | Revised site plan filed: 717,602 sf building (Ph1 129,622 + Ph2 587,980 sf 2-story), 9 Bloom areas (328 MW), LNG tank, chiller bldg; only 5 MW from Vineland Electric | https://www.vinelandcity.org/wp-content/uploads/2026/07/Data-ONe-Public-Hearing-Post-7.24.pdf ; measuredai (secondary) | high
Vineland NJ | 2026-07 (late) | Utility/PJM | ACE withdrew the 49 MW Cumberland County load need from PJM transmission-planning process; ACE large-load adjustment = 0 MW 2026-2046 (not independently verified in PJM docs) | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center (secondary) | medium
Vineland NJ | 2026-07-29 | Regulatory | NJDEP inspection finds 62 Cat G3516H gas engines (1,982 kW each) installed/operated without preconstruction permits | https://dep.nj.gov/wp-content/uploads/newsrel/2026/dataone75894-aonocapa.pdf | high
Vineland NJ | 2026-07-31 | Jobs | Staffing agency hiring event in Vineland for Bloom Energy assembly technicians, start "in August" | https://hntrbrk.com/breaking-news/vineland | medium
Vineland NJ | 2026-08-05 | Planning | 6-hour Planning Board hearing on amended plan (Bloom/LNG) adjourned without vote | https://hntrbrk.com/breaking-news/vineland ; https://whyy.org/articles/vineland-data-center-hearing-power-generation/ | high
Vineland NJ | 2026-08-06 | Permit | City stop-construction order: LNG tank installed with no approvals/permits | https://whyy.org/articles/vineland-data-center-stop-work-orders/ ; https://hntrbrk.com/breaking-news/vineland | high
Vineland NJ | 2026-08-10 | Permit | City stop-construction order: Bloom Energy units - "no prior approvals, plans, or permits" | https://www.scribd.com/document/1073069744/Stop-Construction-Order-Bloom-Energy-Units ; https://hntrbrk.com/breaking-news/vineland | high
Vineland NJ | 2026-08-12 | Mgmt | Q2-26 letter: "delivered all capacity tranches to Microsoft... including two tranches over the past month"; call: building finished, "on track"; stop orders not mentioned | https://assets.nebius.com/assets/4462517b-ce83-41f2-96ed-f2ac1bc06a05/SHLQ226%20%281%29.pdf | high
Vineland NJ | 2026-08 (early) | Developer | DataOne: at least 3 of 14 data halls operating | https://measuredai.substack.com/p/microsoft-new-jersey-ai-data-center (secondary) | medium
Vineland NJ | 2026-08-17 | Planning | Planning Board approves amended site plan 8-1 (special meeting); building permits to lift stop orders not publicly confirmed | https://www.burlingtoncountytimes.com/story/money/business/2026/08/20/vineland-planning-board-hearing-vote-dataone-lincoln-avenue-data-center-new-site-plan/91338935007/ ; https://whyy.org/articles/vineland-planning-board-approves-data-center-plan/ | high
Vineland NJ | 2026-08 (mid/late) | Thermal (3rd party) | Floodlight thermal drone: >=45 of 62 generators running | https://floodlightnews.org/vineland-nj-data-center-air-pollution/ | high
Vineland NJ | 2026-09-08 | Imagery | Full white roof; new dark rectangular arrays E/SE of building vs Jun 2026 (consistent with Bloom pads/units being placed; not confirmable at 10 m) | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ vineland_nj_2026-09-08.png ; strips/vineland_nj_strip.png | low
Vineland NJ | 2026-09 (~22-25) | Regulatory | NJDEP AO & $1.072M penalty; 45 days from receipt to file and obtain permits or cease installation/operation of generators (=> ~early/mid Nov 2026) | https://dep.nj.gov/wp-content/uploads/newsrel/2026/dataone75894-aonocapa.pdf ; https://www.enr.com/articles/63695-inside-the-vineland-data-center-power-dispute | high
Vineland NJ | 2023-2026 | Thermal (Landsat) | Landsat 8/9 daytime ST campus-minus-background, Jun-Aug mean: 2023 +1.35C (n=1), 2024 +0.37 (n=2), 2025 +1.42 (n=3), 2026 +1.92 (n=5). Weak upward trend; confounded by roof/sand albedo; 100 m TIRS; not a power meter | thermal/vineland_nj_landsat_st.csv (Planetary Computer landsat-c2-l2) | low
Mantsala FI | 2014-12 | History | Original Yandex DC (YIT GC, 10,654 m2) commissioned Dec 2014; office Mar 2015 | https://www.yit.fi/projektit/datakeskus | high
Mantsala FI | 2024-10-08 | Mgmt | Expansion to 75 MW announced; target end-2025/early-2026 | https://nebius.com/newsroom/nebius-to-triple-capacity-at-finland-data-center-to-75-mw | high
Mantsala FI | 2023-08..2024-09 | Imagery | Main DC building (Moreenikatu 6) unchanged; no new structure SW of main hall | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ mantsala_fi crops | medium
Mantsala FI | 2025-05-11 | Imagery | New construction (grey structure) SW of main hall | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ mantsala_fi_2025-05-11 | medium
Mantsala FI | 2025-10-18 | Imagery | Long new building SW of main hall with finished roof; persists 2026 (identity as Nebius expansion hall is likely but unconfirmed: could be adjacent utility/heat-recovery plant) | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ mantsala_fi_2025-10-18 ; strips/mantsala_fi_strip.png | low
Mantsala FI | 2026-03-31 | Mgmt | Nebius: expansion to 75 MW "completed earlier this year" | site_list.csv (Nebius PR 2026-03-31) | high
Mantsala FI | 2026 | Utility | Caverion EUR15M 70 MW substation for Mantsala DC#2; completion autumn 2027 (DC#2 in Kapuli, ~1 km away) | https://www.assemblincaverion.com/news-and-media/news/2026/caverion-finland-strengthens-its-position-in-the-data-centre-market-and-will-deliver-a-eur-15-million-substation-for-ai-cloud-company-nebius/ | high
Kansas City MO | 2024-11-19 | Mgmt | Patmos (1601 McGee St) first tenant Nebius, 5 MW, go-live Q1 2025 (launched Apr 2025) | https://nebius.com/blog/posts/nebius-opens-first-availability-zone-in-us | high
Kansas City MO | 2023-2026 | Imagery | No measurable change at 10 m (interior retrofit of existing 400k sf printing plant); rooftop gear not resolvable | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ kansascity_mo | high
Kansas City MO | 2025-09-23 | Landlord | Patmos: facility at 35 MW total, 10 MW new colo available now; +20 MW in 2026 | https://www.datacenterdynamics.com/en/news/patmos-adds-10mw-of-capacity-at-kansas-city-data-center/ | high
Kansas City MO | 2026-09-17 | Jobs | Nebius "Data Center IT Technician - Kansas City MO" posted (H200 cluster; onsite) | https://careers.nebius.com/?gh_jid=4975997101 | medium
Birmingham AL | 2025-09 | Land | Nebius acquires 75 acres at 201 Milan Pkwy (ex-Regions Lakeshore ops center) | https://nebius.com/birminghamal | high
Birmingham AL | 2026-01 | Permit | Demolition permit for existing building | https://bhamnow.com/2026/05/18/40-million-permits-birmingham-data-center/ | high
Birmingham AL | 2026-01-09 | Jobs | DC Operations Manager - Critical Infrastructure (Birmingham AL / Independence MO) posted | https://careers.nebius.com/?gh_jid=4705231101 | medium
Birmingham AL | 2026-01-16..04-20 | Imagery | Existing Regions office building demolished; site mass-graded by Apr 20 2026 | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ strips/birmingham_al_strip.png | high
Birmingham AL | 2026-03-26..04-09 | Zoning | ZBA votes on substation/switching station; city attorney memo Apr 9: not "utility substations", no special exception needed; Nebius appeals denials (May 2026) | https://www.al.com/news/birmingham/2026/04/birmingham-walks-back-on-zoning-decisions-for-ai-factorys-power-infrastructure.html | high
Birmingham AL | 2026-05-11..15 | Permit | Three building permits to Hoar Construction totaling ~$40M | https://bhamnow.com/2026/05/18/40-million-permits-birmingham-data-center/ | high
Birmingham AL | 2026 (letter) | Utility | Nebius to city: 115 kV feed to Nebius-owned substation in service NLT Dec 31 2026; 230 kV switching station (APCO-owned) Oct 2027; ~32 x 400 kW temp gas gensets for ~3-month commissioning | https://abc3340.com/resources/pdf/9222f76a-3063-46e4-aee7-796b30ed611f-NebiusResponsestoCityLetter_Redacted.pdf | high
Birmingham AL | 2026-09-20 | Imagery | Slab/steel framing over main pad + second pad to N; no closed white roof yet | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ birmingham_al_2026-09-20 | medium
Independence MO | 2025-12-05 | Land | Nebius closed on 398 acres (Eastgate, from NorthPoint) | https://www.independencemo.gov/sites/default/files/2025-12/EASTGATE%20UPDATE%20Presentation%2012-8.pdf | high
Independence MO | 2026-01-20 | Utility | City pass-through power contracts: NextEra Jun 2026-May 2027 ($10.7M), Evergy Jun-Nov 2027; Blue Valley (IPP) plant reopening ~Oct 2027, 250 MW 2027 -> up to 1,100 MW 2029 | https://www.govtech.com/artificial-intelligence/independence-mo-to-reopen-old-power-plant-for-ai-data-center | high
Independence MO | 2026-01-12..04-20 | Imagery | Earthworks begin NE of Little Blue Pkwy/MO-78 interchange | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ strips/independence_mo_strip.png | medium
Independence MO | 2026-04-22 / 05-12 | Mgmt | Site handed to GC ~Apr 20-22; groundbreaking May 12 2026; Phase 1 online ~Q3 2027 | https://www.kshb.com/news/local-news/missouri/jackson-county/q-a-taking-independence-residents-concerns-to-nebius-vp-of-public-affairs ; https://ded.mo.gov/press-room/nebius-breaks-ground-gigawatt-scale-ai-factory-independence | high
Independence MO | 2026-07-17 | Local | Residents allege night-work permit violation (ARCO Construction 4pm-4am notice) | https://fox4kc.com/news/independence-residents-allege-permit-violation-at-nebius-data-center-site/ | medium
Independence MO | 2026-09-02 | Imagery | Building pads/structures and bright surfaces on Phase 1 area (consistent with "going vertical by August") | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ independence_mo_2026-09-02 | medium
Butler Twp PA | 2025-09 | Zoning | Data center overlay adopted for original parcel | https://www.republicanherald.com/2026/06/26/ai-company-starts-development-at-highridge-business-park/ | high
Butler Twp PA | 2026-05-01 | Land | Nebius closes ~358 acres from NorthPoint, $187.5M | https://www.republicanherald.com/2026/06/26/ai-company-starts-development-at-highridge-business-park/ | high
Butler Twp PA | 2025-10-16..2026-06-03 | Imagery | New tree clearing/earthworks N of I-81 at Highridge interchange (identity as Nebius parcel probable, not confirmed against parcel 04-09-0037.001 map) | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ strips/butler_pa_strip.png | low
Butler Twp PA | 2026-08-31 | Zoning | Supervisors 2-1 add SEDCO land to overlay (600-acre campus); final land-development plan still required | https://shensentinel.com/news/butler-supervisors-clear-hurdle-for-data-center-campus-expansion-at-highridge/ | high
Butler Twp PA | 2027-10 (target) | Mgmt | Nebius site page: 260 MW initial phase operational by Oct 2027 | https://nebius.com/schuylkillcountypa | high
Bethune FR | 2025-10-30 / 12-04 | Environmental | ICPE "cas par cas" filing Oct 30 2025; decision Dec 4 2025 (SIG Reverse Industry site, ex-Bridgestone, 575 av. George Washington) | https://www.pas-de-calais.gouv.fr/contenu/telechargement/87192/545817/file/PPVE%20SIG%20B%C3%A9thune_%20sommaire%20d%C3%A9taill%C3%A9%20des%20pi%C3%A8ces%20avec%20compl%C3%A9ments.pdf | high
Bethune FR | 2025-12-25 | Imagery | New bright roofing on plant halls first visible (~3 ha vs ~2 ha through Aug 2025) | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ strips/bethune_fr_strip.png | medium
Bethune FR | 2026-02-04 | Environmental | Porter a Connaissance filed (Azur Datacenter: data hall, cooling, power & backup gensets); works planned H1 2026 | https://www.pas-de-calais.gouv.fr/contenu/telechargement/87090/545272/file/R002%201624293FTH%20V01%20-%20Porter%20%C3%A0%20Connaissance%20-%2004%2002%2026%20(1).pdf | high
Bethune FR | 2026-02-12 | Mgmt | Announced 240 MW; first capacity late summer 2026; ~120 MW by YE2026 | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/ | high
Bethune FR | 2026-03..08 | Imagery | Bright roof area grows ~4.3 ha (Mar) -> ~5.3 (May) -> ~6.5 ha (Aug 12) | Sentinel-2 L2A (Element84 Earth Search STAC); chips in imagery/ bethune_fr detail_metrics.csv | medium
Bethune FR | 2026-05-07 | Environmental | DREAL inspection report on the PAC with observations requiring response; operator reply Jul 2026; prefecture letter Jul 15 2026 ends preliminary review | https://www.pas-de-calais.gouv.fr/contenu/telechargement/87091/545277/file/20260506_SIG_BETHUNE_RAP_0007000473[1].pdf | high
Bethune FR | 2026-08-26..09-09 | Environmental | Public e-participation (PPVE) on datacenter modification; prefect to issue arrete de prescriptions complementaires afterwards (not found as of Oct 4 2026); includes >=20 MW combustion & EU ETS (SEQE) documents | https://www.pas-de-calais.gouv.fr/Publications/Consultation-du-public/Participation-du-public-par-voie-electronique/Societe-SIG-REVERSE-INDUSTRY-a-Bethune | high
Paris FR (Equinix PA10) | n/a | Imagery | Not measurable: dense urban colocation; Nebius cages inside existing Equinix building | - | high
Keflavik IS (Verne) | 2023-2026 | Imagery | Chips/strip produced (strips/keflavik_is_strip.png); colocation in existing Verne campus - not interpreted for Nebius-specific change | - | low
Longcross UK (Ark) | 2023-2026 | Imagery | Chips/strip produced; Ark LP02 new building (announced Jun 2026) could be tracked; not interpreted | - | low
Lappeenranta FI | 2023-2026 | Imagery | AOI at city-level coordinate; Pajarila campus NOT located - strip marked _UNLOCATED; no interpretation | - | low
Israel sites | n/a | Imagery | Not attempted (colocation in Mega/Or DCs; small; deprioritized) | - | n/a

## Vineland_MW
as of | gensets installed/operating (source) | genset nameplate MW (x1.982) | grid MW | gross power MW | gensets observed running (thermal) | running-gen output MW (@~80% load) | IT MW est. low (PUE 1.35) | IT MW est. high (PUE 1.2, nameplate-bound) | notes
2025-10 | 16 |  | 5 | [5 empty] | Floodlight/DataOne letter: 16 operating Oct 2025; tranche 1 Nov 2025
2026-02 | 32 |  | 5 | [5 empty] | 32 operating; ~50 MW energized (secondary); tranche 2 Feb 2026
2026-06 (end Q2) | 62 |  | 5 |  | 25 |  |  |  | all 62 fired by June; ~25 running late June (thermal)
2026-08/09 (Q3) | 62 |  | 5 |  | 45 |  |  |  | >=45 running mid/late Aug; Bloom stop-ordered Aug 10, plan approved Aug 17
Method: power-bounded. Upper bound = all nameplate + grid / PUE 1.2 (no redundancy). Low = running units at ~80% load + grid / PUE 1.35. Tranche sizes are undisclosed, so this does not prove/disprove "all tranches delivered"; it bounds physical IT MW. Contracted ~300 MW (315 MW IT per secondary source).
Cross-check: DataOne "at least 3 of 14 data halls operating" (early Aug 2026); if ~300 MW/14 halls ~21 MW/hall => ~65 MW, consistent with Q3 low-end.

## Imagery_metrics
site | date | scene | crop_ha | roof_white_ha | roof_grey_ha | bare_ha | ndvi_mean | png
bethune_fr | 2023-02-14 | S2A_31UDS_20230214_0_L2A | 26.0 | 0.41 | 3.15 | 0.6 | 0.238 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2023-02-14_crop.png
bethune_fr | 2023-06-04 | S2A_31UDR_20230604_0_L2A | 26.0 | 2.15 | 2.66 | 1.34 | 0.285 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2023-06-04_crop.png
bethune_fr | 2023-09-07 | S2B_31UDR_20230907_0_L2A | 26.0 | 1.85 | 3.09 | 0.58 | 0.291 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2023-09-07_crop.png
bethune_fr | 2023-10-07 | S2B_31UDR_20231007_0_L2A | 26.0 | 1.94 | 3.88 | 0.62 | 0.271 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2023-10-07_crop.png
bethune_fr | 2024-01-10 | S2A_31UDS_20240110_0_L2A | 26.0 | 0.81 | 4.58 | 0.56 | 0.238 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2024-01-10_crop.png
bethune_fr | 2024-06-26 | S2B_31UDR_20240626_0_L2A | 26.0 | 1.92 | 1.81 | 1.64 | 0.292 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2024-06-26_crop.png
bethune_fr | 2024-09-19 | S2A_31UDR_20240919_0_L2A | 26.0 | 1.49 | 3.26 | 0.95 | 0.271 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2024-09-19_crop.png
bethune_fr | 2024-10-24 | S2B_31UDS_20241024_0_L2A | 26.0 | 0.98 | 3.12 | 0.68 | 0.305 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2024-10-24_crop.png
bethune_fr | 2025-03-20 | S2B_31UDR_20250320_0_L2A | 26.0 | 1.23 | 3.4 | 1.05 | 0.26 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2025-03-20_crop.png
bethune_fr | 2025-04-29 | S2A_31UDR_20250429_1_L2A | 26.0 | 2.11 | 2.66 | 1.17 | 0.297 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2025-04-29_crop.png
bethune_fr | 2025-08-12 | S2C_31UDR_20250812_0_L2A | 26.0 | 2.22 | 2.86 | 1.62 | 0.26 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2025-08-12_crop.png
bethune_fr | 2025-12-25 | S2B_31UDS_20251225_0_L2A | 26.0 | 2.99 | 4.42 | 0.21 | 0.236 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2025-12-25_crop.png
bethune_fr | 2026-03-18 | S2B_31UDR_20260318_0_L2A | 26.0 | 4.25 | 2.31 | 0.8 | 0.298 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2026-03-18_crop.png
bethune_fr | 2026-05-01 | S2A_31UDR_20260501_0_L2A | 26.0 | 5.28 | 1.8 | 1.36 | 0.29 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2026-05-01_crop.png
bethune_fr | 2026-08-12 | S2B_31UDR_20260812_0_L2A | 26.0 | 6.5 | 1.9 | 3.6 | 0.171 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2026-08-12_crop.png
bethune_fr | 2026-10-04 | S2B_31UDR_20261004_0_L2A | 26.0 | 5.97 | 2.15 | 0.57 | 0.262 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/detail/bethune_fr_2026-10-04_crop.png
birmingham_al | 2023-01-07 | S2A_16SEB_20230107_0_L2A | 57.7 | 2.59 | 0.44 | 1.61 | 0.354 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2023-01-07_crop.png
birmingham_al | 2023-04-19 | S2B_16SEB_20230419_0_L2A | 57.7 | 2.71 | 0.32 | 1.95 | 0.53 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2023-04-19_crop.png
birmingham_al | 2023-09-29 | S2B_16SEB_20230929_0_L2A | 57.7 | 2.65 | 0.34 | 1.9 | 0.515 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2023-09-29_crop.png
birmingham_al | 2023-12-28 | S2B_16SEB_20231228_0_L2A | 57.7 | 2.72 | 0.58 | 1.6 | 0.41 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2023-12-28_crop.png
birmingham_al | 2024-02-06 | S2B_16SEB_20240206_0_L2A | 57.7 | 2.79 | 0.7 | 2.24 | 0.375 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2024-02-06_crop.png
birmingham_al | 2024-04-13 | S2B_16SEC_20240413_0_L2A | 57.7 | 2.78 | 0.29 | 2.04 | 0.506 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2024-04-13_crop.png
birmingham_al | 2024-08-24 | S2B_16SEC_20240824_0_L2A | 57.7 | 2.88 | 0.47 | 1.84 | 0.553 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2024-08-24_crop.png
birmingham_al | 2024-10-25 | S2A_16SEB_20241025_0_L2A | 57.7 | 2.79 | 0.63 | 2.45 | 0.497 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2024-10-25_crop.png
birmingham_al | 2025-01-03 | S2A_16SEB_20250103_0_L2A | 57.7 | 2.71 | 0.5 | 2.38 | 0.385 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2025-01-03_crop.png
birmingham_al | 2025-04-16 | S2C_16SEB_20250416_0_L2A | 57.7 | 2.52 | 0.12 | 2.21 | 0.54 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2025-04-16_crop.png
birmingham_al | 2025-09-10 | S2C_16SEB_20250910_0_L2A | 57.7 | 2.82 | 0.4 | 1.9 | 0.528 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2025-09-10_crop.png
birmingham_al | 2025-11-14 | S2B_16SEB_20251114_0_L2A | 57.7 | 2.94 | 0.86 | 1.48 | 0.48 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2025-11-14_crop.png
birmingham_al | 2026-01-16 | S2B_16SEB_20260116_0_L2A | 57.7 | 2.74 | 1.54 | 1.08 | 0.406 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2026-01-16_crop.png
birmingham_al | 2026-04-20 | S2A_16SEC_20260420_0_L2A | 57.7 | 1.77 | 0.23 | 16.62 | 0.407 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2026-04-20_crop.png
birmingham_al | 2026-09-20 | S2B_16SEC_20260920_0_L2A | 57.7 | 3.02 | 1.07 | 17.13 | 0.319 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/detail/birmingham_al_2026-09-20_crop.png
independence_mo | 2023-02-05 | S2A_15SUD_20230205_0_L2A | 160.7 | 0.02 | 0.0 | 41.98 | 0.229 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2023-02-05_crop.png
independence_mo | 2023-06-20 | S2B_15SUD_20230620_0_L2A | 160.7 | 0.16 | 0.01 | 0.26 | 0.688 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2023-06-20_crop.png
independence_mo | 2023-07-10 | S2B_15SUD_20230710_0_L2A | 160.7 | 0.27 | 0.05 | 0.33 | 0.825 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2023-07-10_crop.png
independence_mo | 2023-11-12 | S2A_15SUD_20231112_0_L2A | 160.7 | 0.07 | 0.01 | 1.92 | 0.31 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2023-11-12_crop.png
independence_mo | 2024-01-31 | S2A_15SUD_20240131_0_L2A | 160.7 | 0.12 | 0.04 | 2.77 | 0.308 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2024-01-31_crop.png
independence_mo | 2024-06-24 | S2B_15SUD_20240624_0_L2A | 160.7 | 0.35 | 0.1 | 0.36 | 0.511 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2024-06-24_crop.png
independence_mo | 2024-09-07 | S2A_15SUD_20240907_0_L2A | 160.7 | 0.2 | 0.06 | 0.37 | 0.806 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2024-09-07_crop.png
independence_mo | 2024-10-07 | S2A_15SUD_20241007_0_L2A | 160.7 | 0.18 | 0.06 | 0.79 | 0.426 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2024-10-07_crop.png
independence_mo | 2025-03-11 | S2B_15SUD_20250311_0_L2A | 160.7 | 0.24 | 0.2 | 4.75 | 0.269 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2025-03-11_crop.png
independence_mo | 2025-04-07 | S2A_15SUD_20250407_0_L2A | 160.7 | 0.29 | 0.11 | 1.66 | 0.39 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2025-04-07_crop.png
independence_mo | 2025-07-09 | S2B_15SUD_20250709_0_L2A | 160.7 | 0.42 | 0.05 | 0.3 | 0.721 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2025-07-09_crop.png
independence_mo | 2025-11-03 | S2A_15SUD_20251103_0_L2A | 160.7 | 0.12 | 0.05 | 7.99 | 0.423 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2025-11-03_crop.png
independence_mo | 2026-01-12 | S2A_15SUD_20260112_0_L2A | 160.7 | 0.08 | 0.03 | 2.38 | 0.287 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2026-01-12_crop.png
independence_mo | 2026-04-20 | S2C_15SUD_20260420_0_L2A | 160.7 | 0.28 | 0.01 | 13.24 | 0.414 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2026-04-20_crop.png
independence_mo | 2026-09-02 | S2B_15SUD_20260902_0_L2A | 160.7 | 4.98 | 2.27 | 48.23 | 0.429 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2026-09-02_crop.png
independence_mo | 2026-10-02 | S2B_15SUD_20261002_0_L2A | 160.7 | 3.49 | 5.98 | 20.01 | 0.43 | /workspace/nebius/capacity/altdata/imagery/independence_mo/detail/independence_mo_2026-10-02_crop.png
mantsala_fi | 2023-04-22 | S2B_35VLH_20230422_0_L2A | 90.4 | 4.57 | 4.37 | 3.56 | 0.371 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2023-04-22_crop.png
mantsala_fi | 2023-08-07 | S2B_35VLH_20230807_0_L2A | 90.4 | 4.46 | 6.18 | 2.48 | 0.484 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2023-08-07_crop.png
mantsala_fi | 2023-10-29 | S2B_35VLH_20231029_0_L2A | 90.4 | 2.96 | 5.25 | 0.63 | 0.453 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2023-10-29_crop.png
mantsala_fi | 2024-05-18 | S2A_35VLH_20240518_0_L2A | 90.4 | 4.45 | 4.84 | 3.63 | 0.425 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2024-05-18_crop.png
mantsala_fi | 2024-09-05 | S2A_35VLH_20240905_0_L2A | 90.4 | 4.2 | 7.41 | 1.14 | 0.52 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2024-09-05_crop.png
mantsala_fi | 2024-11-17 | S2C_35VMH_20241117_1_L2A | 90.4 | 2.74 | 8.36 | 0.43 | 0.404 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2024-11-17_crop.png
mantsala_fi | 2025-03-19 | S2A_35VLH_20250319_1_L2A | 90.4 | 4.09 | 1.92 | 7.81 | 0.396 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2025-03-19_crop.png
mantsala_fi | 2025-05-11 | S2B_35VMH_20250511_0_L2A | 90.4 | 4.49 | 12.55 | 2.15 | 0.382 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2025-05-11_crop.png
mantsala_fi | 2025-07-24 | S2A_35VMH_20250724_1_L2A | 90.4 | 4.77 | 10.7 | 2.1 | 0.559 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2025-07-24_crop.png
mantsala_fi | 2025-10-18 | S2B_35VLH_20251018_1_L2A | 90.4 | 2.2 | 3.55 | 0.95 | 0.537 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2025-10-18_crop.png
mantsala_fi | 2026-03-24 | S2B_35VMH_20260324_1_L2A | 90.4 | 4.52 | 7.31 | 4.11 | 0.407 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2026-03-24_crop.png
mantsala_fi | 2026-05-30 | S2A_35VMH_20260530_1_L2A | 90.4 | 5.73 | 11.05 | 2.26 | 0.522 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2026-05-30_crop.png
mantsala_fi | 2026-09-27 | S2A_35VMH_20260927_1_L2A | 90.4 | 3.9 | 6.18 | 1.61 | 0.532 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/detail/mantsala_fi_2026-09-27_crop.png
vineland_nj | 2023-01-15 | S2A_18SVJ_20230115_0_L2A | 96.1 | 3.38 | 1.95 | 25.48 | 0.253 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-01-15_crop.png
vineland_nj | 2023-02-24 | S2A_18SVJ_20230224_0_L2A | 96.1 | 2.77 | 1.59 | 34.71 | 0.238 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-02-24_crop.png
vineland_nj | 2023-03-08 | S2B_18SVJ_20230308_0_L2A | 96.1 | 4.06 | 2.74 | 38.08 | 0.226 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-03-08_crop.png
vineland_nj | 2023-04-02 | S2A_18SVJ_20230402_0_L2A | 96.1 | 3.98 | 2.7 | 35.07 | 0.243 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-04-02_crop.png
vineland_nj | 2023-05-25 | S2A_18SVJ_20230525_0_L2A | 96.1 | 4.87 | 1.77 | 32.9 | 0.329 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-05-25_crop.png
vineland_nj | 2023-06-01 | S2A_18SVJ_20230601_0_L2A | 96.1 | 5.44 | 3.94 | 32.11 | 0.28 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-06-01_crop.png
vineland_nj | 2023-07-11 | S2A_18SVJ_20230711_0_L2A | 96.1 | 3.97 | 2.23 | 31.12 | 0.332 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-07-11_crop.png
vineland_nj | 2023-08-20 | S2A_18SVJ_20230820_0_L2A | 96.1 | 4.03 | 2.47 | 25.15 | 0.356 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-08-20_crop.png
vineland_nj | 2023-09-14 | S2B_18SVJ_20230914_0_L2A | 96.1 | 4.04 | 4.02 | 22.68 | 0.378 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-09-14_crop.png
vineland_nj | 2023-10-24 | S2B_18SVJ_20231024_0_L2A | 96.1 | 3.52 | 3.82 | 26.37 | 0.351 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-10-24_crop.png
vineland_nj | 2023-11-16 | S2B_18SVJ_20231116_0_L2A | 96.1 | 2.61 | 3.14 | 32.48 | 0.28 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-11-16_crop.png
vineland_nj | 2023-12-21 | S2A_18SVJ_20231221_0_L2A | 96.1 | 2.64 | 2.86 | 38.07 | 0.229 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2023-12-21_crop.png
vineland_nj | 2024-01-05 | S2B_18SVJ_20240105_0_L2A | 96.1 | 2.97 | 3.15 | 40.41 | 0.235 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-01-05_crop.png
vineland_nj | 2024-02-04 | S2B_18SVJ_20240204_0_L2A | 96.1 | 2.86 | 1.88 | 37.08 | 0.223 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-02-04_crop.png
vineland_nj | 2024-03-25 | S2B_18SVJ_20240325_0_L2A | 96.1 | 3.72 | 2.86 | 42.89 | 0.23 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-03-25_crop.png
vineland_nj | 2024-04-29 | S2A_18SVJ_20240429_0_L2A | 96.1 | 3.3 | 2.82 | 43.18 | 0.244 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-04-29_crop.png
vineland_nj | 2024-05-31 | S2B_18SVJ_20240531_0_L2A | 96.1 | 5.27 | 2.64 | 35.36 | 0.297 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-05-31_crop.png
vineland_nj | 2024-06-15 | S2A_18SVJ_20240615_0_L2A | 96.1 | 4.98 | 1.22 | 35.69 | 0.269 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-06-15_crop.png
vineland_nj | 2024-07-03 | S2B_18SVJ_20240703_0_L2A | 96.1 | 4.33 | 2.81 | 33.91 | 0.287 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-07-03_crop.png
vineland_nj | 2024-08-27 | S2A_18SVJ_20240827_0_L2A | 96.1 | 2.77 | 3.85 | 25.68 | 0.347 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-08-27_crop.png
vineland_nj | 2024-09-08 | S2B_18SVJ_20240908_0_L2A | 96.1 | 3.67 | 3.14 | 25.6 | 0.369 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-09-08_crop.png
vineland_nj | 2024-10-11 | S2B_18SVJ_20241011_0_L2A | 96.1 | 2.64 | 3.55 | 26.73 | 0.342 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-10-11_crop.png
vineland_nj | 2024-11-12 | S2A_18SVJ_20241112_0_L2A | 96.1 | 2.65 | 2.76 | 29.25 | 0.272 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-11-12_crop.png
vineland_nj | 2024-12-30 | S2B_18SVJ_20241230_0_L2A | 96.1 | 2.1 | 5.8 | 24.04 | 0.221 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2024-12-30_crop.png
vineland_nj | 2025-01-29 | S2B_18SVJ_20250129_0_L2A | 96.1 | 3.91 | 3.9 | 24.01 | 0.197 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-01-29_crop.png
vineland_nj | 2025-02-10 | S2C_18SVJ_20250210_0_L2A | 96.1 | 3.03 | 5.16 | 37.35 | 0.194 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-02-10_crop.png
vineland_nj | 2025-03-25 | S2C_18SVJ_20250325_0_L2A | 96.1 | 4.2 | 4.15 | 43.0 | 0.173 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-03-25_crop.png
vineland_nj | 2025-04-01 | S2C_18SVJ_20250401_0_L2A | 96.1 | 4.1 | 5.93 | 43.65 | 0.193 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-04-01_crop.png
vineland_nj | 2025-05-19 | S2B_18SVJ_20250519_0_L2A | 96.1 | 5.64 | 4.8 | 42.54 | 0.248 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-05-19_crop.png
vineland_nj | 2025-06-03 | S2C_18SVJ_20250603_0_L2A | 96.1 | 3.67 | 1.48 | 42.02 | 0.27 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-06-03_crop.png
vineland_nj | 2025-07-25 | S2B_18SVJ_20250725_0_L2A | 96.1 | 6.06 | 4.51 | 38.31 | 0.242 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-07-25_crop.png
vineland_nj | 2025-08-22 | S2C_18SVJ_20250822_0_L2A | 96.1 | 4.4 | 2.12 | 40.35 | 0.272 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-08-22_crop.png
vineland_nj | 2025-09-23 | S2B_18SVJ_20250923_1_L2A | 96.1 | 4.91 | 3.4 | 41.68 | 0.25 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-09-23_crop.png
vineland_nj | 2025-10-16 | S2B_18SVJ_20251016_0_L2A | 96.1 | 3.58 | 2.27 | 38.38 | 0.282 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-10-16_crop.png
vineland_nj | 2025-11-29 | S2A_18SVJ_20251129_0_L2A | 96.1 | 3.62 | 3.18 | 43.57 | 0.209 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-11-29_crop.png
vineland_nj | 2025-12-22 | S2B_18SVJ_20251222_0_L2A | 96.1 | 4.76 | 6.73 | 38.63 | 0.184 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2025-12-22_crop.png
vineland_nj | 2026-01-04 | S2B_18SVJ_20260104_0_L2A | 96.1 | 3.76 | 5.45 | 44.99 | 0.168 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2026-01-04_crop.png
vineland_nj | 2026-03-09 | S2A_18SVJ_20260309_0_L2A | 96.1 | 5.15 | 2.05 | 45.5 | 0.137 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2026-03-09_crop.png
vineland_nj | 2026-04-06 | S2C_18SVJ_20260406_1_L2A | 96.1 | 5.96 | 5.45 | 47.66 | 0.174 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2026-04-06_crop.png
vineland_nj | 2026-05-04 | S2B_18SVJ_20260504_0_L2A | 96.1 | 6.59 | 5.41 | 47.65 | 0.202 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2026-05-04_crop.png
vineland_nj | 2026-06-03 | S2B_18SVJ_20260603_0_L2A | 96.1 | 8.84 | 4.78 | 47.42 | 0.209 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2026-06-03_crop.png
vineland_nj | 2026-07-20 | S2B_18SVJ_20260720_0_L2A | 96.1 | 9.05 | 4.25 | 38.6 | 0.253 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2026-07-20_crop.png
vineland_nj | 2026-08-24 | S2C_18SVJ_20260824_0_L2A | 96.1 | 7.99 | 5.67 | 39.21 | 0.25 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2026-08-24_crop.png
vineland_nj | 2026-09-08 | S2B_18SVJ_20260908_1_L2A | 96.1 | 9.09 | 7.17 | 36.05 | 0.252 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/detail/vineland_nj_2026-09-08_crop.png

## Imagery_AOI_metrics
site | period | date | scene | scene_cloud | aoi_cloud | aoi_snow | valid_frac | ndvi_mean | ndbi_mean | bsi_mean | builtbare_ha | brightroof_ha | chip
bethune_fr | 2023-01-01 | 2023-02-14 | S2A_31UDS_20230214_0_L2A | 0.023548 | 0 | 0 | 1 | 0.3577 | -0.0044 | 0.0367 | 83.91 | 2.01 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2023-02-14.png
bethune_fr | 2023-04-01 | 2023-06-04 | S2A_31UDR_20230604_0_L2A | 0.005199 | 0 | 0 | 1 | 0.4521 | -0.1252 | -0.0757 | 60.7 | 4.41 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2023-06-04.png
bethune_fr | 2023-07-01 | 2023-09-07 | S2B_31UDR_20230907_0_L2A | 0.002203 | 0 | 0 | 1 | 0.4664 | -0.079 | -0.0559 | 69.75 | 3.09 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2023-09-07.png
bethune_fr | 2023-10-01 | 2023-10-07 | S2B_31UDR_20231007_0_L2A | 8.1603 | 0 | 0 | 1 | 0.3846 | -0.0235 | 0.0067 | 79.72 | 2.79 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2023-10-07.png
bethune_fr | 2024-01-01 | 2024-01-10 | S2A_31UDS_20240110_0_L2A | 3.4346 | 0.0007 | 0.0026 | 0.996 | 0.343 | -0.0192 | 0.0077 | 76.51 | 1.54 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2024-01-10.png
bethune_fr | 2024-04-01 | 2024-06-26 | S2B_31UDR_20240626_0_L2A | 2.6388 | 0 | 0 | 1 | 0.4965 | -0.1334 | -0.1036 | 62.12 | 4.62 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2024-06-26.png
bethune_fr | 2024-07-01 | 2024-09-19 | S2A_31UDR_20240919_0_L2A | 0.001074 | 0 | 0 | 1 | 0.4168 | -0.0578 | -0.032 | 66.99 | 2.06 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2024-09-19.png
bethune_fr | 2024-10-01 | 2024-10-24 | S2B_31UDS_20241024_0_L2A | 0.014841 | 0 | 0 | 1 | 0.4472 | -0.0732 | -0.039 | 47.32 | 1.68 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2024-10-24.png
bethune_fr | 2025-01-01 | 2025-03-20 | S2B_31UDR_20250320_0_L2A | 0.001745 | 0 | 0 | 1 | 0.3415 | 0.0386 | 0.0553 | 102.03 | 2.41 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2025-03-20.png
bethune_fr | 2025-04-01 | 2025-04-29 | S2A_31UDR_20250429_1_L2A | 0.001865 | 0 | 0 | 1 | 0.4472 | -0.108 | -0.067 | 71.44 | 3.23 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2025-04-29.png
bethune_fr | 2025-07-01 | 2025-08-12 | S2C_31UDR_20250812_0_L2A | 0.001198 | 0 | 0 | 1 | 0.3906 | -0.0334 | -0.001 | 84.2 | 3.57 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2025-08-12.png
bethune_fr | 2025-10-01 | 2025-12-25 | S2B_31UDS_20251225_0_L2A | 1.3399 | 0 | 0 | 1 | 0.3517 | -0.0176 | -0.0336 | 78.74 | 2.78 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2025-12-25.png
bethune_fr | 2026-01-01 | 2026-03-18 | S2B_31UDR_20260318_0_L2A | 0.074473 | 0 | 0 | 1 | 0.4334 | -0.0617 | -0.0233 | 58.77 | 5.14 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2026-03-18.png
bethune_fr | 2026-04-01 | 2026-05-01 | S2A_31UDR_20260501_0_L2A | 0.001958 | 0 | 0 | 1 | 0.4693 | -0.1267 | -0.0837 | 66.67 | 6.96 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2026-05-01.png
bethune_fr | 2026-07-01 | 2026-08-12 | S2B_31UDR_20260812_0_L2A | 0.001928 | 0 | 0 | 1 | 0.3487 | -0.0073 | 0.0273 | 94.88 | 8.51 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2026-08-12.png
bethune_fr | 2026-10-01 | 2026-10-04 | S2B_31UDR_20261004_0_L2A | 0.001943 | 0 | 0 | 1 | 0.4049 | -0.0336 | -0.0096 | 74.45 | 6.29 | /workspace/nebius/capacity/altdata/imagery/bethune_fr/bethune_fr_2026-10-04.png
birmingham_al | 2023-01-01 | 2023-01-07 | S2A_16SEB_20230107_0_L2A | 0.00032 | 0 | 0 | 1 | 0.4096 | 0.0964 | 0.1231 | 42.75 | 2.55 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2023-01-07.png
birmingham_al | 2023-04-01 | 2023-04-19 | S2B_16SEB_20230419_0_L2A | 0.000787 | 0 | 0 | 1 | 0.6296 | -0.1883 | -0.154 | 26.75 | 4.25 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2023-04-19.png
birmingham_al | 2023-07-01 | 2023-09-29 | S2B_16SEB_20230929_0_L2A | 0.003399 | 0 | 0 | 1 | 0.6094 | -0.1819 | -0.1497 | 21.3 | 3.79 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2023-09-29.png
birmingham_al | 2023-10-01 | 2023-12-28 | S2B_16SEB_20231228_0_L2A | 9.3e-05 | 0 | 0 | 1 | 0.4557 | 0.014 | 0.0578 | 32.41 | 3.27 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2023-12-28.png
birmingham_al | 2024-01-01 | 2024-02-06 | S2B_16SEB_20240206_0_L2A | 0.000426 | 0 | 0 | 1 | 0.4259 | 0.0461 | 0.0851 | 37.99 | 3.73 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2024-02-06.png
birmingham_al | 2024-04-01 | 2024-04-13 | S2B_16SEC_20240413_0_L2A | 0.000665 | 0 | 0 | 1 | 0.6073 | -0.1499 | -0.1179 | 26.8 | 4.63 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2024-04-13.png
birmingham_al | 2024-07-01 | 2024-08-24 | S2B_16SEC_20240824_0_L2A | 0.000485 | 0 | 0 | 1 | 0.6672 | -0.2217 | -0.1895 | 22.4 | 6.4 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2024-08-24.png
birmingham_al | 2024-10-01 | 2024-10-25 | S2A_16SEB_20241025_0_L2A | 0.000335 | 0 | 0 | 1 | 0.5821 | -0.103 | -0.0621 | 35.36 | 7.34 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2024-10-25.png
birmingham_al | 2025-01-01 | 2025-01-03 | S2A_16SEB_20250103_0_L2A | 0.001268 | 0 | 0 | 1 | 0.4148 | 0.0684 | 0.0997 | 40.89 | 3.69 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2025-01-03.png
birmingham_al | 2025-04-01 | 2025-04-16 | S2C_16SEB_20250416_0_L2A | 0.004953 | 0.0002 | 0 | 1 | 0.622 | -0.1972 | -0.151 | 25.24 | 5.27 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2025-04-16.png
birmingham_al | 2025-07-01 | 2025-09-10 | S2C_16SEB_20250910_0_L2A | 0.01311 | 0 | 0 | 1 | 0.6266 | -0.1602 | -0.1274 | 26.23 | 5.11 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2025-09-10.png
birmingham_al | 2025-10-01 | 2025-11-14 | S2B_16SEB_20251114_0_L2A | 0.000359 | 0 | 0 | 1 | 0.5006 | -0.0253 | 0.0081 | 39.9 | 3.78 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2025-11-14.png
birmingham_al | 2026-01-01 | 2026-01-16 | S2B_16SEB_20260116_0_L2A | 0.000896 | 0 | 0 | 1 | 0.424 | 0.0456 | 0.0802 | 43.59 | 3.32 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2026-01-16.png
birmingham_al | 2026-04-01 | 2026-04-20 | S2A_16SEC_20260420_0_L2A | 0.001311 | 0 | 0 | 1 | 0.583 | -0.1791 | -0.1363 | 43.09 | 5.82 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2026-04-20.png
birmingham_al | 2026-07-01 | 2026-09-20 | S2B_16SEC_20260920_0_L2A | 0.019485 | 0 | 0 | 1 | 0.5371 | -0.0839 | -0.0638 | 49.88 | 3.9 | /workspace/nebius/capacity/altdata/imagery/birmingham_al/birmingham_al_2026-09-20.png
butler_pa | 2023-01-01 | 2023-02-14 | S2A_18TUL_20230214_0_L2A | 0.067301 | 0 | 0 | 1 | 0.4322 | 0.1361 | 0.1756 | 244.89 | 32.63 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2023-02-14.png
butler_pa | 2023-04-01 | 2023-04-10 | S2B_18TUL_20230410_0_L2A | 0.033943 | 0.0006 | 0 | 0.999 | 0.3951 | 0.1241 | 0.1408 | 254.81 | 34.94 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2023-04-10.png
butler_pa | 2023-10-01 | 2023-11-19 | S2B_18TUL_20231119_1_L2A | 0.51965 | 0 | 0 | 0.967 | 0.4531 | 0.07 | 0.0958 | 191.41 | 33.24 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2023-11-19.png
butler_pa | 2024-01-01 | 2024-02-04 | S2B_18TUL_20240204_0_L2A | 0.007717 | 0 | 0 | 1 | 0.4644 | 0.1036 | 0.1457 | 226.55 | 33.98 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2024-02-04.png
butler_pa | 2024-04-01 | 2024-05-24 | S2B_18TUL_20240524_0_L2A | 1.5617 | 0 | 0 | 1 | 0.7567 | -0.2947 | -0.2647 | 159.12 | 42.43 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2024-05-24.png
butler_pa | 2024-07-01 | 2024-07-26 | S2B_18TUL_20240726_0_L2A | 0.55546 | 0.0001 | 0 | 0.955 | 0.7654 | -0.2932 | -0.2668 | 131.38 | 50.21 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2024-07-26.png
butler_pa | 2024-10-01 | 2024-10-21 | S2B_18TUL_20241021_0_L2A | 0.000881 | 0 | 0 | 1 | 0.4965 | 0.0145 | 0.0702 | 238.48 | 34.75 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2024-10-21.png
butler_pa | 2025-01-01 | 2025-03-10 | S2B_18TUL_20250310_0_L2A | 0.001831 | 0 | 0 | 1 | 59.8758 | 1.3007 | 7.1338 | 341.83 | 30.78 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2025-03-10.png
butler_pa | 2025-04-01 | 2025-06-03 | S2C_18TUL_20250603_0_L2A | 0.027502 | 0 | 0 | 1 | 0.7014 | -0.2379 | -0.2018 | 192.32 | 44.94 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2025-06-03.png
butler_pa | 2025-07-01 | 2025-08-10 | S2B_18TUL_20250810_0_L2A | 0.000634 | 0 | 0 | 0.959 | 0.7513 | -0.2371 | -0.214 | 177.28 | 46.55 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2025-08-10.png
butler_pa | 2025-10-01 | 2025-10-16 | S2B_18TUL_20251016_2_L2A | 0.001 | 0 | 0 | 1 | 0.6302 | -0.0675 | -0.0148 | 203.69 | 34.82 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2025-10-16.png
butler_pa | 2026-04-01 | 2026-06-03 | S2B_18TUL_20260603_0_L2A | 0.001248 | 0 | 0 | 1 | 0.6926 | -0.2172 | -0.189 | 206.28 | 47.44 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2026-06-03.png
butler_pa | 2026-07-01 | 2026-07-23 | S2B_18TUL_20260723_0_L2A | 0.018341 | 0 | 0 | 1 | 0.7411 | -0.2772 | -0.2484 | 151.44 | 44.57 | /workspace/nebius/capacity/altdata/imagery/butler_pa/butler_pa_2026-07-23.png
independence_mo | 2023-01-01 | 2023-02-05 | S2A_15SUD_20230205_0_L2A | 0.002641 | 0 | 0 | 1 | 0.268 | 0.22 | 0.2572 | 339.3 | 3.05 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2023-02-05.png
independence_mo | 2023-04-01 | 2023-06-20 | S2B_15SUD_20230620_0_L2A | 0.00038 | 0 | 0 | 1 | 0.6617 | -0.1238 | -0.0999 | 21.61 | 2.94 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2023-06-20.png
independence_mo | 2023-07-01 | 2023-07-10 | S2B_15SUD_20230710_0_L2A | 0.000989 | 0 | 0 | 1 | 0.7676 | -0.2501 | -0.2202 | 25.1 | 4.85 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2023-07-10.png
independence_mo | 2023-10-01 | 2023-11-12 | S2A_15SUD_20231112_0_L2A | 0.000383 | 0 | 0 | 1 | 0.3675 | 0.1918 | 0.2158 | 177.29 | 2.19 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2023-11-12.png
independence_mo | 2024-01-01 | 2024-01-31 | S2A_15SUD_20240131_0_L2A | 0.002252 | 0 | 0 | 1 | 0.3325 | 0.1926 | 0.2282 | 82.55 | 1.66 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2024-01-31.png
independence_mo | 2024-04-01 | 2024-06-24 | S2B_15SUD_20240624_0_L2A | 0.000586 | 0 | 0 | 1 | 0.5869 | -0.0458 | -0.0312 | 28.4 | 5.93 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2024-06-24.png
independence_mo | 2024-07-01 | 2024-09-07 | S2A_15SUD_20240907_0_L2A | 0.4899 | 0.0032 | 0 | 0.997 | 0.7231 | -0.2146 | -0.1772 | 32.45 | 4.98 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2024-09-07.png
independence_mo | 2024-10-01 | 2024-10-07 | S2A_15SUD_20241007_0_L2A | 0.00025 | 0 | 0 | 1 | 0.5047 | 0.0245 | 0.069 | 39.44 | 3.68 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2024-10-07.png
independence_mo | 2025-01-01 | 2025-03-11 | S2B_15SUD_20250311_0_L2A | 11.1424 | 0 | 0 | 1 | 0.2796 | 0.2174 | 0.2151 | 125.87 | 3.54 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2025-03-11.png
independence_mo | 2025-04-01 | 2025-04-07 | S2A_15SUD_20250407_0_L2A | 0.006239 | 0.0015 | 0 | 0.999 | 0.4107 | 0.0981 | 0.1214 | 52.31 | 3.25 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2025-04-07.png
independence_mo | 2025-07-01 | 2025-07-09 | S2B_15SUD_20250709_0_L2A | 0.97367 | 0 | 0 | 1 | 0.6908 | -0.1302 | -0.1048 | 41.26 | 5.73 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2025-07-09.png
independence_mo | 2025-10-01 | 2025-11-03 | S2A_15SUD_20251103_0_L2A | 0.001599 | 0 | 0 | 1 | 0.4518 | 0.0875 | 0.1226 | 141.43 | 2.25 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2025-11-03.png
independence_mo | 2026-01-01 | 2026-01-12 | S2A_15SUD_20260112_0_L2A | 0.007687 | 0 | 0 | 1 | 0.2994 | 0.2142 | 0.2354 | 121.3 | 1.56 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2026-01-12.png
independence_mo | 2026-04-01 | 2026-04-20 | S2C_15SUD_20260420_0_L2A | 0.000912 | 0 | 0 | 1 | 0.5199 | -0.0343 | 0.0011 | 86.86 | 3.55 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2026-04-20.png
independence_mo | 2026-07-01 | 2026-09-02 | S2B_15SUD_20260902_0_L2A | 0.00016 | 0 | 0 | 1 | 0.6393 | -0.1484 | -0.1242 | 119.44 | 9.46 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2026-09-02.png
independence_mo | 2026-10-01 | 2026-10-02 | S2B_15SUD_20261002_0_L2A | 0.000376 | 0 | 0 | 1 | 0.6411 | -0.165 | -0.1234 | 93.5 | 2.86 | /workspace/nebius/capacity/altdata/imagery/independence_mo/independence_mo_2026-10-02.png
kansascity_mo | 2023-01-01 | 2023-02-03 | S2B_15SUD_20230203_0_L2A | 0.001556 | 0 | 0 | 1 | 0.0842 | 0.0988 | 0.1303 | 50.23 | 9.8 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2023-02-03.png
kansascity_mo | 2023-04-01 | 2023-06-20 | S2B_15SUD_20230620_0_L2A | 0.00038 | 0 | 0 | 1 | 0.0931 | 0.0661 | 0.0839 | 53.5 | 14.68 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2023-06-20.png
kansascity_mo | 2023-07-01 | 2023-07-10 | S2B_15SUD_20230710_0_L2A | 0.000989 | 0 | 0 | 1 | 0.0907 | 0.0627 | 0.087 | 51.94 | 15.65 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2023-07-10.png
kansascity_mo | 2023-10-01 | 2023-11-12 | S2A_15SUD_20231112_0_L2A | 0.000383 | 0 | 0 | 1 | 0.0847 | 0.0841 | 0.1225 | 50.12 | 9.56 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2023-11-12.png
kansascity_mo | 2024-01-01 | 2024-03-19 | S2B_15SUD_20240319_0_L2A | 0.00095 | 0 | 0 | 1 | 0.0768 | 0.0729 | 0.0995 | 52.85 | 11.74 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2024-03-19.png
kansascity_mo | 2024-04-01 | 2024-04-08 | S2B_15SUD_20240408_0_L2A | 0.000355 | 0 | 0 | 1 | 0.0825 | 0.0606 | 0.0932 | 52.32 | 13.01 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2024-04-08.png
kansascity_mo | 2024-07-01 | 2024-09-10 | S2A_15SUD_20240910_0_L2A | 0.071086 | 0.003 | 0 | 0.997 | 0.1359 | 0.0234 | 0.052 | 49.11 | 7.39 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2024-09-10.png
kansascity_mo | 2024-10-01 | 2024-10-07 | S2A_15SUD_20241007_0_L2A | 0.00025 | 0 | 0 | 1 | 0.0913 | 0.0678 | 0.1043 | 49.58 | 11.79 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2024-10-07.png
kansascity_mo | 2025-01-01 | 2025-02-27 | S2C_15SUD_20250227_0_L2A | 0.009686 | 0 | 0 | 1 | 1.757 | 0.0758 | 0.0431 | 35.36 | 4.98 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2025-02-27.png
kansascity_mo | 2025-04-01 | 2025-04-07 | S2A_15SUD_20250407_0_L2A | 0.006239 | 0 | 0 | 1 | 0.0862 | 0.0404 | 0.0827 | 50.4 | 14.33 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2025-04-07.png
kansascity_mo | 2025-07-01 | 2025-08-08 | S2A_15SUD_20250808_1_L2A | 0.004744 | 0 | 0 | 1 | 0.096 | 0.0928 | 0.1096 | 54.34 | 11.29 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2025-08-08.png
kansascity_mo | 2025-10-01 | 2025-10-20 | S2B_15SUD_20251020_0_L2A | 0.000877 | 0 | 0 | 1 | 0.0848 | 0.0806 | 0.105 | 51.56 | 10.76 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2025-10-20.png
kansascity_mo | 2026-01-01 | 2026-03-09 | S2B_15SUD_20260309_0_L2A | 0.000916 | 0 | 0 | 1 | 0.0643 | 0.08 | 0.1036 | 52.84 | 12.18 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2026-03-09.png
kansascity_mo | 2026-04-01 | 2026-04-20 | S2C_15SUD_20260420_0_L2A | 0.000912 | 0 | 0 | 1 | 0.0989 | 0.0377 | 0.0779 | 48.97 | 15.68 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2026-04-20.png
kansascity_mo | 2026-07-01 | 2026-09-02 | S2B_15SUD_20260902_0_L2A | 0.00016 | 0 | 0 | 1 | 0.0699 | 0.0869 | 0.097 | 53.91 | 14.3 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2026-09-02.png
kansascity_mo | 2026-10-01 | 2026-10-02 | S2B_15SUD_20261002_0_L2A | 0.000376 | 0 | 0 | 1 | 0.0914 | 0.0527 | 0.0824 | 48.59 | 13.73 | /workspace/nebius/capacity/altdata/imagery/kansascity_mo/kansascity_mo_2026-10-02.png
keflavik_is | 2023-01-01 | 2023-03-08 | S2A_27VVL_20230308_0_L2A | 2.829 | 0.0163 | 0 | 0.983 | 0.2862 | 0.0418 | 0.0969 | 108.16 | 3.04 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2023-03-08.png
keflavik_is | 2023-04-01 | 2023-04-30 | S2A_27WVM_20230430_0_L2A | 2.2125 | 0 | 0 | 1 | 0.2552 | 0.077 | 0.1136 | 125.76 | 2.9 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2023-04-30.png
keflavik_is | 2023-07-01 | 2023-08-13 | S2B_27WVM_20230813_0_L2A | 0.001017 | 0 | 0 | 1 | 0.4702 | -0.081 | -0.0409 | 83.04 | 2.64 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2023-08-13.png
keflavik_is | 2023-10-01 | 2023-10-31 | S2A_27WVM_20231031_0_L2A | 1.0203 | 0.0015 | 0.0024 | 0.996 | 0.2797 | -0.0533 | -0.0324 | 98.8 | 3.52 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2023-10-31.png
keflavik_is | 2024-01-01 | 2024-03-30 | S2B_27VVL_20240330_0_L2A | 0.23166 | 0.0159 | 0 | 0.985 | 0.2543 | 0.0657 | 0.1012 | 132.1 | 3.87 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2024-03-30.png
keflavik_is | 2024-04-01 | 2024-05-14 | S2A_27WVM_20240514_0_L2A | 0.54463 | 0 | 0 | 1 | 0.2706 | 0.0688 | 0.103 | 120.21 | 3.66 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2024-05-14.png
keflavik_is | 2024-07-01 | 2024-09-15 | S2A_27VVL_20240915_0_L2A | 0.017878 | 0.0022 | 0 | 0.998 | 0.4231 | -0.0733 | -0.0237 | 85.14 | 3.54 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2024-09-15.png
keflavik_is | 2024-10-01 | 2024-10-05 | S2A_27VVL_20241005_0_L2A | 0.061782 | 0.0006 | 0 | 0.999 | 0.371 | -0.0684 | 0.0014 | 83.79 | 3.71 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2024-10-05.png
keflavik_is | 2025-01-01 | 2025-02-15 | S2C_27WVM_20250215_1_L2A | 22.2548 | 0 | 0 | 1 | 5.3898 | 2.0696 | 3.0621 | 60.11 | 1.82 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2025-02-15.png
keflavik_is | 2025-04-01 | 2025-06-13 | S2B_27VVL_20250613_0_L2A | 0.000515 | 0 | 0 | 1 | 0.4156 | -0.051 | -0.0098 | 90.09 | 3.68 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2025-06-13.png
keflavik_is | 2025-07-01 | 2025-09-18 | S2B_27VVL_20250918_1_L2A | 1.929 | 0.0001 | 0 | 1 | 0.4888 | -0.1269 | -0.0719 | 75.97 | 5.04 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2025-09-18.png
keflavik_is | 2025-10-01 | 2025-11-11 | S2A_27WVM_20251111_1_L2A | 1.7413 | 0.0038 | 0.0131 | 0.983 | 0.2507 | -0.0832 | -0.0759 | 101.17 | 6.02 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2025-11-11.png
keflavik_is | 2026-01-01 | 2026-02-08 | S2B_27VVL_20260208_0_L2A | 0.83299 | 0.0091 | 0.004 | 0.987 | 0.2464 | -0.0878 | -0.0633 | 97.26 | 4.3 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2026-02-08.png
keflavik_is | 2026-04-01 | 2026-05-04 | S2C_27VVL_20260504_0_L2A | 0.14377 | 0.04 | 0 | 0.961 | 0.2633 | 0.0642 | 0.1042 | 121.32 | 3.73 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2026-05-04.png
keflavik_is | 2026-07-01 | 2026-09-08 | S2C_27WVM_20260908_0_L2A | 0.00278 | 0 | 0 | 1 | 0.4806 | -0.1013 | -0.0361 | 82.29 | 3.64 | /workspace/nebius/capacity/altdata/imagery/keflavik_is/keflavik_is_2026-09-08.png
lappeenranta_fi | 2023-04-01 | 2023-04-19 | S2B_35VNH_20230419_0_L2A | 0.002283 | 0 | 0.0869 | 0.913 | 0.1234 | -0.1395 | 0.0335 | 490.39 | 292.34 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2023-04-19.png
lappeenranta_fi | 2023-07-01 | 2023-08-07 | S2B_35VNH_20230807_0_L2A | 0.35992 | 0 | 0 | 1 | 0.3884 | -0.1306 | -0.1088 | 273.29 | 5.34 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2023-08-07.png
lappeenranta_fi | 2023-10-01 | 2023-10-21 | S2A_35VNH_20231021_0_L2A | 2.3869 | 0 | 0 | 1 | 0.3534 | -0.1011 | 0.0278 | 308.78 | 4.03 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2023-10-21.png
lappeenranta_fi | 2024-04-01 | 2024-05-18 | S2A_35VNH_20240518_0_L2A | 0.10617 | 0 | 0 | 1 | 0.3337 | -0.0226 | 0.0157 | 501.87 | 7.66 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2024-05-18.png
lappeenranta_fi | 2024-07-01 | 2024-09-05 | S2A_35VNH_20240905_0_L2A | 0.49211 | 0 | 0 | 1 | 0.4043 | -0.1264 | -0.0841 | 273.09 | 5.1 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2024-09-05.png
lappeenranta_fi | 2024-10-01 | 2024-11-19 | S2B_35VNH_20241119_0_L2A | 46.6494 | 0.0453 | 0.0102 | 0.945 | 0.1486 | -0.1839 | -0.205 | 321.42 | 7.24 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2024-11-19.png
lappeenranta_fi | 2025-01-01 | 2025-03-29 | S2B_35VNH_20250329_0_L2A | 0.43518 | 0 | 0.115 | 0.885 | 0.123 | -0.1438 | 0.012 | 397.1 | 78.68 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2025-03-29.png
lappeenranta_fi | 2025-04-01 | 2025-06-14 | S2B_35VNH_20250614_0_L2A | 0.13328 | 0 | 0 | 1 | 0.409 | -0.17 | -0.1373 | 241.33 | 9.35 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2025-06-14.png
lappeenranta_fi | 2025-07-01 | 2025-07-19 | S2C_35VNH_20250719_0_L2A | 0.11414 | 0 | 0 | 1 | 0.4322 | -0.1586 | -0.1169 | 244.12 | 9.23 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2025-07-19.png
lappeenranta_fi | 2025-10-01 | 2025-10-17 | S2C_35VNH_20251017_0_L2A | 0.044191 | 0.0002 | 0 | 1 | 0.3632 | 0.0759 | 0.1544 | 426.46 | 4.77 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2025-10-17.png
lappeenranta_fi | 2026-01-01 | 2026-03-28 | S2A_35VNH_20260328_0_L2A | 0.002504 | 0 | 0.0023 | 0.998 | 0.2251 | -0.0012 | 0.0886 | 449.99 | 6.21 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2026-03-28.png
lappeenranta_fi | 2026-04-01 | 2026-06-22 | S2B_35VNH_20260622_0_L2A | 0.13649 | 0 | 0 | 1 | 0.4207 | -0.1293 | -0.107 | 445.14 | 8.79 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2026-06-22.png
lappeenranta_fi | 2026-07-01 | 2026-09-14 | S2A_35VNH_20260914_0_L2A | 0.44185 | 0 | 0.001 | 0.999 | 0.4369 | -0.1474 | -0.0361 | 260.69 | 4.92 | /workspace/nebius/capacity/altdata/imagery/lappeenranta_fi/lappeenranta_fi_2026-09-14.png
longcross_uk | 2023-01-01 | 2023-01-21 | S2A_30UXC_20230121_0_L2A | 3.176 | 0 | 0 | 1 | 0.533 | -0.1016 | -0.0137 | 14.78 | 2.56 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2023-01-21.png
longcross_uk | 2023-04-01 | 2023-05-26 | S2B_30UXB_20230526_0_L2A | 0.009194 | 0 | 0 | 1 | 0.5696 | -0.1549 | -0.1102 | 21.53 | 4.17 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2023-05-26.png
longcross_uk | 2023-07-01 | 2023-09-05 | S2A_30UXB_20230905_0_L2A | 0.004322 | 0.0018 | 0 | 0.95 | 0.5637 | -0.1636 | -0.1078 | 17.21 | 2.93 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2023-09-05.png
longcross_uk | 2023-10-01 | 2023-11-17 | S2A_30UXC_20231117_0_L2A | 9.7046 | 0 | 0 | 1 | 0.5751 | -0.1664 | -0.065 | 12.56 | 2.3 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2023-11-17.png
longcross_uk | 2024-01-01 | 2024-01-26 | S2A_30UXC_20240126_0_L2A | 0.005776 | 0 | 0 | 1 | 0.5018 | -0.0632 | 0.0205 | 17.65 | 2.29 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2024-01-26.png
longcross_uk | 2024-04-01 | 2024-05-20 | S2B_30UXB_20240520_0_L2A | 0.005856 | 0 | 0 | 1 | 0.5944 | -0.1668 | -0.1272 | 20.38 | 3.49 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2024-05-20.png
longcross_uk | 2024-07-01 | 2024-07-29 | S2B_30UXB_20240729_0_L2A | 0.055308 | 0 | 0 | 1 | 0.6166 | -0.1827 | -0.1482 | 23.09 | 3.49 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2024-07-29.png
longcross_uk | 2024-10-01 | 2024-11-26 | S2B_30UXC_20241126_0_L2A | 0.017203 | 0 | 0 | 1 | 0.5489 | -0.0934 | -0.0494 | 16.79 | 2.28 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2024-11-26.png
longcross_uk | 2025-01-01 | 2025-01-30 | S2C_30UXB_20250130_0_L2A | 0.023069 | 0.0005 | 0 | 0.999 | 82.853 | -3.2067 | 6.4787 | 30.58 | 1.62 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2025-01-30.png
longcross_uk | 2025-04-01 | 2025-04-30 | S2C_30UXB_20250430_0_L2A | 0.00634 | 0 | 0 | 1 | 0.5418 | -0.1268 | -0.0806 | 20.11 | 3.01 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2025-04-30.png
longcross_uk | 2025-07-01 | 2025-09-19 | S2A_30UXB_20250919_1_L2A | 3.7041 | 0 | 0 | 1 | 0.6023 | -0.1537 | -0.1083 | 20.61 | 2.6 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2025-09-19.png
longcross_uk | 2025-10-01 | 2025-11-21 | S2B_30UXB_20251121_0_L2A | 1.5452 | 0 | 0 | 1 | 0.574 | -0.1151 | -0.0628 | 14.48 | 2.32 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2025-11-21.png
longcross_uk | 2026-01-01 | 2026-03-18 | S2A_30UXB_20260318_1_L2A | 0.007802 | 0 | 0 | 1 | 0.4562 | 0.0149 | 0.0649 | 23.52 | 2.91 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2026-03-18.png
longcross_uk | 2026-04-01 | 2026-05-25 | S2C_30UXC_20260525_0_L2A | 0.001928 | 0 | 0 | 1 | 0.5711 | -0.1321 | -0.0857 | 22.47 | 4.67 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2026-05-25.png
longcross_uk | 2026-07-01 | 2026-07-29 | S2B_30UXB_20260729_0_L2A | 0.004104 | 0 | 0 | 1 | 0.5447 | -0.1288 | -0.0875 | 26.53 | 4.54 | /workspace/nebius/capacity/altdata/imagery/longcross_uk/longcross_uk_2026-07-29.png
mantsala_fi | 2023-04-01 | 2023-04-22 | S2B_35VLH_20230422_0_L2A | 5.3e-05 | 0 | 0.0011 | 0.999 | 0.4222 | 0.0255 | 0.0668 | 221.78 | 5.32 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2023-04-22.png
mantsala_fi | 2023-07-01 | 2023-08-07 | S2B_35VLH_20230807_0_L2A | 0.002846 | 0 | 0 | 1 | 0.6388 | -0.1815 | -0.152 | 90.79 | 4.06 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2023-08-07.png
mantsala_fi | 2023-10-01 | 2023-10-29 | S2B_35VLH_20231029_0_L2A | 0.11685 | 0.0015 | 0 | 0.999 | 0.5537 | -0.1257 | -0.0957 | 90.45 | 2.95 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2023-10-29.png
mantsala_fi | 2024-04-01 | 2024-05-18 | S2A_35VLH_20240518_0_L2A | 0.000518 | 0 | 0 | 1 | 0.523 | -0.0751 | -0.0301 | 161.91 | 4.37 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2024-05-18.png
mantsala_fi | 2024-07-01 | 2024-09-05 | S2A_35VLH_20240905_0_L2A | 0.06959 | 0 | 0 | 1 | 0.6417 | -0.1709 | -0.1278 | 95.96 | 3.97 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2024-09-05.png
mantsala_fi | 2024-10-01 | 2024-11-17 | S2C_35VMH_20241117_1_L2A | 3.2723 | 0 | 0 | 1 | 0.505 | -0.1623 | -0.1713 | 97.39 | 2.89 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2024-11-17.png
mantsala_fi | 2025-01-01 | 2025-03-19 | S2A_35VLH_20250319_1_L2A | 0.019081 | 0 | 0.0735 | 0.927 | 0.4554 | -0.0783 | 0.0037 | 122.94 | 5.4 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2025-03-19.png
mantsala_fi | 2025-04-01 | 2025-05-11 | S2B_35VMH_20250511_0_L2A | 0.023636 | 0.0007 | 0 | 0.999 | 0.465 | -0.0321 | 0.0033 | 152.02 | 4.68 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2025-05-11.png
mantsala_fi | 2025-07-01 | 2025-07-24 | S2A_35VMH_20250724_1_L2A | 0.28711 | 0 | 0 | 1 | 0.6975 | -0.2639 | -0.2216 | 74.93 | 4.65 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2025-07-24.png
mantsala_fi | 2025-10-01 | 2025-10-18 | S2B_35VLH_20251018_1_L2A | 1.3424 | 0 | 0 | 1 | 0.6339 | -0.1433 | -0.0813 | 72 | 2.25 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2025-10-18.png
mantsala_fi | 2026-01-01 | 2026-03-24 | S2B_35VMH_20260324_1_L2A | 0.021204 | 0 | 0.0008 | 0.999 | 0.4571 | -0.0144 | 0.0248 | 151.68 | 4.71 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2026-03-24.png
mantsala_fi | 2026-04-01 | 2026-05-30 | S2A_35VMH_20260530_1_L2A | 0.000239 | 0 | 0 | 1 | 0.6127 | -0.1932 | -0.1444 | 114.94 | 5.82 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2026-05-30.png
mantsala_fi | 2026-07-01 | 2026-09-27 | S2A_35VMH_20260927_1_L2A | 0.075872 | 0 | 0 | 1 | 0.6222 | -0.1984 | -0.1268 | 83.97 | 4.29 | /workspace/nebius/capacity/altdata/imagery/mantsala_fi/mantsala_fi_2026-09-27.png
vineland_nj | 2023-01-01 | 2023-01-15 | S2A_18SVJ_20230115_0_L2A | 8.1821 | 0 | 0 | 1 | 0.3611 | 0.0691 | 0.1187 | 135.96 | 8.89 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-01-15.png
vineland_nj | 2023-02-01 | 2023-02-24 | S2A_18SVJ_20230224_0_L2A | 0.47752 | 0 | 0 | 1 | 0.3468 | 0.0502 | 0.104 | 143.42 | 15.33 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-02-24.png
vineland_nj | 2023-03-01 | 2023-03-08 | S2B_18SVJ_20230308_0_L2A | 0.014522 | 0 | 0 | 1 | 0.3411 | 0.0549 | 0.0965 | 152.35 | 45.79 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-03-08.png
vineland_nj | 2023-04-01 | 2023-04-02 | S2A_18SVJ_20230402_0_L2A | 1.6043 | 0.0107 | 0 | 0.989 | 0.3778 | -0.0048 | 0.054 | 130.34 | 9.9 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-04-02.png
vineland_nj | 2023-05-01 | 2023-05-25 | S2A_18SVJ_20230525_0_L2A | 0.74539 | 0.0013 | 0 | 0.999 | 0.5197 | -0.1644 | -0.1031 | 105.94 | 32.24 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-05-25.png
vineland_nj | 2023-06-01 | 2023-06-01 | S2A_18SVJ_20230601_0_L2A | 6.1031 | 0 | 0 | 1 | 0.4086 | -0.1166 | -0.0761 | 114.4 | 24.29 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-06-01.png
vineland_nj | 2023-07-01 | 2023-07-11 | S2A_18SVJ_20230711_0_L2A | 0.028411 | 0 | 0 | 1 | 0.5091 | -0.1146 | -0.0684 | 109.37 | 24.43 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-07-11.png
vineland_nj | 2023-08-01 | 2023-08-20 | S2A_18SVJ_20230820_0_L2A | 7.2374 | 0 | 0 | 1 | 0.5328 | -0.1075 | -0.0666 | 103.62 | 24.6 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-08-20.png
vineland_nj | 2023-09-01 | 2023-09-14 | S2B_18SVJ_20230914_0_L2A | 0.30724 | 0 | 0 | 1 | 0.5409 | -0.1352 | -0.0894 | 88.78 | 14.52 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-09-14.png
vineland_nj | 2023-10-01 | 2023-10-24 | S2B_18SVJ_20231024_0_L2A | 0.012035 | 0 | 0 | 1 | 0.5035 | -0.0924 | -0.0426 | 109.64 | 18.75 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-10-24.png
vineland_nj | 2023-11-01 | 2023-11-16 | S2B_18SVJ_20231116_0_L2A | 0.006573 | 0 | 0 | 1 | 0.4027 | -0.0153 | 0.0456 | 127.5 | 10.8 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-11-16.png
vineland_nj | 2023-12-01 | 2023-12-21 | S2A_18SVJ_20231221_0_L2A | 0.11904 | 0 | 0 | 1 | 0.3478 | 0.0208 | 0.0835 | 136.06 | 17.03 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2023-12-21.png
vineland_nj | 2024-01-01 | 2024-01-05 | S2B_18SVJ_20240105_0_L2A | 2.3543 | 0.0231 | 0 | 0.977 | 0.3639 | 0.0037 | 0.069 | 123.94 | 19.54 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-01-05.png
vineland_nj | 2024-02-01 | 2024-02-04 | S2B_18SVJ_20240204_0_L2A | 0.006772 | 0 | 0 | 1 | 0.3516 | 0.0131 | 0.0852 | 126.16 | 15.55 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-02-04.png
vineland_nj | 2024-03-01 | 2024-03-25 | S2B_18SVJ_20240325_0_L2A | 1.3983 | 0 | 0 | 1 | 0.3705 | -0.027 | 0.0449 | 128.59 | 24.65 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-03-25.png
vineland_nj | 2024-04-01 | 2024-04-29 | S2A_18SVJ_20240429_0_L2A | 9.3315 | 0 | 0 | 1 | 0.4113 | -0.0533 | -0.0012 | 140.81 | 29.94 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-04-29.png
vineland_nj | 2024-05-01 | 2024-05-31 | S2B_18SVJ_20240531_0_L2A | 2.5549 | 0 | 0 | 1 | 0.4986 | -0.1201 | -0.0744 | 116.07 | 42.87 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-05-31.png
vineland_nj | 2024-06-01 | 2024-06-15 | S2A_18SVJ_20240615_0_L2A | 1.1049 | 0.0283 | 0 | 0.972 | 0.4773 | -0.0828 | -0.0398 | 128.98 | 47.54 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-06-15.png
vineland_nj | 2024-07-01 | 2024-07-03 | S2B_18SVJ_20240703_0_L2A | 7.3881 | 0 | 0 | 1 | 0.4768 | -0.0986 | -0.0535 | 122.15 | 41.5 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-07-03.png
vineland_nj | 2024-08-01 | 2024-08-27 | S2A_18SVJ_20240827_0_L2A | 0.29457 | 0 | 0 | 1 | 0.5249 | -0.126 | -0.0764 | 91.83 | 11.63 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-08-27.png
vineland_nj | 2024-09-01 | 2024-09-08 | S2B_18SVJ_20240908_0_L2A | 0.099465 | 0 | 0 | 1 | 0.5569 | -0.1537 | -0.1048 | 82.99 | 20.33 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-09-08.png
vineland_nj | 2024-10-01 | 2024-10-11 | S2B_18SVJ_20241011_0_L2A | 0.00279 | 0 | 0 | 1 | 0.5017 | -0.0825 | -0.0307 | 93.6 | 13.18 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-10-11.png
vineland_nj | 2024-11-01 | 2024-11-12 | S2A_18SVJ_20241112_0_L2A | 1.02 | 0 | 0 | 1 | 0.383 | 0.027 | 0.0893 | 116.28 | 10.14 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-11-12.png
vineland_nj | 2024-12-01 | 2024-12-30 | S2B_18SVJ_20241230_0_L2A | 0.029987 | 0 | 0 | 1 | 0.3432 | 0.0074 | 0.0769 | 114.93 | 7.21 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2024-12-30.png
vineland_nj | 2025-01-01 | 2025-01-29 | S2B_18SVJ_20250129_0_L2A | 11.7384 | 0 | 0.008 | 0.992 | 0.2988 | 0.0343 | 0.0954 | 141.53 | 9.2 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-01-29.png
vineland_nj | 2025-02-01 | 2025-02-10 | S2C_18SVJ_20250210_0_L2A | 7.0517 | 0.0293 | 0 | 0.971 | 16.1595 | 0.1423 | 4.9871 | 83.12 | 2.27 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-02-10.png
vineland_nj | 2025-03-01 | 2025-03-25 | S2C_18SVJ_20250325_0_L2A | 0.10522 | 0 | 0 | 1 | 0.3184 | 0.0417 | 0.1022 | 146.88 | 13.59 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-03-25.png
vineland_nj | 2025-04-01 | 2025-04-01 | S2C_18SVJ_20250401_0_L2A | 1.9384 | 0.0156 | 0 | 0.984 | 0.3349 | 0.0118 | 0.067 | 129.35 | 9.7 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-04-01.png
vineland_nj | 2025-05-01 | 2025-05-19 | S2B_18SVJ_20250519_0_L2A | 4.3095 | 0 | 0 | 1 | 0.4976 | -0.12 | -0.073 | 113.94 | 38.39 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-05-19.png
vineland_nj | 2025-06-01 | 2025-06-03 | S2C_18SVJ_20250603_0_L2A | 0.018351 | 0 | 0 | 1 | 0.5377 | -0.1349 | -0.0868 | 105.47 | 37.86 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-06-03.png
vineland_nj | 2025-07-01 | 2025-07-25 | S2B_18SVJ_20250725_0_L2A | 0.060144 | 0 | 0 | 1 | 0.4969 | -0.0761 | -0.0497 | 115.61 | 27.9 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-07-25.png
vineland_nj | 2025-08-01 | 2025-08-22 | S2C_18SVJ_20250822_0_L2A | 0.005478 | 0 | 0 | 1 | 0.5532 | -0.133 | -0.0881 | 105.64 | 19.22 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-08-22.png
vineland_nj | 2025-09-01 | 2025-09-23 | S2B_18SVJ_20250923_1_L2A | 0.007456 | 0 | 0 | 1 | 0.5076 | -0.0767 | -0.0458 | 111.75 | 18.86 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-09-23.png
vineland_nj | 2025-10-01 | 2025-10-16 | S2B_18SVJ_20251016_0_L2A | 0.008115 | 0 | 0 | 1 | 0.5352 | -0.1276 | -0.0702 | 93.46 | 13 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-10-16.png
vineland_nj | 2025-11-01 | 2025-11-29 | S2A_18SVJ_20251129_0_L2A | 0.1898 | 0 | 0 | 1 | 0.3766 | 0.0252 | 0.0794 | 127.14 | 19.4 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-11-29.png
vineland_nj | 2025-12-01 | 2025-12-22 | S2B_18SVJ_20251222_0_L2A | 0.038289 | 0.0001 | 0 | 1 | 0.348 | 0.0168 | 0.0648 | 125 | 18.99 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2025-12-22.png
vineland_nj | 2026-01-01 | 2026-01-04 | S2B_18SVJ_20260104_0_L2A | 7.0092 | 0 | 0 | 1 | 0.3276 | 0.0212 | 0.072 | 143.38 | 23.49 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2026-01-04.png
vineland_nj | 2026-03-01 | 2026-03-09 | S2A_18SVJ_20260309_0_L2A | 0.010135 | 0 | 0 | 1 | 0.2971 | 0.083 | 0.13 | 159.79 | 13.57 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2026-03-09.png
vineland_nj | 2026-04-01 | 2026-04-06 | S2C_18SVJ_20260406_1_L2A | 1.2993 | 0.0067 | 0 | 0.993 | 0.3811 | -0.0228 | 0.0346 | 124.02 | 19.72 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2026-04-06.png
vineland_nj | 2026-05-01 | 2026-05-04 | S2B_18SVJ_20260504_0_L2A | 0.010806 | 0 | 0 | 1 | 0.4581 | -0.104 | -0.0492 | 123.49 | 32.84 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2026-05-04.png
vineland_nj | 2026-06-01 | 2026-06-03 | S2B_18SVJ_20260603_0_L2A | 0.73318 | 0 | 0 | 1 | 0.4991 | -0.1208 | -0.0775 | 127 | 40.76 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2026-06-03.png
vineland_nj | 2026-07-01 | 2026-07-20 | S2B_18SVJ_20260720_0_L2A | 0.23316 | 0 | 0 | 1 | 0.5256 | -0.1288 | -0.0892 | 110.5 | 44.01 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2026-07-20.png
vineland_nj | 2026-08-01 | 2026-08-24 | S2C_18SVJ_20260824_0_L2A | 0.10307 | 0 | 0 | 1 | 0.5395 | -0.153 | -0.1046 | 91.72 | 26.69 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2026-08-24.png
vineland_nj | 2026-09-01 | 2026-09-08 | S2B_18SVJ_20260908_1_L2A | 8.6924 | 0 | 0 | 1 | 0.5498 | -0.1589 | -0.1146 | 94.4 | 28.19 | /workspace/nebius/capacity/altdata/imagery/vineland_nj/vineland_nj_2026-09-08.png

## Thermal
site | date | id | campus_C | background_C | anomaly_C
vineland_nj | 2023-02-13 | LC09_L2SP_014033_20230213_02_T1 | 11.94 | 12.69 | -0.75
vineland_nj | 2023-03-09 | LC08_L2SP_014033_20230309_02_T1 | 14.17 | 14.92 | -0.75
vineland_nj | 2023-04-02 | LC09_L2SP_014033_20230402_02_T1 | 16.14 | 17.34 | -1.19
vineland_nj | 2023-04-10 | LC08_L2SP_014033_20230410_02_T1 | 23.36 | 23.68 | -0.32
vineland_nj | 2023-04-18 | LC09_L2SP_014033_20230418_02_T1 | 26.13 | 26.35 | -0.22
vineland_nj | 2023-07-23 | LC09_L2SP_014033_20230723_02_T1 | 39.66 | 38.31 | 1.35
vineland_nj | 2023-09-01 | LC08_L2SP_014033_20230901_02_T1 | 29.99 | 29.14 | 0.85
vineland_nj | 2023-10-03 | LC08_L2SP_014033_20231003_02_T1 | 28.26 | 27.68 | 0.58
vineland_nj | 2023-10-11 | LC09_L2SP_014033_20231011_02_T1 | 25.4 | 24.72 | 0.68
vineland_nj | 2023-10-19 | LC08_L2SP_014033_20231019_02_T1 | 20.64 | 20.86 | -0.22
vineland_nj | 2023-10-27 | LC09_L2SP_014033_20231027_02_T1 | 26.75 | 26.5 | 0.25
vineland_nj | 2024-02-08 | LC08_L2SP_014033_20240208_02_T1 | 11.09 | 11.61 | -0.51
vineland_nj | 2024-03-03 | LC09_L2SP_014033_20240303_02_T1 | 18.67 | 19.48 | -0.81
vineland_nj | 2024-03-11 | LC08_L2SP_014033_20240311_02_T1 | 10.88 | 12.32 | -1.43
vineland_nj | 2024-04-28 | LC08_L2SP_014033_20240428_02_T1 | 31.09 | 30.74 | 0.36
vineland_nj | 2024-05-22 | LC09_L2SP_014033_20240522_02_T1 | 36.11 | 35.47 | 0.64
vineland_nj | 2024-06-15 | LC08_L2SP_014033_20240615_02_T1 | 37.95 | 37.03 | 0.93
vineland_nj | 2024-08-10 | LC09_L2SP_014033_20240810_02_T1 | 34.41 | 34.61 | -0.19
vineland_nj | 2024-09-03 | LC08_L2SP_014033_20240903_02_T1 | 30.17 | 29.08 | 1.1
vineland_nj | 2024-09-11 | LC09_L2SP_014033_20240911_02_T1 | 34.45 | 32.99 | 1.46
vineland_nj | 2024-10-13 | LC09_L2SP_014033_20241013_02_T1 | 28.88 | 28.29 | 0.59
vineland_nj | 2024-10-21 | LC08_L2SP_014033_20241021_02_T1 | 27.47 | 26.94 | 0.53
vineland_nj | 2024-11-06 | LC08_L2SP_014033_20241106_02_T1 | 26.12 | 25.82 | 0.3
vineland_nj | 2024-11-30 | LC09_L2SP_014033_20241130_02_T1 | 4.36 | 4.68 | -0.32
vineland_nj | 2024-12-16 | LC09_L2SP_014033_20241216_02_T2 | 6.33 | 5.73 | 0.6
vineland_nj | 2025-01-09 | LC08_L2SP_014033_20250109_02_T1 | -4.8 | -4.55 | -0.25
vineland_nj | 2025-02-26 | LC08_L2SP_014033_20250226_02_T1 | 17.27 | 17.89 | -0.62
vineland_nj | 2025-05-17 | LC08_L2SP_014033_20250517_02_T1 | 31.25 | 32.15 | -0.9
vineland_nj | 2025-06-02 | LC08_L2SP_014033_20250602_02_T1 | 29.39 | 28.77 | 0.62
vineland_nj | 2025-06-26 | LC09_L2SP_014033_20250626_02_T1 | 45.31 | 43.14 | 2.17
vineland_nj | 2025-07-04 | LC08_L2SP_014033_20250704_02_T1 | 36.25 | 34.76 | 1.48
vineland_nj | 2025-09-22 | LC08_L2SP_014033_20250922_02_T1 | 29.93 | 28.4 | 1.54
vineland_nj | 2025-10-16 | LC09_L2SP_014033_20251016_02_T1 | 18.01 | 17.96 | 0.05
vineland_nj | 2025-10-24 | LC08_L2SP_014033_20251024_02_T1 | 19.21 | 18.59 | 0.62
vineland_nj | 2025-11-01 | LC09_L2SP_014033_20251101_02_T1 | 17.07 | 17.8 | -0.73
vineland_nj | 2025-12-03 | LC09_L2SP_014033_20251203_02_T1 | 6.3 | 6.46 | -0.16
vineland_nj | 2026-02-13 | LC08_L2SP_014033_20260213_02_T1 | 0.62 | 0.98 | -0.36
vineland_nj | 2026-03-09 | LC09_L2SP_014033_20260309_02_T1 | 22.42 | 24.66 | -2.24
vineland_nj | 2026-03-17 | LC08_L2SP_014033_20260317_02_T1 | 9.82 | 10.76 | -0.93
vineland_nj | 2026-04-10 | LC09_L2SP_014033_20260410_02_T1 | 25.28 | 25.66 | -0.38
vineland_nj | 2026-05-04 | LC08_L2SP_014033_20260504_02_T1 | 29.96 | 29.53 | 0.42
vineland_nj | 2026-05-12 | LC09_L2SP_014033_20260512_02_T1 | 28.38 | 27.03 | 1.36
vineland_nj | 2026-05-20 | LC08_L2SP_014033_20260520_02_T1 | 45.68 | 43.55 | 2.12
vineland_nj | 2026-05-28 | LC09_L2SP_014033_20260528_02_T1 | 31.92 | 31.78 | 0.14
vineland_nj | 2026-06-13 | LC09_L2SP_014033_20260613_02_T1 | 41.45 | 39.28 | 2.17
vineland_nj | 2026-07-15 | LC09_L2SP_014033_20260715_02_T1 | 40.98 | 39.43 | 1.55
vineland_nj | 2026-07-23 | LC08_L2SP_014033_20260723_02_T1 | 34.48 | 32.49 | 1.99
vineland_nj | 2026-08-08 | LC08_L2SP_014033_20260808_02_T1 | 38.54 | 35.88 | 2.66
vineland_nj | 2026-08-24 | LC08_L2SP_014033_20260824_02_T1 | 33.48 | 32.24 | 1.24

## Sites_AOI
site | lat | lon | half_m | cadence | coordinate basis
vineland_nj | 39.4282 | -75.0184 | 1200 | M | Nominatim: 3963 S Lincoln Ave, Vineland NJ (Block 7503 Lot 35.01, PILOT ordinance)
mantsala_fi | 60.6289 | 25.262 | 1500 | Q | Nominatim: Moreenikatu 6, Mantsala (Nebius DC Oy registered visiting address); AOI also covers Kapuli area ~1 km
kansascity_mo | 39.094 | -94.5794 | 400 | Q | Nominatim: 1601 McGee St (Patmos / former KC Star press)
birmingham_al | 33.4291 | -86.8851 | 800 | Q | Nominatim: 201 Milan Pkwy, Birmingham AL
independence_mo | 39.103 | -94.308 | 1600 | Q | visually located: active earthworks NE of Little Blue Pkwy / MO-78 interchange in S2 chips (Oct 2026); Nebius/City FAQ location description
butler_pa | 40.735 | -76.3 | 2500 | Q | approx: Highridge Park Rd (OSM 40.7346,-76.3022) / Gordon Mountain Rd (OSM 40.7409,-76.3251) near I-81; wide AOI
bethune_fr | 50.5397 | 2.659 | 900 | Q | Nominatim/OSM: Bridgestone plant, Bethune
keflavik_is | 63.9716 | -22.5734 | 1000 | Q | Nominatim: Asbru campus (Verne); approx
lappeenranta_fi | 61.06 | 28.19 | 2000 | Q | approx: site_list city-level (Pajarila)
longcross_uk | 51.3806 | -0.5946 | 600 | Q | Nominatim/OSM: Ark Longcross Park