## Sites
# | Site | City/Region | Country | Lat | Lon | Coord basis | Type | Partner/Landlord | Announced MW – initial phase | Announced MW – full build-out | IT vs gross | Timeline (announced; revisions) | GPU generation(s) | Anchor customer | Status (as of Oct 4 2026) | Sources (date)
1 | Mäntsälä DC #1 | Mäntsälä, Uusimaa | Finland | 60.633 | 25.317 | approx, town-level | Owned greenfield (self-built) | — (Nebius-owned) | 25 MW pre-expansion (DCD, Nov-2024) | 75 MW after tripling (Nebius PR Oct 8 2024) | not disclosed | Expansion announced Oct 8 2024; target 'end-2025 or early 2026' (Q3'24 PR); Q1'25 call: phase 1 late Q3'25, phase 2 ~YE25; Mar 31 2026 PR: expansion to 75 MW 'completed earlier this year' | H100 (installed), H200 (from Nov 2024), GB300 NVL72 ('Europe's first operational', Mar 2026); docs eu-north1: H100/H200/L40S | not disclosed | Operational, 75 MW built | https://nebius.com/newsroom/nebius-to-triple-capacity-at-finland-data-center-to-75-mw (2024-10-08); https://nebius.com/newsroom/nebius-group-n-v-announces-third-quarter-2024-financial-results (2024-11); https://www.datacenterdynamics.com/en/news/nebius-to-deploy-5mw-nvidia-h200-cluster-at-patmos-data-center-in-kansas-city-missouri/ (2024-11-19); https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf (2026-03-31); https://docs.nebius.com/overview/regions (accessed 2026-10-04)
2 | Mäntsälä DC #2 | Mäntsälä, Uusimaa | Finland | 60.633 | 25.317 | approx, town-level | Owned (implied: Nebius 'building a second data center'; not explicitly labelled) | Caverion (EUR15M 70 MW substation contractor) | not disclosed | up to 70 MW | not disclosed | Announced Aug 13 2026 (LinkedIn, with Q2'26 results; Q2 letter: 'additional sites in … Finland'); capacity 'from 2027'; substation completion autumn 2027. Finland total 455 MW across 3 sites | not disclosed | not disclosed | Planned / pre-construction | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/ (2026-08-13); https://www.assemblincaverion.com/news-and-media/news/2026/caverion-finland-strengthens-its-position-in-the-data-centre-market-and-will-deliver-a-eur-15-million-substation-for-ai-cloud-company-nebius/ (2026); https://assets.nebius.com/assets/4462517b-ce83-41f2-96ed-f2ac1bc06a05/SHLQ226%20%281%29.pdf (2026-08-12)
3 | Lappeenranta AI factory (Pajarila) | Lappeenranta, South Karelia | Finland | 61.06 | 28.19 | approx, city-level | Owned per Nebius ('new owned location', Q1'26 letter) — but developer Polarnode describes Nebius as 'operating Polarnode's campus' (see conflicts) | Polarnode (developer/builder); Caverion (substation) | Substation phase 1: 70 MW (Caverion) | up to 310 MW | not disclosed | Announced Mar 31 2026 (Nebius PR; Reuters: '10th site', >$10B value); first capacity to customers in 2027; substation construction from Jul 2026, completion spring 2027 (Caverion) | 'latest Blackwell and Rubin generations' (company-level statement in PR; site-specific not disclosed) | not disclosed | Under construction (pre-construction by Polarnode) | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf (2026-03-31); https://www.reuters.com/technology/nebius-furthers-european-expansion-with-10-billion-ai-data-centre-finland-2026-03-31/ (2026-03-31); https://www.polarnode.fi/historic-investment-in-lappeenranta-finland-nebius-to-operate-polarnodes-310-mw-data-center-campus/ (2026-03); https://www.caverion.com/newsroom/releases/2026/caverion-to-deliver-eur-15-million-substation-for-nebius-data-center-in-finland-creating-jobs-for-more-than-80-professionals/ (2026); https://assets.nebius.com/assets/aa1bc2e6-df83-40cd-a6a2-95e7cda3d16c/Nebius%20SHL_Q1%202026.pdf (2026-05-13)
4 | Paris – Equinix PA10 | Saint-Denis, Île-de-France | France | 48.92 | 2.36 | approx, Saint-Denis district | Colocation | Equinix (PA10) | not disclosed (third-party DC Atlas: ~5 MW — unverified) | not disclosed | not disclosed | Agreement Jul 2024 (20-F); announced Sep 25 2024; first client workloads Nov 2024; in operation Nov 2024 (Q4'24 PR) | H200 (docs eu-west1: H200) | not disclosed | Operational | https://nebius.com/blog/posts/nebius-launches-gpu-cluster-in-paris-france (2024-09-25); https://www.sec.gov/Archives/edgar/data/1513845/000110465925015480/tm257185d1_ex99-1.htm (2025-02-20); https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm (2026-04-30); https://docs.nebius.com/overview/regions
5 | Béthune AI factory (ex-Bridgestone plant) | Béthune, Pas-de-Calais (near Lille) | France | 50.53 | 2.64 | approx, town-level | Colocation per 20-F ('two new co-location sites in France', Feb-2026); Nebius PR says 'building an AI factory' | Azur Datacenter (finances/builds shell; Nebius IT) per DCmag/Reuters | First capacity 'late summer 2026'; ~120 MW (half) by YE2026 | 240 MW | not disclosed | Announced Feb 12 2026 (with Q4'25 results; Reuters/Les Echos); first capacity late summer 2026; ~half (120 MW) by end-2026; full 240 MW in 2027 (DCmag/GNT: end-2027) | not disclosed | not disclosed | Under construction / phase 1 possibly live (unconfirmed) | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/ (2026-02-12); https://dcmag.fr/nebius-annonce-un-mega-datacenter-de-240-mw-a-bethune-pas-de-calais-chez-azur-datacenter/ (2026-02-13); https://www.generation-nt.com/actualites/nebius-datacenter-bethune-ia-france-bridgestone-2070889 (2026-02-17); https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm (2026-04-30); https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf (2026-03-31)
6 | France – 2nd new colocation site (unnamed) | not disclosed | France |  |  | not disclosed | Colocation (20-F) | not disclosed | not disclosed | not disclosed | not disclosed | Secured Feb 2026 (20-F). Possibly the private region eu-west2 (docs: France, B300) — INFERENCE | eu-west2 lists B300 (if this is the site — inference) | not disclosed | not disclosed | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm (2026-04-30); https://docs.nebius.com/overview/regions
7 | Keflavik – Verne | Keflavik (Ásbrú campus), Reykjanes | Iceland | 63.97 | -22.58 | approx, Verne campus area | Colocation | Verne | 10 MW cluster | 10 MW (no expansion disclosed) | not disclosed | Agreement Dec 2024 (20-F); announced Mar 5 2025; live Mar 2025 (Q1'25 letter) | H200 (Q4'24 call; docs eu-north2 private region: H200) | not disclosed | Operational (private region) | https://nebius.com/blog/posts/300-mw-new-jersey-and-iceland-regions (2025-03-05); https://www.sec.gov/Archives/edgar/data/1513845/000110465925050975/tm2515580d1_ex99-2.htm (2025-05-20); https://equibles.com/stocks/nbis/calls/2024-q4 (2025-02-20); https://docs.nebius.com/overview/regions
8 | London – Ark Longcross Park (LP01; LP02 planned) | Chertsey, Surrey | UK | 51.38 | -0.59 | approx, Longcross Park | Colocation | Ark Data Centres | 16 MW; phase 1 4,000 HGX B300 (Nov 2025) | Phase 2 +3,000 B300 (7,000 total). Jun 2026: Nebius leases entire existing facility; Ark building new 36 MW LP02 (Nebius share not disclosed) | not disclosed | Announced Jun 2025 (Ark named host Jun 25 2025); target Q4'25; launched Nov 6 2025. Jun 2026: Nebius fills LP01 (16 MW live + 3 MW in delivery); Ark £807M expansion | B300 / Blackwell Ultra (docs uk-south1: B300) | not disclosed | Operational + expanding | https://www.datacenterdynamics.com/en/news/nebius-to-host-uk-nvidia-blackwell-ultra-gpu-cluster-in-ark-data-centres-facility-in-surrey/ (2025-06-25); https://www.datacenterdynamics.com/en/news/nebius-launches-nvidia-gpu-cluster-in-london-uk/ (2025-11-06); https://www.datacenterdynamics.com/en/news/ark-dc-to-add-new-building-to-longcross-data-center-campus-outside-london-uk/ (2026-06-09); https://datacentrenews.uk/story/nebius-fills-ark-s-longcross-data-centre-to-capacity (2026-06); https://docs.nebius.com/overview/regions
9 | Harlow – Kao Data (KLON-02/03) | Harlow, Essex | UK | 51.77 | 0.1 | approx, Kao Harlow campus | Colocation (10-year) | Kao Data | not disclosed | 22 MW | not disclosed | Announced Jun 8 2026 as part of £1.7bn UK plan; three new UK deployments total 65 MW fully ramped in 2027 | 'latest generations' of NVIDIA (not specified); docs uk-south2: RTX PRO 6000 (site mapping is inference) | not disclosed | Hardware install underway (third-party); capacity ramp to 2027 | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/ (2026-06-08); https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai (2026-06-08)
10 | UK – third new deployment (unnamed) | not disclosed | UK |  |  | not disclosed | not disclosed (likely colocation — inference) | not disclosed | not disclosed | Residual of 65 MW UK total (65 − 22 Harlow − Longcross expansion share) — not disclosed | not disclosed | Jun 8 2026 PR: 3 new deployments (4 sites incl. existing) at ~£1.7bn; Q2'26 letter: 'additional sites in the UK' | not disclosed | not disclosed | not disclosed | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai (2026-06-08); https://assets.nebius.com/assets/4462517b-ce83-41f2-96ed-f2ac1bc06a05/SHLQ226%20%281%29.pdf (2026-08-12)
11 | Modi'in – Mega Or | Modi'in | Israel | 31.9 | 35.01 | approx, city-level | Colocation | Mega Or / Mega DC | 8 MW; 4,000 HGX B200 | Mega Or said Nebius may double to 8,000 GPUs subject to demand (not Nebius-confirmed) | not disclosed | Lease signed May 2025 (Mega Or); launched Oct 20 2025 | B200 (docs me-west1: B200) | 25% of GPUs offered to Israel Innovation Authority (national supercomputer) | Operational | https://nebius.com/newsroom/nebius-brings-nvidia-blackwell-to-israel-with-one-of-the-country-s-first-ai-infrastructure-deployments (2025-10-20); https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/ (2026-01); https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
12 | Masmiyya – Mega DC | Masmiyya junction area | Israel | 31.74 | 34.78 | approx | Colocation (5-yr + extension option) | Mega Or / Mega DC | 22 MW | 22 MW (site could reach 64 MW; Nebius share n/d) | not disclosed | Signed ~Jan 2026 (Mega Or TASE disclosure); delivery Q3 2026 | not disclosed | not disclosed | Delivery scheduled Q3 2026 | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/ (2026-01); https://www.calcalistech.com/ctechnews/article/p4ds17rzm (2026-01); https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
13 | Beit Shemesh – Mega DC | Beit Shemesh | Israel | 31.75 | 34.99 | approx, city-level | Colocation (5-yr + extension option) | Mega Or / Mega DC | Staged from Q3 2026 | 58 MW (site could reach ~222 MW; Nebius share n/d) | not disclosed | Signed ~Jan 2026; staged delivery Q3 2026 – Q1 2027 | not disclosed | not disclosed | Under construction | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/ (2026-01); https://www.calcalistech.com/ctechnews/article/p4ds17rzm (2026-01)
14 | Madrid-Getafe – Merlin Edged | Getafe, Madrid | Spain | 40.3 | -3.73 | approx, city-level | Colocation | Merlin Properties / Edged | Phase 1 live Sep 2026 (MW n/d); phases 2-3 'coming weeks' | 18 MW | not disclosed | Q1'26 letter (May 13 2026): 'new colocation site in Spain'; 18 MW reported Jul 3 2026 (El Mundo/DCD; Merlin confirmed); live mid-Sep 2026 (employee LinkedIn post) | RTX PRO 6000 (phase 1) and B300 planned (LinkedIn); docs eu-south1: RTX PRO 6000 | not disclosed | Operational (phase 1) | https://assets.nebius.com/assets/aa1bc2e6-df83-40cd-a6a2-95e7cda3d16c/Nebius%20SHL_Q1%202026.pdf (2026-05-13); https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/ (2026-07-03); https://www.merlinproperties.com/dia-a-dia/firmamos-un-contrato-de-18-mw-con-nebius-para-nuestro-date-center-madrid-getafe/ (2026); https://www.linkedin.com/feed/update/urn:li:activity:7505906816590073857 (2026-09-16); https://docs.nebius.com/overview/regions
15 | Tallinn – Greenergy Hüüru | Hüüru, Saue Parish (W of Tallinn) | Estonia | 59.37 | 24.58 | approx | Colocation | Greenergy Data Centers (MCF Group) | 22 MW first phase later in 2026 | 22 MW (facility total 31.5 MW) | not disclosed | Signed Q2 2026; announced Aug 12-13 2026 with Q2 results; first phase operational later in 2026 | not disclosed | not disclosed | Under construction | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/ (2026-08-13); https://news.err.ee/1610109073/baltics-first-ai-factory-to-open-in-estonia (2026-08); https://assets.nebius.com/assets/4462517b-ce83-41f2-96ed-f2ac1bc06a05/SHLQ226%20%281%29.pdf (2026-08-12)
16 | Kansas City – Patmos | Kansas City, Missouri (downtown, former KC Star press building) | USA | 39.093 | -94.58 | approx, downtown KC | Colocation (20-F); Nov-24 PR called it 'first U.S. cluster' | Patmos | 5 MW initial phase (thousands of Hopper GPUs) | Expandable to 40 MW (~35,000 GPUs) | not disclosed | Announced Nov 2024; go-live target end-Q1 2025 → launched Apr 2025; phase 2 agreed Mar 2025 (target end-Q2'25) → added early Jul 2025; first B200 cluster launched Q3'25 | H200 (phase 1), B200 (phase 2); docs us-central1: B200/H200/RTX PRO 6000 | not disclosed | Operational | https://www.datacenterdynamics.com/en/news/nebius-to-deploy-5mw-nvidia-h200-cluster-at-patmos-data-center-in-kansas-city-missouri/ (2024-11-19); https://www.sec.gov/Archives/edgar/data/1513845/000110465925015480/tm257185d1_ex99-1.htm (2025-02-20); https://nebius.com/blog/posts/300-mw-new-jersey-and-iceland-regions (2025-03-05); https://www.sec.gov/Archives/edgar/data/1513845/000110465925050975/tm2515580d1_ex99-2.htm (2025-05-20); https://www.sec.gov/Archives/edgar/data/1513845/000110465925075028/tm2522866d1_ex99-2.htm (2025-08-07); https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm (2025-11-11)
17 | Vineland – DataOne | Vineland, New Jersey | USA | 39.49 | -75.03 | approx, city-level | Build-to-suit (DataOne owns/operates shell; Nebius tenant) | DataOne; Northeast Precast (builder); Bloom Energy (on-site fuel cells) | Phase 1 'summer 2025'; 100 MW available in 2025 + 100 MW in 2026 (200 MW contracted, Q2'25) | up to 300 MW (Mar 2025); option for 'hundreds of MW' more (Q3'25) | not disclosed | Announced Mar 5 2025 (agreement Feb 2025 per 20-F); first phase target summer 2025 → 'end of summer', instances fall 2025; MSFT tranche 1 Nov 2025, tranche 2 Feb 2026; Q1'26: majority of remaining capacity 2H26; Q2'26: building finished summer 2026, power switched to Bloom, site-plan amendment hearing adjourned; still in 2026 connected power | not disclosed by Nebius for site | Microsoft – $17.4B (up to $19.4B) 5-yr, served exclusively from NJ; 9 tranches 2025-26 (+2 via Jan-2026 addendum) | Partially operational, ramping | https://nebius.com/blog/posts/300-mw-new-jersey-and-iceland-regions (2025-03-05); https://www.sec.gov/Archives/edgar/data/1513845/000110465925075028/tm2522866d1_ex99-2.htm (2025-08-07); https://www.sec.gov/Archives/edgar/data/1513845/000110465925088312/tm2525580d1_6k.htm (2025-09-08); https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm (2025-11-11); https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm (2026-04-30); https://assets.nebius.com/assets/aa1bc2e6-df83-40cd-a6a2-95e7cda3d16c/Nebius%20SHL_Q1%202026.pdf (2026-05-13); https://stockanalysis.com/stocks/nbis/transcripts/655490-q2-2026/ (2026-08-12); https://nebius.com/vinelandnj
18 | Independence AI factory (Eastgate Commerce Center) | Independence, Missouri (Rte 78 & Little Blue Pkwy) | USA | 39.04 | -94.33 | approx, from stated intersection | Owned greenfield | — (land from NorthPoint; power from Independence Power & Light / new Blue Valley plant by IPP) | IPL initial power 2H 2026 (MW n/d); first buildings operational 2027 | up to 1.2 GW (originally reported 800 MW) | not disclosed | Land Dec 2025; announced as owned site Feb 12 2026; Ch.100 approval Mar 2026; groundbreaking May 12 2026; operational 2027 (Q1'26 letter); additional power study for early 2029; build-out over 5-7 yrs | Vera Rubin planned in US (company-level); site-specific n/d | not disclosed (Meta #2 'multiple locations' — not site-attributed) | Under construction | https://nebius.com/independencemo (accessed 2026-10-04); https://www.datacenterdynamics.com/en/news/nebius-breaks-ground-on-400-acre-data-center-campus-in-independence-missouri/ (2026-05-13); https://www.datacenterdynamics.com/en/news/nebius-plans-800mw-data-center-campus-in-kansas-city-missouri/; https://www.sec.gov/Archives/edgar/data/1513845/000110465926013946/tm266173d1_ex99-2.htm (2026-02-12); https://assets.nebius.com/assets/aa1bc2e6-df83-40cd-a6a2-95e7cda3d16c/Nebius%20SHL_Q1%202026.pdf (2026-05-13)
19 | Birmingham BHM01 (Oxmoor; former Regions Lakeshore ops center) | Birmingham, Alabama (201 Milan Pkwy) | USA | 33.43 | -86.86 | approx, from street address | Owned brownfield (via Alabama ADC Holdings LLC) | — (Alabama Power supplies; Hoar Construction GC; Raeden affiliate involved in 201 Milan transaction) | Phase 1 ~100 MW (press-reported) | ~300 MW (press-reported; not in Nebius filings) | 'electrical capacity' per press | Land Sep 2025; announced Feb 12 2026; Nebius page: construction Q2 2026, initial phase commissioning/energization Q4 2026, full build-out through 2028; Q1'26 letter: operational in 2027 | not disclosed | not disclosed | Under construction | https://nebius.com/birminghamal (accessed 2026-10-04); https://www.datacenterdynamics.com/en/news/nebius-targets-data-center-development-in-birmingham-alabama/ (2026-02-10); https://www.al.com/news/2026/02/multibillion-dollar-birmingham-ai-factory-taking-shape-not-coming-to-town-to-build-a-big-grey-box.html (2026-02); https://assets.nebius.com/assets/aa1bc2e6-df83-40cd-a6a2-95e7cda3d16c/Nebius%20SHL_Q1%202026.pdf (2026-05-13)
20 | Pennsylvania AI factory (Highridge Business Park) | Butler Twp, Schuylkill County, Pennsylvania (I-81 & Gordon Mountain Rd) | USA | 40.78 | -76.25 | approx, from stated intersection | Owned greenfield | — (PPL 1.2 GW power agreement; land from SEDCO) | ~250-300 MW by end-2027 (Q1'26 call); 260 MW by Oct 2027 (DCD/site plans) | up to 1.2 GW; ~660 MW by 2029 (DCD); +~300 MW/yr to 1.2 GW by ~2030 (call) | not disclosed | Announced May 13 2026; land closed May 1 2026 ($187.5M, local press); expansion overlay approved Sep 1 2026; first two buildings construction late 2026 (~3 yrs) | not disclosed | not disclosed | Site prep | https://assets.nebius.com/assets/6fc0ea6c-0884-4a1f-bed8-1f797eb9628f/Financial%20results_Q1%202026.pdf (2026-05-13); https://assets.nebius.com/assets/aa1bc2e6-df83-40cd-a6a2-95e7cda3d16c/Nebius%20SHL_Q1%202026.pdf (2026-05-13); https://www.fool.com/earnings/call-transcripts/2026/05/13/nebius-nbis-q1-2026-earnings-transcript/ (2026-05-13); https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/ (2026-07-27); https://www.republicanherald.com/2026/09/01/nebius-gets-green-light-to-expand-its-data-center-plan-in-butler-twp/ (2026-09-01)
21 | Oklahoma colocation (unnamed) | Oklahoma City (third-party only) | USA | 35.47 | -97.52 | approx, city-level (location unverified) | Colocation (20-F) | not disclosed | not disclosed | not disclosed | not disclosed | Secured Feb 2026 (20-F / Q4'25 letter map) | not disclosed | not disclosed | not disclosed | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm (2026-04-30); https://www.sec.gov/Archives/edgar/data/1513845/000110465926013946/tm266173d1_ex99-2.htm (2026-02-12)
22 | Minnesota colocation (us-north1) | Woodbury, Minnesota (per Nebius docs) | USA | 44.92 | -92.96 | approx, city-level | Colocation (20-F) | not disclosed | not disclosed | not disclosed | not disclosed | Secured Feb 2026 (20-F); region us-north1 live (docs) | B300 (docs us-north1) | not disclosed | Operational (region listed) | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm (2026-04-30); https://docs.nebius.com/overview/regions
23 | AIB Data Centers – southeastern US (unnamed) | not disclosed (southeastern US) | USA |  |  | not disclosed | Colocation / leased (12-yr initial term) | AIB Data Centers Inc. (NYSE American: AIB) | not disclosed | 50 MW critical IT (65 MW utility ESA) | IT MW stated (50 MW critical IT); 65 MW utility load | Announced by AIB Sep 30 2026 (not yet in Nebius release); two data halls; dates n/d | not disclosed | not disclosed | Contracted | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html (2026-09-30)

## Site x Quarter KPIs
Entity | Quarter | Metric | Value | Tag | Method / note | Source
Company | Q1'24 | Active MW | not disclosed | Reported (none) | Pre-relisting (Nasdaq trading resumed Oct 2024); no capacity KPI published | —
Company | Q1'24 | GPUs deployed | not disclosed | Reported (none) | Third-party aggregator claims (~10k GPUs mid-2024) are not company disclosures — excluded | —
Company | Q2'24 | Active MW | not disclosed | Reported (none) | Pre-relisting (Nasdaq trading resumed Oct 2024); no capacity KPI published | —
Company | Q2'24 | GPUs deployed | not disclosed | Reported (none) | Third-party aggregator claims (~10k GPUs mid-2024) are not company disclosures — excluded | —
Company | Q3'24 | GPUs deployed | ~10,000 (est.) | Estimated | Q4'24 PR: Hopper base 'nearly doubled QoQ' in Q4; Q3'24 call guided '>20,000 GPUs deployed by YE24' → Q3'24 ≈ 20,000/2 ≈ 10,000 | https://exa.ai/library/markets/stocks/NBIS/earnings/FY2024/Q3/transcript; https://www.sec.gov/Archives/edgar/data/1513845/000110465925015480/tm257185d1_ex99-1.htm
Company | Q3'24 | Active MW | not disclosed | — | Only Mäntsälä (25 MW site capacity) + Paris (live Nov) existed | —
Company | Q4'24 | GPUs deployed | >20,000 (est.) | Estimated | Q3'24 call target >20,000 by YE24; Q4'24 PR: base nearly doubled QoQ (actual count not given) | https://exa.ai/library/markets/stocks/NBIS/earnings/FY2024/Q3/transcript; https://www.sec.gov/Archives/edgar/data/1513845/000110465925015480/tm257185d1_ex99-1.htm
Company | Q4'24 | Connected MW | 25 MW | Reported | Q3'25 letter chart 'Connected power CYE 2024: 25 MW' | https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm
Company | Q1'25 | GPUs deployed | ~38,000 (mostly H200, remainder H100) | Reported | Feb 20 2025 call: 'total current capacity ~38,000 GPUs' incl. Iceland & KC, 'by end of March'; Q1'25 letter: mostly H200 | https://equibles.com/stocks/nbis/calls/2024-q4; https://www.sec.gov/Archives/edgar/data/1513845/000110465925050975/tm2515580d1_ex99-2.htm
Company | Q1'25 | Active MW | not disclosed | — | Locations: Finland, Paris, Iceland (KC online Apr) | https://www.sec.gov/Archives/edgar/data/1513845/000110465925050975/tm2515580d1_ex99-2.htm
Company | Q2'25 | Active MW | not disclosed | — | 5 active locations at end Q2 (Finland, Paris, Iceland, KC, +Israel announced) | https://www.sec.gov/Archives/edgar/data/1513845/000110465925075028/tm2522866d1_ex99-2.htm
Company | Q2'25 | GPUs deployed | not disclosed | — | B200 rollout began Q2'25; GB200 GA in Europe Jun 2025 | https://www.sec.gov/Archives/edgar/data/1513845/000110465925075028/tm2522866d1_ex99-2.htm
Company | Q3'25 | Active MW | not disclosed | — | Guide: 220 MW connected / 100 MW active by YE25 | https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm
Company | Q4'25 | Active MW | ~170 MW | Reported | Q4'25 letter / 20-F: ~170 MW active at Dec 31 2025 (vs 100 MW target) | https://www.sec.gov/Archives/edgar/data/1513845/000110465926013946/tm266173d1_ex99-2.htm; https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Company | Q4'25 | Connected MW | ~220 MW (target) | Reported target, actual n/d | YE25 connected target 220 MW (Aug & Nov 2025); actual YE25 connected not explicitly reported | https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm
Company | Q4'25 | Contracted MW | n/d at YE; >2,000 MW by Feb 12 2026 | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465926013946/tm266173d1_ex99-2.htm
Company | Q1'26 | Active MW | not disclosed | — | Letter: delivered all commitments; 'significantly increase capacity in place in 3Q' | https://assets.nebius.com/assets/aa1bc2e6-df83-40cd-a6a2-95e7cda3d16c/Nebius%20SHL_Q1%202026.pdf
Company | Q1'26 | Contracted MW | >3,500 MW (as of May 13 2026) | Reported | owned >75% | https://assets.nebius.com/assets/aa1bc2e6-df83-40cd-a6a2-95e7cda3d16c/Nebius%20SHL_Q1%202026.pdf
Company | Q2'26 | Active MW | not disclosed | — | Letter: added capacity in US & Europe late Q2; no MW figure | https://assets.nebius.com/assets/4462517b-ce83-41f2-96ed-f2ac1bc06a05/SHLQ226%20%281%29.pdf
Company | Q2'26 | Contracted MW | n/d (YE26 target raised to 5 GW) | Reported target |  | https://assets.nebius.com/assets/4462517b-ce83-41f2-96ed-f2ac1bc06a05/SHLQ226%20%281%29.pdf
Mäntsälä #1 | Q1'24 | Live MW / GPUs / GPU gen | 25 MW site capacity (live MW n/d); H100 | Reported (capacity) | Pre-expansion capacity 25 MW per DCD | https://www.datacenterdynamics.com/en/news/nebius-to-deploy-5mw-nvidia-h200-cluster-at-patmos-data-center-in-kansas-city-missouri/
Mäntsälä #1 | Q2'24 | Live MW / GPUs / GPU gen | 25 MW site capacity; H100 | Reported (capacity) |  | https://www.datacenterdynamics.com/en/news/nebius-to-deploy-5mw-nvidia-h200-cluster-at-patmos-data-center-in-kansas-city-missouri/
Mäntsälä #1 | Q3'24 | Live MW / GPUs / GPU gen | 25 MW site capacity; H100 (+H200 from Nov) | Reported (capacity) | Expansion announced Oct 8 2024 | https://nebius.com/newsroom/nebius-to-triple-capacity-at-finland-data-center-to-75-mw
Mäntsälä #1 | Q4'24 | Live MW / GPUs / GPU gen | 25 MW site capacity; H100/H200 | Reported (capacity) | Q4'24 call: first part of expansion due Q3'25 | https://equibles.com/stocks/nbis/calls/2024-q4
Mäntsälä #1 | Q1'25 | Live MW / GPUs / GPU gen | 25 MW; H100/H200 | Derived | No change disclosed until Q3'25 phase 1 | https://www.fool.com/earnings/call-transcripts/2025/05/20/nebius-nbis-q1-2025-earnings-call-transcript/
Mäntsälä #1 | Q2'25 | Live MW / GPUs / GPU gen | 25 MW; H100/H200 + GB200 (Europe GA Jun-25, site assumed Finland — inference) | Estimated | GB200 location not stated | https://www.sec.gov/Archives/edgar/data/1513845/000110465925075028/tm2522866d1_ex99-2.htm
Mäntsälä #1 | Q3'25 | Live MW / GPUs / GPU gen | Expansion phase 1 targeted late Q3'25 (MW n/d) | Reported (plan) |  | https://www.fool.com/earnings/call-transcripts/2025/05/20/nebius-nbis-q1-2025-earnings-call-transcript/
Mäntsälä #1 | Q4'25 | Live MW / GPUs / GPU gen | Expansion 'should be completed by end of year' (MW n/d); B300/GB300 deployment began 2025 | Reported (plan) |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm
Mäntsälä #1 | Q1'26 | Live MW / GPUs / GPU gen | 75 MW built ('completed earlier this year'); GB300 NVL72 operational | Reported | Live/active share n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Mäntsälä #1 | Q2'26 | Live MW / GPUs / GPU gen | 75 MW built; GB300 NVL72 | Reported |  | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Paris (Equinix PA10) | Q1'24 | Live MW / GPUs / GPU gen | not disclosed | —
Paris (Equinix PA10) | Q2'24 | Live MW / GPUs / GPU gen | not disclosed | —
Paris (Equinix PA10) | Q3'24 | Live MW / GPUs / GPU gen | Deployment underway; H200 | Reported |  | https://nebius.com/blog/posts/nebius-launches-gpu-cluster-in-paris-france
Paris (Equinix PA10) | Q4'24 | Live MW / GPUs / GPU gen | Live Nov 2024; H200; MW n/d | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465925015480/tm257185d1_ex99-1.htm
Paris (Equinix PA10) | Q1'25 | Live MW / GPUs / GPU gen | Live; H200; MW n/d | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465925050975/tm2515580d1_ex99-2.htm
Paris (Equinix PA10) | Q2'25 | Live MW / GPUs / GPU gen | Live; H200 | Reported |  | https://docs.nebius.com/overview/regions
Paris (Equinix PA10) | Q3'25 | Live MW / GPUs / GPU gen | Live; H200 | Reported |  | https://docs.nebius.com/overview/regions
Paris (Equinix PA10) | Q4'25 | Live MW / GPUs / GPU gen | Live; H200 | Reported |  | https://docs.nebius.com/overview/regions
Paris (Equinix PA10) | Q1'26 | Live MW / GPUs / GPU gen | Live; H200 | Reported |  | https://docs.nebius.com/overview/regions
Paris (Equinix PA10) | Q2'26 | Live MW / GPUs / GPU gen | Live; H200 | Reported |  | https://docs.nebius.com/overview/regions
Keflavik (Verne) | Q1'24 | Live MW / GPUs / GPU gen | not disclosed | —
Keflavik (Verne) | Q2'24 | Live MW / GPUs / GPU gen | not disclosed | —
Keflavik (Verne) | Q3'24 | Live MW / GPUs / GPU gen | not disclosed | —
Keflavik (Verne) | Q4'24 | Live MW / GPUs / GPU gen | Agreement signed Dec 2024; not live | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Keflavik (Verne) | Q1'25 | Live MW / GPUs / GPU gen | 10 MW cluster live Mar 2025; H200 | Reported | Assumes full 10 MW at go-live ('fully operational' by end-Mar) | https://nebius.com/blog/posts/300-mw-new-jersey-and-iceland-regions
Keflavik (Verne) | Q2'25 | Live MW / GPUs / GPU gen | 10 MW; H200 | Derived | No change disclosed | https://docs.nebius.com/overview/regions
Keflavik (Verne) | Q3'25 | Live MW / GPUs / GPU gen | 10 MW; H200 | Derived | No change disclosed | https://docs.nebius.com/overview/regions
Keflavik (Verne) | Q4'25 | Live MW / GPUs / GPU gen | 10 MW; H200 | Derived | No change disclosed | https://docs.nebius.com/overview/regions
Keflavik (Verne) | Q1'26 | Live MW / GPUs / GPU gen | 10 MW; H200 | Derived | No change disclosed | https://docs.nebius.com/overview/regions
Keflavik (Verne) | Q2'26 | Live MW / GPUs / GPU gen | 10 MW; H200 | Derived | No change disclosed | https://docs.nebius.com/overview/regions
Kansas City (Patmos) | Q1'24 | Live MW / GPUs / GPU gen | not disclosed | —
Kansas City (Patmos) | Q2'24 | Live MW / GPUs / GPU gen | not disclosed | —
Kansas City (Patmos) | Q3'24 | Live MW / GPUs / GPU gen | not disclosed | —
Kansas City (Patmos) | Q4'24 | Live MW / GPUs / GPU gen | Announced; not live (5 MW phase 1 planned) | Reported |  | https://www.datacenterdynamics.com/en/news/nebius-to-deploy-5mw-nvidia-h200-cluster-at-patmos-data-center-in-kansas-city-missouri/
Kansas City (Patmos) | Q1'25 | Live MW / GPUs / GPU gen | Deploying; live Apr 2025 (i.e., not live at Q1 end) | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465925050975/tm2515580d1_ex99-2.htm
Kansas City (Patmos) | Q2'25 | Live MW / GPUs / GPU gen | 5 MW phase 1 live (H200); phase 2 B200 being installed | Reported (MW = initial-phase capacity) |  | https://www.fool.com/earnings/call-transcripts/2025/05/20/nebius-nbis-q1-2025-earnings-call-transcript/
Kansas City (Patmos) | Q3'25 | Live MW / GPUs / GPU gen | Phase 2 added early Jul 2025; first B200 cluster launched; MW n/d (≤40 MW cap) | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm
Kansas City (Patmos) | Q4'25 | Live MW / GPUs / GPU gen | H200 + B200; MW n/d | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm
Kansas City (Patmos) | Q1'26 | Live MW / GPUs / GPU gen | H200/B200/RTX PRO 6000; MW n/d | Reported |  | https://docs.nebius.com/overview/regions
Kansas City (Patmos) | Q2'26 | Live MW / GPUs / GPU gen | H200/B200/RTX PRO 6000; MW n/d | Reported |  | https://docs.nebius.com/overview/regions
Vineland (DataOne) | Q1'24 | Live MW / GPUs / GPU gen | not disclosed | —
Vineland (DataOne) | Q2'24 | Live MW / GPUs / GPU gen | not disclosed | —
Vineland (DataOne) | Q3'24 | Live MW / GPUs / GPU gen | not disclosed | —
Vineland (DataOne) | Q4'24 | Live MW / GPUs / GPU gen | not disclosed | —
Vineland (DataOne) | Q1'25 | Live MW / GPUs / GPU gen | Announced (up to 300 MW); under construction | Reported |  | https://nebius.com/blog/posts/300-mw-new-jersey-and-iceland-regions
Vineland (DataOne) | Q2'25 | Live MW / GPUs / GPU gen | Under construction; 200 MW contracted | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465925075028/tm2522866d1_ex99-2.htm
Vineland (DataOne) | Q3'25 | Live MW / GPUs / GPU gen | Opening end of summer 2025 targeted; 100 MW to be available in 2025 | Reported (plan) |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465925075028/tm2522866d1_ex99-2.htm
Vineland (DataOne) | Q4'25 | Live MW / GPUs / GPU gen | MSFT tranche 1 delivered Nov 2025; MW n/d (plan: 100 MW in 2025) | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Vineland (DataOne) | Q1'26 | Live MW / GPUs / GPU gen | MSFT tranche 2 delivered Feb 2026; MW n/d | Reported |  | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Vineland (DataOne) | Q2'26 | Live MW / GPUs / GPU gen | Additional MSFT tranches delivered (all to date); building finished summer 2026; MW n/d | Reported |  | https://assets.nebius.com/assets/4462517b-ce83-41f2-96ed-f2ac1bc06a05/SHLQ226%20%281%29.pdf
Modi'in (Mega Or) | Q1'24 | Live MW / GPUs / GPU gen | not disclosed | —
Modi'in (Mega Or) | Q2'24 | Live MW / GPUs / GPU gen | not disclosed | —
Modi'in (Mega Or) | Q3'24 | Live MW / GPUs / GPU gen | not disclosed | —
Modi'in (Mega Or) | Q4'24 | Live MW / GPUs / GPU gen | not disclosed | —
Modi'in (Mega Or) | Q1'25 | Live MW / GPUs / GPU gen | not disclosed | —
Modi'in (Mega Or) | Q2'25 | Live MW / GPUs / GPU gen | Lease signed May 2025 (8 MW) | Reported |  | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Modi'in (Mega Or) | Q3'25 | Live MW / GPUs / GPU gen | Facility began operations Sep 2025 (Mega Or); Nebius launch Oct | Reported |  | https://www.calcalistech.com/ctechnews/article/p4ds17rzm
Modi'in (Mega Or) | Q4'25 | Live MW / GPUs / GPU gen | 8 MW; 4,000 HGX B200 | Reported |  | https://nebius.com/newsroom/nebius-brings-nvidia-blackwell-to-israel-with-one-of-the-country-s-first-ai-infrastructure-deployments
Modi'in (Mega Or) | Q1'26 | Live MW / GPUs / GPU gen | 8 MW; 4,000 HGX B200 | Reported |  | https://nebius.com/newsroom/nebius-brings-nvidia-blackwell-to-israel-with-one-of-the-country-s-first-ai-infrastructure-deployments
Modi'in (Mega Or) | Q2'26 | Live MW / GPUs / GPU gen | 8 MW; 4,000 HGX B200 | Reported |  | https://nebius.com/newsroom/nebius-brings-nvidia-blackwell-to-israel-with-one-of-the-country-s-first-ai-infrastructure-deployments
London Longcross (Ark) | Q1'24 | Live MW / GPUs / GPU gen | not disclosed | —
London Longcross (Ark) | Q2'24 | Live MW / GPUs / GPU gen | not disclosed | —
London Longcross (Ark) | Q3'24 | Live MW / GPUs / GPU gen | not disclosed | —
London Longcross (Ark) | Q4'24 | Live MW / GPUs / GPU gen | not disclosed | —
London Longcross (Ark) | Q1'25 | Live MW / GPUs / GPU gen | not disclosed | —
London Longcross (Ark) | Q2'25 | Live MW / GPUs / GPU gen | Announced Jun 2025; not live | Reported |  | https://www.datacenterdynamics.com/en/news/nebius-to-host-uk-nvidia-blackwell-ultra-gpu-cluster-in-ark-data-centres-facility-in-surrey/
London Longcross (Ark) | Q3'25 | Live MW / GPUs / GPU gen | Not live (target Q4'25) | Reported |  | https://www.datacenterdynamics.com/en/news/nebius-to-host-uk-nvidia-blackwell-ultra-gpu-cluster-in-ark-data-centres-facility-in-surrey/
London Longcross (Ark) | Q4'25 | Live MW / GPUs / GPU gen | 16 MW; 4,000 HGX B300 (phase 1) | Reported |  | https://www.datacenterdynamics.com/en/news/nebius-launches-nvidia-gpu-cluster-in-london-uk/
London Longcross (Ark) | Q1'26 | Live MW / GPUs / GPU gen | 16 MW; B300; phase 2 (+3,000 B300) timing n/d | Reported | Q3'25 letter: next UK phase Q1 2026 | https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm
London Longcross (Ark) | Q2'26 | Live MW / GPUs / GPU gen | 16 MW live + 3 MW in delivery; B300 (up to 7,000 GPUs if phase 2 done — unconfirmed) | Reported |  | https://datacentrenews.uk/story/nebius-fills-ark-s-longcross-data-centre-to-capacity
Mäntsälä #2 | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Mäntsälä #2 | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Mäntsälä #2 | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Mäntsälä #2 | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Mäntsälä #2 | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Mäntsälä #2 | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Mäntsälä #2 | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Mäntsälä #2 | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Mäntsälä #2 | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Mäntsälä #2 | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Lappeenranta | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Lappeenranta | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Lappeenranta | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Lappeenranta | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Lappeenranta | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Lappeenranta | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Lappeenranta | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Lappeenranta | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Lappeenranta | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Lappeenranta | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Béthune | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Béthune | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Béthune | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Béthune | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Béthune | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Béthune | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Béthune | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Béthune | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Béthune | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (first capacity targeted late summer 2026) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Béthune | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (first capacity targeted late summer 2026) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
France 2nd colo | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Harlow (Kao) | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
Harlow (Kao) | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
Harlow (Kao) | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
Harlow (Kao) | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
Harlow (Kao) | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
Harlow (Kao) | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
Harlow (Kao) | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
Harlow (Kao) | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
Harlow (Kao) | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
Harlow (Kao) | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-22mw-capacity-agreement-with-kao-data-in-the-uk/
UK 3rd new site | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
UK 3rd new site | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
UK 3rd new site | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
UK 3rd new site | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
UK 3rd new site | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
UK 3rd new site | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
UK 3rd new site | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
UK 3rd new site | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
UK 3rd new site | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
UK 3rd new site | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
Masmiyya | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Madrid-Getafe | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Madrid-Getafe | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Madrid-Getafe | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Madrid-Getafe | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Madrid-Getafe | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Madrid-Getafe | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Madrid-Getafe | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Madrid-Getafe | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Madrid-Getafe | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Madrid-Getafe | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-signs-18mw-lease-with-merlin-properties-at-spain-data-center-report/
Tallinn Hüüru | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Tallinn Hüüru | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Tallinn Hüüru | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Tallinn Hüüru | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Tallinn Hüüru | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Tallinn Hüüru | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Tallinn Hüüru | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Tallinn Hüüru | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Tallinn Hüüru | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Tallinn Hüüru | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Independence MO | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Independence MO | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Independence MO | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Independence MO | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Independence MO | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Independence MO | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Independence MO | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Independence MO | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Independence MO | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Independence MO | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/independencemo
Birmingham AL | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Birmingham AL | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Birmingham AL | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Birmingham AL | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Birmingham AL | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Birmingham AL | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Birmingham AL | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Birmingham AL | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Birmingham AL | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Birmingham AL | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://nebius.com/birminghamal
Pennsylvania | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Pennsylvania | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Pennsylvania | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Pennsylvania | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Pennsylvania | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Pennsylvania | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Pennsylvania | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Pennsylvania | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Pennsylvania | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Pennsylvania | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.datacenterdynamics.com/en/news/nebius-details-plans-for-12gw-data-center-campus-in-pennsylvania/
Oklahoma colo | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Oklahoma colo | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Oklahoma colo | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Oklahoma colo | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Oklahoma colo | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Oklahoma colo | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Oklahoma colo | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Oklahoma colo | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Oklahoma colo | Q1'26 | Live MW / GPUs / GPU gen | not disclosed (secured Feb 2026; Minnesota region us-north1 B300 live per docs as of Oct 2026) | — | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Oklahoma colo | Q2'26 | Live MW / GPUs / GPU gen | not disclosed (secured Feb 2026; Minnesota region us-north1 B300 live per docs as of Oct 2026) | — | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q1'26 | Live MW / GPUs / GPU gen | not disclosed (secured Feb 2026; Minnesota region us-north1 B300 live per docs as of Oct 2026) | — | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Minnesota colo | Q2'26 | Live MW / GPUs / GPU gen | not disclosed (secured Feb 2026; Minnesota region us-north1 B300 live per docs as of Oct 2026) | — | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
AIB SE-US | Q1'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html
AIB SE-US | Q2'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html
AIB SE-US | Q3'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html
AIB SE-US | Q4'24 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html
AIB SE-US | Q1'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html
AIB SE-US | Q2'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html
AIB SE-US | Q3'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html
AIB SE-US | Q4'25 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html
AIB SE-US | Q1'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html
AIB SE-US | Q2'26 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) | Derived | Site announced or first capacity dated after the quarter / not live by Q2'26; Minnesota & Oklahoma live status by Q2'26 n/d | https://www.globenewswire.com/news-release/2026/09/30/3371855/0/en/aib-data-centers-signs-contract-with-nebius-for-ai-data-center-capacity.html

## KPI pivot
Entity | Metric | Q1'24 | Q2'24 | Q3'24 | Q4'24 | Q1'25 | Q2'25 | Q3'25 | Q4'25 | Q1'26 | Q2'26
Company | Active MW | not disclosed [Reported (none)] | not disclosed [Reported (none)] | not disclosed [—] | not disclosed | not disclosed [—] | not disclosed [—] | not disclosed [—] | ~170 MW [Reported] | not disclosed [—] | not disclosed [—]
Company | GPUs deployed | not disclosed [Reported (none)] | not disclosed [Reported (none)] | ~10,000 (est.) [Estimated] | >20,000 (est.) [Estimated] | ~38,000 (mostly H200, remainder H100) [Reported] | not disclosed [—] | not disclosed | not disclosed | not disclosed | not disclosed
Company | Connected MW | not disclosed | not disclosed | not disclosed | 25 MW [Reported] | not disclosed | not disclosed | not disclosed | ~220 MW (target) [Reported target, actual n/d] | not disclosed | not disclosed
Company | Contracted MW | not disclosed | not disclosed | not disclosed | not disclosed | not disclosed | not disclosed | not disclosed | n/d at YE; >2,000 MW by Feb 12 2026 [Reported] | >3,500 MW (as of May 13 2026) [Reported] | n/d (YE26 target raised to 5 GW) [Reported target]
Mäntsälä #1 | Live MW / GPUs / GPU gen | 25 MW site capacity (live MW n/d); H100 [Reported (capacity)] | 25 MW site capacity; H100 [Reported (capacity)] | 25 MW site capacity; H100 (+H200 from Nov) [Reported (capacity)] | 25 MW site capacity; H100/H200 [Reported (capacity)] | 25 MW; H100/H200 [Derived] | 25 MW; H100/H200 + GB200 (Europe GA Jun-25, site assumed Finland — inference) [Estimated] | Expansion phase 1 targeted late Q3'25 (MW n/d) [Reported (plan)] | Expansion 'should be completed by end of year' (MW n/d); B300/GB300 deployment began 2025 [Reported (plan)] | 75 MW built ('completed earlier this year'); GB300 NVL72 operational [Reported] | 75 MW built; GB300 NVL72 [Reported]
Paris (Equinix PA10) | Live MW / GPUs / GPU gen | not disclosed [—] | not disclosed [—] | Deployment underway; H200 [Reported] | Live Nov 2024; H200; MW n/d [Reported] | Live; H200; MW n/d [Reported] | Live; H200 [Reported] | Live; H200 [Reported] | Live; H200 [Reported] | Live; H200 [Reported] | Live; H200 [Reported]
Keflavik (Verne) | Live MW / GPUs / GPU gen | not disclosed [—] | not disclosed [—] | not disclosed [—] | Agreement signed Dec 2024; not live [Reported] | 10 MW cluster live Mar 2025; H200 [Reported] | 10 MW; H200 [Derived] | 10 MW; H200 [Derived] | 10 MW; H200 [Derived] | 10 MW; H200 [Derived] | 10 MW; H200 [Derived]
Kansas City (Patmos) | Live MW / GPUs / GPU gen | not disclosed [—] | not disclosed [—] | not disclosed [—] | Announced; not live (5 MW phase 1 planned) [Reported] | Deploying; live Apr 2025 (i.e., not live at Q1 end) [Reported] | 5 MW phase 1 live (H200); phase 2 B200 being installed [Reported (MW = initial-phase capacity)] | Phase 2 added early Jul 2025; first B200 cluster launched; MW n/d (≤40 MW cap) [Reported] | H200 + B200; MW n/d [Reported] | H200/B200/RTX PRO 6000; MW n/d [Reported] | H200/B200/RTX PRO 6000; MW n/d [Reported]
Vineland (DataOne) | Live MW / GPUs / GPU gen | not disclosed [—] | not disclosed [—] | not disclosed [—] | not disclosed [—] | Announced (up to 300 MW); under construction [Reported] | Under construction; 200 MW contracted [Reported] | Opening end of summer 2025 targeted; 100 MW to be available in 2025 [Reported (plan)] | MSFT tranche 1 delivered Nov 2025; MW n/d (plan: 100 MW in 2025) [Reported] | MSFT tranche 2 delivered Feb 2026; MW n/d [Reported] | Additional MSFT tranches delivered (all to date); building finished summer 2026; MW n/d [Reported]
Modi'in (Mega Or) | Live MW / GPUs / GPU gen | not disclosed [—] | not disclosed [—] | not disclosed [—] | not disclosed [—] | not disclosed [—] | Lease signed May 2025 (8 MW) [Reported] | Facility began operations Sep 2025 (Mega Or); Nebius launch Oct [Reported] | 8 MW; 4,000 HGX B200 [Reported] | 8 MW; 4,000 HGX B200 [Reported] | 8 MW; 4,000 HGX B200 [Reported]
London Longcross (Ark) | Live MW / GPUs / GPU gen | not disclosed [—] | not disclosed [—] | not disclosed [—] | not disclosed [—] | not disclosed [—] | Announced Jun 2025; not live [Reported] | Not live (target Q4'25) [Reported] | 16 MW; 4,000 HGX B300 (phase 1) [Reported] | 16 MW; B300; phase 2 (+3,000 B300) timing n/d [Reported] | 16 MW live + 3 MW in delivery; B300 (up to 7,000 GPUs if phase 2 done — unconfirmed) [Reported]
Mäntsälä #2 | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Lappeenranta | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Béthune | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (first capacity targeted late summer 2026) [Derived] | 0 MW live (first capacity targeted late summer 2026) [Derived]
France 2nd colo | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Harlow (Kao) | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
UK 3rd new site | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Masmiyya | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Beit Shemesh | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Madrid-Getafe | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Tallinn Hüüru | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Independence MO | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Birmingham AL | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Pennsylvania | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]
Oklahoma colo | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | not disclosed (secured Feb 2026; Minnesota region us-north1 B300 live per docs as of Oct 2026) [—] | not disclosed (secured Feb 2026; Minnesota region us-north1 B300 live per docs as of Oct 2026) [—]
Minnesota colo | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | not disclosed (secured Feb 2026; Minnesota region us-north1 B300 live per docs as of Oct 2026) [—] | not disclosed (secured Feb 2026; Minnesota region us-north1 B300 live per docs as of Oct 2026) [—]
AIB SE-US | Live MW / GPUs / GPU gen | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived] | 0 MW live (not yet announced/energized in history window) [Derived]

## YE2026 energized vs guide
Site | Low MW | Base MW | High MW | Basis (INFERENCE unless Reported) | Source
Mäntsälä #1 | 75 | 75 | 75 | 75 MW expansion completed early 2026 (Reported built) | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
Paris (Equinix PA10) | 5 | 5 | 5 | MW never disclosed; 5 MW = third-party DC Atlas (Estimated, low confidence) | https://dcatlas.io/en/explore/facilities/nebius-equinix-paris
Keflavik (Verne) | 10 | 10 | 10 | 10 MW live since Mar 2025 (Reported) | https://nebius.com/blog/posts/300-mw-new-jersey-and-iceland-regions
Kansas City (Patmos) | 5 | 20 | 40 | 5 MW phase 1 reported; phase 2 MW n/d; 40 MW = stated max. Base 20 = Estimated midpoint | https://www.datacenterdynamics.com/en/news/nebius-to-deploy-5mw-nvidia-h200-cluster-at-patmos-data-center-in-kansas-city-missouri/
Vineland (DataOne) | 200 | 200 | 300 | Q2'25: 100 MW in 2025 + 100 MW in 2026 = 200 MW (Reported plan); 300 MW = site max; Q2'26 call: Vineland part of 2026 connected power. Risk: Bloom switch + site-plan hearing | https://www.sec.gov/Archives/edgar/data/1513845/000110465925075028/tm2522866d1_ex99-2.htm
London Longcross (Ark) | 16 | 19 | 19 | 16 MW live + 3 MW in delivery (Ark, Jun 2026); LP02 36 MW timing n/d (excluded) | https://datacentrenews.uk/story/nebius-fills-ark-s-longcross-data-centre-to-capacity
Harlow (Kao) | 0 | 0 | 4.4 | 22 MW total; bulk in KLON-03 from early 2027; 4.4 MW in KLON-02 is a third-party inference | https://northwiseproject.com/research/nebius-harlow-data-center
UK 3rd new site | 0 | 0 | 0 | not disclosed (counted 0) | https://nebius.com/newsroom/nebius-expands-in-uk-with-more-nvidia-powered-infrastructure-more-customers-and-more-cloud-capabilities-for-agentic-and-enterprise-ai
Modi'in (Mega Or) | 8 | 8 | 8 | 8 MW live since Oct 2025 (Reported) | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Masmiyya (Mega DC) | 0 | 22 | 22 | 22 MW, delivery Q3 2026 (landlord disclosure) | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Beit Shemesh (Mega DC) | 0 | 29 | 58 | 58 MW staged Q3'26–Q1'27; base = half by YE26 (Estimated: linear over 3 quarters ≈ 2/3, rounded down to 1/2 for slippage) | https://www.datacenterdynamics.com/en/news/nebius-signs-80mw-data-center-lease-with-mega-or-in-israel/
Madrid-Getafe (Merlin Edged) | 9 | 18 | 18 | 18 MW; phase 1 live Sep 2026, phases 2-3 'coming weeks' | https://www.linkedin.com/feed/update/urn:li:activity:7505906816590073857
Tallinn Hüüru (Greenergy) | 0 | 22 | 22 | 22 MW first phase 'later in 2026' | https://www.datacenterdynamics.com/en/news/nebius-expands-european-presence-announces-deployment-in-estonia-and-second-data-center-in-m%C3%A4nts%C3%A4l%C3%A4-finland/
Béthune (Azur) | 0 | 120 | 120 | Nebius CCO: ~half (120 MW) operational by end-2026 | https://www.reuters.com/technology/amsterdam-based-ai-firm-nebius-build-240mw-data-centre-near-lille-france-2026-02-12/
Birmingham BHM01 | 0 | 50 | 100 | Nebius page: initial-phase energization Q4 2026; Q1'26 letter: operational 2027; phase 1 ~100 MW press-reported; base = 50% (Estimated) | https://nebius.com/birminghamal
Independence MO | 0 | 0 | 0 | IPL initial power 2H 2026 but MW n/d; letter: operational 2027 → counted 0 (upside not quantifiable) | https://nebius.com/independencemo
Minnesota colo | 0 | 0 | 0 | MW not disclosed (region live) → counted 0; upside | https://docs.nebius.com/overview/regions
Oklahoma colo | 0 | 0 | 0 | MW not disclosed → counted 0; upside | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
France 2nd colo | 0 | 0 | 0 | not disclosed → 0; upside | https://www.sec.gov/Archives/edgar/data/1513845/000110465926052948/nbis-20251231x20f.htm
Lappeenranta / Mäntsälä #2 / Pennsylvania / AIB | 0 | 0 | 0 | First capacity 2027+ (Reported) / AIB date n/d | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
TOTAL identified | 328 | 598 | 801.4 | Guide: 800 MW–1 GW CONNECTED by YE2026 (not active). Gap to 800: low 472 / base 202 / high -1 MW

## Company targets history
Date | Target / disclosure | Source
2024-10-08 | Mäntsälä tripled to 75 MW; >$1B Europe AI infra by mid-2025 | https://nebius.com/newsroom/nebius-to-triple-capacity-at-finland-data-center-to-75-mw
2024-10-31 | Expect >20,000 GPUs deployed by YE2024 | https://exa.ai/library/markets/stocks/NBIS/earnings/FY2024/Q3/transcript
2025-02-20 | ~38,000 GPUs by end-Mar 2025; 100 MW 'in operations' by YE2025; new facilities scalable to >300 MW | https://equibles.com/stocks/nbis/calls/2024-q4
2025-05-20 | ~100 MW contracted capacity by YE2025; >1 GW pipeline 'in the midterm' | https://www.sec.gov/Archives/edgar/data/1513845/000110465925050975/tm2515580d1_ex99-2.htm
2025-08-07 | 220 MW connected by YE2025 (of which 100 MW active); >1 GW contracted by YE2026 | https://www.sec.gov/Archives/edgar/data/1513845/000110465925075028/tm2522866d1_ex99-2.htm
2025-11-11 | >2.5 GW contracted by YE2026; 800 MW–1 GW connected by YE2026; 220 MW connected/100 MW active YE25 on track | https://www.sec.gov/Archives/edgar/data/1513845/000110465925109806/tm2530882d1_ex99-2.htm
2026-02-12 | Actual ~170 MW active YE2025; >2 GW contracted already; YE26 target >3 GW; 16 sites; 800 MW–1 GW connected reaffirmed | https://www.sec.gov/Archives/edgar/data/1513845/000110465926013946/tm266173d1_ex99-2.htm
2026-03-31 | >750 MW contracted in EMEA (own + colo) | https://assets.nebius.com/assets/6590d0a0-0fc4-4396-bc3f-f52a9ccb770e/20260331%20Nebius%20to%20construct%20310%20MW%20AI%20factory%20in%20Finland.pdf
2026-05-13 | >3.5 GW contracted; YE26 target >4 GW; owned >75% of contracted; owned = 3 GW across 5 sites; 800 MW–1 GW connected reaffirmed | https://assets.nebius.com/assets/aa1bc2e6-df83-40cd-a6a2-95e7cda3d16c/Nebius%20SHL_Q1%202026.pdf
2026-08-12 | YE26 contracted target 5 GW; deploy >1 GW/yr starting 2027; 800 MW–1 GW connected YE26 reaffirmed on call (active through 1H27); asset-light partner model | https://assets.nebius.com/assets/4462517b-ce83-41f2-96ed-f2ac1bc06a05/SHLQ226%20%281%29.pdf; https://stockanalysis.com/stocks/nbis/transcripts/655490-q2-2026/