## README
Nebius Capacity & Power — Site Tracker (Wednesday-ready)
Built: 2026-10-05 08:30 ET
Purpose: one-row-per-site YE26/YE27/YE28 energized MW + company totals + locked billing path for Modeling handoff.
Tabs
README — this page
By_Site — one row per site from nebius_capacity.xlsx v2 Sites/Quarterly MW/Basis/Capacity tranches
Company_Totals — IT-normalized energized, gross-normalized, connected, stated-basis, billing (raw workbook) Q3'26–Q4'28
Billing_Lock — LOCKED team figures (~258/284 YE26; ~475/645 FY27 avg). Do not use ~350/~710 shortcuts.
Sources — file and disclosure map
Standards
Blue font / light-blue fill = hardcoded input. Black = formula or copied static value from capacity workbook.
Every numeric cell has Tag (Reported / Derived / Estimated) and Source.
Static values: this file stores calculated numbers from nebius_capacity.xlsx (data_only). Re-run build after capacity model changes.
Locked billing (do not change)
Base YE26 billing ~258 MW; FY27 average billing ~475 MW
High YE26 billing ~284 MW; FY27 average billing ~645 MW
Source: vineland_watch.md §0c (Modeling + Skeptic lock, Oct 5 AM ET); Derived from capacity v2 billing with 1-quarter lag.
Company YE energized IT (from capacity v2 IT-normalized series, Derived)
YE26 base/low/high: 301.72 / 189.49 / 413.95
YE27 base/low/high: 1081.92 / 794.61 / 1369.24
YE28 base/low/high: 1652.76 / 1407.61 / 1897.9
Scope: public info only. No invented MW. Missing announced MW / ownership flagged on By_Site.
Oct 5 ~10:30 AM ET — colo MW gap pass + owned-campus power path + tranche search
Workstream A: Newport/UK3/MN/OK/France2nd re-searched; Nebius absolute MW still n/d (facility/category leads on By_Site Notes). Locked billing UNCHANGED (258/475 base; 284/645 high). Workstream B: owned_campus_power_path.md (Independence/Butler/Birmingham). Workstream C: Microsoft per-tranche MW not disclosed; 26.7 IT remains Estimated (vineland_watch.md §2).

## By_Site
Site | Country | Owned/leased | Ownership detail | GPU generation | Customer | Contracted vs unsold | Risk grade | Announced/contracted MW | Announced MW basis | Announced MW tag | Energized basis (stated) | Gross/IT factor | YE26 energized low | YE26 energized base | YE26 energized high | YE27 energized low | YE27 energized base | YE27 energized high | YE28 energized low | YE28 energized base | YE28 energized high | YE26 IT-norm base (est) | YE27 IT-norm base (est) | YE28 IT-norm base (est) | Connected MW (company path) | Status / go-live (evidence) | Missing announced MW? | Missing ownership? | Tag (energized path) | Source | Q3 2026 base | Q4 2026 base | Q1 2027 base | Q2 2027 base | Q3 2027 base | Q4 2027 base | Q1 2028 base | Q2 2028 base | Q3 2028 base | Q4 2028 base | Notes
Vineland NJ (DataOne) | USA | leased | Build-to-suit (DataOne owns shell; Nebius tenant) | GB300 NVL72 (assumed) | Microsoft | Contracted ($17.39B TCV, 9 tranches) | Yellow/Red | 300 | Contracted 300 = gross (Estimated); energized rows = IT MW (altdata power-bounde | Reported | IT | 1.2 | 57 | 81.8 | 106.6 | 230 | 235 | 240 | 230 | 235 | 240 | 81.8 | 235 | 235 | see Company_Totals (no per-site connected series in v2) | ~107 MW IT ceiling on rented gensets through YE26; Bloom-powered remainder 1H-2H 2027 |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 66 | 81.8 | 118.5 | 168.5 | 200 | 235 | 235 | 235 | 235 | 235 | Energized IT; contracted 300 = gross; capped 240 IT; Bloom T5-T9 risk — see vineland_watch.md
Independence MO (Eastgate) | USA | owned | Owned greenfield | Vera Rubin NVL72 | unassigned (Meta #2 candidate - assumed) | Contracted | Green | 1200 | unknown (likely gross/utility) | Reported | stated/unknown | 1.35 | 0 | 0 | 0 | 50 | 125 | 200 | 200 | 225 | 250 | 0 | 92.59 | 166.67 | see Company_Totals (no per-site connected series in v2) | Phase 1 ~Q3 2027; 600 MW not before 2029 |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 0 | 0 | 0 | 50 | 125 | 125 | 175 | 175 | 225
Butler Twp PA (Highridge) | USA | owned | Owned greenfield | Vera Rubin NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Red | 1200 | unknown (PPL ESA = utility/gross) | Reported | stated/unknown | 1.35 | 0 | 0 | 0 | 0 | 65 | 130 | 130 | 265 | 400 | 0 | 48.15 | 196.3 | see Company_Totals (no per-site connected series in v2) | First MW Q4 2027 at best; base ~Q2 2028-2029 (PPL lines late-27 to early-29; 3-yr build) |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 0 | 0 | 0 | 0 | 65 | 130 | 130 | 130 | 265
Birmingham AL (BHM01, Oxmoor) | USA | owned | Owned brownfield | Vera Rubin NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Yellow | 300 | unknown (300 MW is press figure, not Nebius) | Reported | stated/unknown | 1.35 | 0 | 0 | 0 | 50 | 75 | 100 | 200 | 250 | 300 | 0 | 55.56 | 185.19 | see Company_Totals (no per-site connected series in v2) | 115 kV NLT Dec 31 2026; first revenue MW 2027; 230 kV Oct 2027 |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 0 | 12.5 | 25 | 50 | 75 | 75 | 150 | 150 | 250
Bethune FR (Azur Datacenter, ex-Bridgestone) | France | leased | Colocation (20-F); Azur finances/builds | GB300 NVL72 | Meta (#2 likely) - press | Contracted | Yellow | 240 | unknown | Reported | stated/unknown | 1.3 | 0 | 30 | 60 | 120 | 180 | 240 | 240 | 240 | 240 | 23.08 | 138.46 | 184.62 | see Company_Totals (no per-site connected series in v2) | Start Q4 2026 (~27 MW initial); 120 MW ~1H27; prefect ICPE decision pending |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 30 | 73.5 | 120 | 120 | 180 | 180 | 180 | 180 | 240
Lappeenranta FI (Pajarila / Polarnode) | Finland | owned | Owned per Nebius; Polarnode says Nebius 'operates' its campus (conflict) | Vera Rubin NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Green | 310 | unknown | Reported | stated/unknown | 1.15 | 0 | 0 | 0 | 35 | 52.5 | 70 | 140 | 170 | 200 | 0 | 45.65 | 147.83 | see Company_Totals (no per-site connected series in v2) | First building H1 2027 (Fira); substation spring 2027 |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 0 | 0 | 17.5 | 35 | 52.5 | 52.5 | 105 | 105 | 170
Mantsala FI #1 | Finland | owned | Owned | Hopper (first 25 MW) + GB300 NVL72 (expansion, Estimated split) | self-serve (assumed); Meta #1 site not disclosed | Contracted | Green | 75 | unknown; PUE ~1.1 (company) | Reported | stated/unknown | 1.1 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 68.18 | 68.18 | 68.18 | see Company_Totals (no per-site connected series in v2) | 75 MW built (completed early 2026) |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75
Mantsala FI #2 (Kapuli) | Finland | owned | Owned (implied) | Vera Rubin NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Yellow | 70 | unknown (70 MW substation) | Reported | stated/unknown | 1.15 | 0 | 0 | 0 | 0 | 17.5 | 35 | 70 | 70 | 70 | 0 | 15.22 | 60.87 | see Company_Totals (no per-site connected series in v2) | Q4 2027 earliest (substation completes autumn 2027) |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 0 | 0 | 0 | 0 | 17.5 | 52.5 | 70 | 70 | 70
Kansas City MO (Patmos) | USA | leased | Colocation | H200 (first 5 MW) + B200 (rest) | self-serve (assumed) | Unsold / self-serve or undisclosed customer (not disclosed) | Green | 40 | unknown | Reported | stated/unknown | 1.35 | 5 | 20 | 35 | 20 | 30 | 40 | 20 | 30 | 40 | 20 | 30 | 30 | see Company_Totals (no per-site connected series in v2) | Operational; Nebius share of 35 MW facility not disclosed |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 20 | 20 | 20 | 20 | 20 | 30 | 30 | 30 | 30 | 30
Paris (Equinix PA10) | France | leased | Colocation | Hopper H100/H200 | self-serve (assumed) | Unsold / self-serve or undisclosed customer (not disclosed) | Green | 5 | unknown; MW not disclosed (5 = 3rd-party) | Reported | stated/unknown | 1.35 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | see Company_Totals (no per-site connected series in v2) | Operational |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Keflavik IS (Verne) | Iceland | leased | Colocation | Hopper H100/H200 | self-serve (assumed) | Unsold / self-serve or undisclosed customer (not disclosed) | Green | 10 | unknown | Reported | stated/unknown | 1.15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | see Company_Totals (no per-site connected series in v2) | Operational (private region) |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
London Longcross (Ark LP01) | UK | leased | Colocation | B300 (HGX) | self-serve (assumed) | Unsold / self-serve or undisclosed customer (not disclosed) | Green | 19 | unknown (GPU/MW fit suggests gross) | Reported | stated/unknown | 1.3 | 16 | 17.5 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 13.46 | 14.62 | 14.62 | see Company_Totals (no per-site connected series in v2) | 19 MW by ~Q4 2026; LP02 share/timing not disclosed |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 16 | 17.5 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
Harlow UK (Kao Data KLON-02/03) | UK | leased | Colocation (10-yr) | B300 (HGX) | self-serve (assumed) | Unsold / self-serve or undisclosed customer (not disclosed) | Green | 22 | unknown | Reported | stated/unknown | 1.2 | 0 | 2.2 | 4.4 | 22 | 22 | 22 | 22 | 22 | 22 | 2.2 | 22 | 22 | see Company_Totals (no per-site connected series in v2) | KLON-03 completion end-2026; MW early 2027 |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 2.2 | 13.2 | 13.2 | 22 | 22 | 22 | 22 | 22 | 22
Newport UK (Vantage CWL1) | UK | leased | Colocation (Vantage) | GB300 NVL72 | self-serve (assumed) | Unsold / self-serve or undisclosed customer (not disclosed) | Yellow | n/d (Nebius lease); campus ≤~148 MW IT critical (Vantage CWL1, not Nebius share) | Nebius MW not disclosed; UK 65−Harlow 22 = 43 MW for Newport+UK3 (D) | n/d (Nebius) / R (campus) / D (43 residual) | stated/unknown | 1.25 | 0 | 5 | 10 | 20 | 31.5 | 43 | 20 | 31.5 | 43 | 5 | 31.5 | 31.5 | see Company_Totals (no per-site connected series in v2) | Newport + UK 3rd = 65 - 22 (Harlow) = 43 MW by 2027 (Derived); Newport ~29 if LON-East is the 3rd site (low) | YES — Nebius MW still n/d after Oct 5 search |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | Vantage PR Aug 13 2026; Jun 8 UK 65 MW PR; unseen_capacity.md §2; owned_campus_power_path.md N/A | 0 | 5 | 15 | 22.5 | 29 | 31.5 | 31.5 | 31.5 | 31.5 | 31.5 | Vantage+Nebius PR Aug 13 2026: MW not shared (R). CWL1 campus rated up to ~148 MW critical IT (secondary). Model YE27 base 31.5 assumes ~29–32 of the 43 MW residual if UK3≈14 (E, low). Searched: Vantage PR, DCD, Nebius UK Jun 8 PR, docs.nebius.com.
UK 3rd new deployment (lead: Green Mountain LON-East, Romford) | UK | leased | not disclosed | GB300 NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Red | n/d as Nebius; lead = Green Mountain LON-East 14 MW to unnamed neocloud | Landlord disclosed 14 MW (R); customer not named — Nebius unconfirmed | E (lead only) | stated/unknown | 1.25 | 0 | 0 | 0 | 0 | 7 | 14 | 0 | 7 | 14 | 0 | 7 | 7 | see Company_Totals (no per-site connected series in v2) | Lead only: Green Mountain LON-East 14 MW to unnamed neocloud (Sep 1 2026) + Nebius East London job (Feb 2); low confidence | YES — Nebius identity + MW unconfirmed | YES | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | DCD / Green Mountain Sep 1 2026; unseen_capacity.md §2 | 0 | 0 | 0 | 2.5 | 6 | 7 | 7 | 7 | 7 | 7 | Green Mountain Sep 1 2026: 14 MW AI-ready at LON-East Romford to unnamed neocloud (R). East London Nebius job is supporting clue only. If Nebius, Newport residual ≈29 of 43 (D, low). Searched: GM PR, DCD, Property Week, Nebius careers.
Modi'in IL (Mega Or) | Israel | leased | Colocation | B200 (HGX) | self-serve (assumed); 25% to Israel Innovation Authority | Unsold / self-serve or undisclosed customer (not disclosed) | Green | 8 | IT (4,000 B200 / 8 MW = 500/MW fits IT model) | Reported | IT | 1.3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | see Company_Totals (no per-site connected series in v2) | Operational |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Masmiyya IL (Mega DC) | Israel | leased | Colocation (5-yr) | GB300 NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Yellow | 22 | unknown | Reported | stated/unknown | 1.3 | 0 | 5.5 | 11 | 22 | 22 | 22 | 22 | 22 | 22 | 5.5 | 22 | 22 | see Company_Totals (no per-site connected series in v2) | Mega Or Q2-26 deck: Yoav construction completion Q4 2026 -> Q4-26/Q2-27 |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 5.5 | 11 | 16.5 | 22 | 22 | 22 | 22 | 22 | 22
Beit Shemesh IL (Mega DC) | Israel | leased | Colocation (5-yr) | GB300 NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Yellow | 58 | unknown | Reported | stated/unknown | 1.3 | 0 | 0 | 0 | 58 | 58 | 58 | 58 | 58 | 58 | 0 | 58 | 58 | see Company_Totals (no per-site connected series in v2) | Mega Or Q2-26 deck: completion Q2 2027 -> staged Q1-Q4 2027 |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 0 | 10 | 29.5 | 48.5 | 58 | 58 | 58 | 58 | 58
Madrid-Getafe ES (Merlin Edged) | Spain | leased | Colocation | B300 (HGX) | self-serve (assumed) | Unsold / self-serve or undisclosed customer (not disclosed) | Green | 18 | unknown | Reported | stated/unknown | 1.3 | 9 | 13.5 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 13.5 | 18 | 18 | see Company_Totals (no per-site connected series in v2) | Phase 1 live; 18 MW by Q4 2026-Q1 2027 |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 7.5 | 13.5 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
Tallinn EE (Greenergy Huuru) | Estonia | leased | Colocation | GB300 NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Yellow | 22 | unknown | Reported | stated/unknown | 1.2 | 0 | 11 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 11 | 22 | 22 | see Company_Totals (no per-site connected series in v2) | Q4 2026-Q2 2027; Estonian govt security review discussed at Cabinet (Aug 2026) |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 11 | 16.5 | 22 | 22 | 22 | 22 | 22 | 22 | 22
Minnesota colo (us-north1, Woodbury) | USA | leased | Colocation (20-F) | B300 (HGX) | self-serve (assumed) | Unsold / self-serve or undisclosed customer (not disclosed) | Yellow | n/d (Nebius tenant MW); IronGate MSP01 facility 15 MW live / 66 MW full (landlord) | Facility MW = IronGate (R); Nebius share = inference only (E) | E (Nebius) / R (facility) | stated/unknown | 1.3 | 5 | 10 | 15 | 5 | 10 | 15 | 5 | 10 | 15 | 10 | 10 | 10 | see Company_Totals (no per-site connected series in v2) | us-north1 Woodbury; likely IronGate MSP01 (15 MW live, fully leased; inference) | partial — facility MW known; Nebius allocation n/d |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | docs.nebius.com/overview/regions; Woodbury News Net Sep 9 2026 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | us-north1 Woodbury MN (R, docs.nebius.com). IronGate MSP01 401 Bielenberg: 15 MW live, fully leased, 66 MW full build (R, Woodbury News Net Sep 9 2026). Nebius-at-IronGate still inference. Map <100 MW. Model 5/10/15 YE26 L/B/H unchanged. Searched: docs regions, Woodbury News Net, CBRE IronGate flyer, Northwise, PUC/MISO (none naming Nebius).
Oklahoma colo (unnamed) | USA | leased | Colocation (20-F) | GB300 NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Yellow/Red | >100 (map category only); absolute MW n/d | Q2'26 letter map 'Sites >100MW' (R); landlord/town/permits n/d | R (category) / n/d (absolute) | stated/unknown | 1.3 | 10 | 25 | 40 | 75 | 100 | 125 | 75 | 100 | 125 | 25 | 100 | 100 | see Company_Totals (no per-site connected series in v2) | Q2-26 letter map: Sites >100MW; 8 on-site roles since Mar 2 2026; town/landlord not found | YES — absolute MW + landlord still n/d |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | Q2'26 letter map; unseen_capacity.md §2; Aterio OK listing (blank MW) | 10 | 25 | 50 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | Re-search Oct 5: still no landlord, address, OCC/SPP docket, or absolute MW. Jobs confirm on-site colo (8 roles). Project Anthem Tulsa = Meta per press, not Nebius. Aterio Tulsa listing has blank power. Model YE27 base 100 = category floor (E). Searched: Q2 letter map, Greenhouse jobs, OKC/Tulsa lists, Core Scientific, CloudBurst, Aterio, Northwise.
France 2nd colo (unnamed; possibly eu-west2) | France | leased | Colocation (20-F) | B300 (HGX) (inference) | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Yellow | n/d | eu-west2 private region (R); physical site/landlord/MW n/d | n/d | stated/unknown | 1.3 | [12 empty] | see Company_Totals (no per-site connected series in v2) | eu-west2 (France, B300) live in docs - mapping is inference; MW n/d -> in plug | YES — MW, landlord, address still n/d |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | docs.nebius.com/overview/regions; unseen_capacity.md §2 | [10 empty] | eu-west2 France B300 private region (R, docs). Distinct from Equinix PA10 (first Paris colo). Re-search Oct 5: Eclairion, Data4, Telehouse, Digital Realty, Northwise — no Nebius second-site disclosure. Map <100 MW. Energized path remains blank. Searched: docs.nebius.com/regions, Q2 map, Paris jobs, colo operator news.
AIB CLT1 (Moore, Spartanburg County SC; Lockhart Power) | USA | leased | Colocation/lease (12-yr) | Vera Rubin NVL72 | unassigned | Unsold / self-serve or undisclosed customer (not disclosed) | Red | 50 | IT (50 MW critical IT on 65 MW utility ESA) | Reported | IT | 1.3 | 0 | 0 | 0 | 0 | 25 | 50 | 50 | 50 | 50 | 0 | 25 | 50 | see Company_Totals (no per-site connected series in v2) | Hall 1 ~Q3-Q4 2027; permits only submitted; project financing not arranged |  |  | Derived (from nebius_capacity.xlsx Quarterly MW base/low/high) | nebius_capacity.xlsx Sites + Quarterly MW + Basis + Capacity tranches; site_list.csv | 0 | 0 | 0 | 0 | 12.5 | 25 | 37.5 | 37.5 | 50 | 50 | 50 MW critical IT Reported (AIB 8-K); YE27 base 25 / YE28 50
SUM of site energized base (stated/mixed; not IT-normalized) | [13 empty] | 319.5 |  |  | 1212.5 |  |  | 1942.5 |  | 301.7 | 1081.9 | 1652.8 |  |  |  |  | Derived | Sum of By_Site YE energized base; compare to Company_Totals stated-basis row

## Company_Totals
Energized MW low — IT-normalized | IT | Derived | nebius_capacity.xlsx Quarterly MW R135 | 22.73 | 22.73 | 22.73 | 27.73 | 42.73 | 42.73 | 42.73 | 107.56 | 143.49 | 146.49 | 181.49 | 189.49 | 256.97 | 404.35 | 553.47 | 794.61 | 850.05 | 984.99 | 1009.99 | 1407.61
Energized MW base — IT-normalized | IT | Derived | nebius_capacity.xlsx Quarterly MW R136 | 22.73 | 22.73 | 22.73 | 27.73 | 47.73 | 47.73 | 59.09 | 138.33 | 170.99 | 182.49 | 216.99 | 301.72 | 453.79 | 629.54 | 812.61 | 1081.92 | 1173.01 | 1326.47 | 1338.97 | 1652.76
Energized MW high — IT-normalized | IT | Derived | nebius_capacity.xlsx Quarterly MW R137 | 22.73 | 22.73 | 22.73 | 27.73 | 52.73 | 52.73 | 75.45 | 169.09 | 198.49 | 218.49 | 252.49 | 413.95 | 650.62 | 854.73 | 1071.76 | 1369.24 | 1495.97 | 1667.95 | 1667.95 | 1897.9
Energized MW base — gross-normalized | gross | Derived | nebius_capacity.xlsx Quarterly MW R139 | 25 | 25 | 25 | 31.75 | 56.75 | 56.75 | 69.25 | 165.59 | 204.65 | 219.45 | 261.6 | 368.6 | 560.94 | 781.54 | 1015.5 | 1363.97 | 1480.22 | 1675.22 | 1691.47 | 2101.47
Energized MW base — stated/mixed (identified sites) | mixed | Derived | nebius_capacity.xlsx Quarterly MW R126 | 25 | 25 | 25 | 30 | 50 | 50 | 62.5 | 147.7 | 181.5 | 193 | 227.5 | 319.5 | 485.2 | 677.2 | 882 | 1212.5 | 1325 | 1520 | 1532.5 | 1942.5
Connected MW low (gross/shell, bottom-up) | gross/shell | Estimated | nebius_capacity.xlsx Quarterly MW R141 |  |  |  | 25 |  |  |  | 220 |  |  | 295 | 561 | 626.4 | 763.4 | 990 | 1249
Connected MW base (gross/shell, bottom-up) | gross/shell | Estimated | nebius_capacity.xlsx Quarterly MW R142 |  |  |  | 25 |  |  |  | 220 |  |  | 353 | 941 | 1078 | 1243 | 1382 | 1882
Connected MW high (gross/shell, bottom-up) | gross/shell | Estimated | nebius_capacity.xlsx Quarterly MW R143 |  |  |  | 25 |  |  |  | 220 |  |  | 412 | 1195 | 1322 | 1577 | 2017 | 2517
Mgmt connected guide YE26 | as stated | Reported | Q1'26/Q2'26 letters: 800–1,000 MW connected YE26 | [11 empty] | 800-1,000
Billing MW (IT) — capacity workbook base (1Q lag + Vineland billed tranches) | IT | Derived | nebius_capacity.xlsx Quarterly MW R147; YE26=257.7 ≈ locked ~258 | 0 | 22.73 | 22.73 | 22.73 | 27.73 | 47.73 | 47.73 | 85.76 | 165.46 | 186.82 | 250.16 | 257.66 | 326.59 | 495.29 | 701.04 | 852.61 | 1086.92 | 1178.01 | 1331.47 | 1343.97
LOCKED Base YE26 billing / FY27 avg (see Billing_Lock) | IT | Derived | vineland_watch.md §0c team lock | [11 empty] | 258
LOCKED High YE26 billing (see Billing_Lock) | IT | Derived | vineland_watch.md §0c team lock | [11 empty] | 284
YE SNAPSHOT (IT-normalized energized)
Year | IT low | IT base | IT high | Gross base | Connected base | Stated base | Billing workbook base | Tag
YE26 | 189.49 | 301.72 | 413.95 | 368.6 | 941 | 319.5 | 257.66 | Derived
YE27 | 794.61 | 1081.92 | 1369.24 | 1363.97 | 1882 | 1212.5 | 852.61 | Derived
YE28 | 1407.61 | 1652.76 | 1897.9 | 2101.47 |  | 1942.5 | 1343.97 | Derived
FY27 average billing — workbook raw Q1–Q4'27 mean of billing base row | 593.9 | Derived | Raw mean=593.9; LOCKED team FY27 avg is 475 (Billing_Lock) — use locked, not this raw mean

## Billing_Lock
Item | Value | Unit | Tag | Source | Notes
LOCKED Base YE26 billing MW | 258 | MW IT | Derived | vineland_watch.md §0c; Modeling+Skeptic lock Oct 5 AM ET | Matches capacity workbook Billing MW base YE26 = 257.7 (≈258). 1-quarter lag from energized + Vineland billed-tranche timing.
LOCKED High YE26 billing MW | 284 | MW IT | Derived | vineland_watch.md §0c team lock | Like-for-like high path with same 1Q-lag method. Do NOT use ~350 shortcut.
LOCKED Base FY27 average billing MW | 475 | MW IT | Derived | vineland_watch.md §0c team lock | FY27 average (not YE27 exit). Capacity workbook raw Q1–Q4'27 mean of billing row ≈594 — do NOT use that; use this locked 475.
LOCKED High FY27 average billing MW | 645 | MW IT | Derived | vineland_watch.md §0c team lock | Like-for-like high. Do NOT use ~710 shortcut. High-path gap to ~769 MW needed at $16M comps ≈19%.
DROPPED shortcut Base (do not use) | 350 | MW IT | n/a — dropped | earlier team shortcut | Simple YE energized averages × 80–85%. Superseded.
DROPPED shortcut High (do not use) | 710 | MW IT | n/a — dropped | earlier team shortcut | Superseded by locked ~284 / ~645.
Capacity workbook Billing YE26 (cross-check) | 257.66 | MW IT | Derived | nebius_capacity.xlsx Quarterly MW R147 | Should round to locked ~258.
Capacity workbook Billing YE27 exit (NOT the FY27 avg) | 852.61 | MW IT | Derived | nebius_capacity.xlsx Quarterly MW R147 | Exit ≠ average. Locked FY27 avg is 475, not this exit.
Capacity workbook Billing YE28 exit | 1343.97 | MW IT | Derived | nebius_capacity.xlsx Quarterly MW R147
Lag rule | 1 quarter |  | Estimated / team convention | nebius_capacity.xlsx billing row construction; vineland_watch.md | Billing MW ≈ prior-quarter energized IT for non-Vineland; Vineland uses tranche billing-start dates from Vineland tranche track.
Energized IT YE26 base (reference) | 301.72 | MW IT | Derived | nebius_capacity.xlsx IT-normalized base | Energized > billing at YE26 because of lag / Vineland billing timing.
Energized IT YE27 base (reference) | 1081.92 | MW IT | Derived | nebius_capacity.xlsx IT-normalized base
Energized IT YE28 base (reference) | 1652.76 | MW IT | Derived | nebius_capacity.xlsx IT-normalized base
Energized IT YE26 high (reference) | 413.95 | MW IT | Derived | nebius_capacity.xlsx IT-normalized high
Energized IT YE27 high (reference) | 1369.24 | MW IT | Derived | nebius_capacity.xlsx IT-normalized high
HOW TO USE FOR MODELING
For revenue builds, use LOCKED Base (~258 YE26 billing; ~475 FY27 avg billing) and LOCKED High (~284; ~645). These are the Oct 5 AM team lock (Modeling + Skeptic), Derived from nebius_capacity.xlsx v2 billing with a 1-quarter lag. Drop any ~350 / ~710 shortcuts. YE27 energized IT base (~1,082) is an exit stock, not a billing average — do not multiply YE27 exit × ACV for FY27 revenue. Vineland Bloom 2Q-slip scenario cuts FY27 Vineland billing materially (see vineland_watch.md / capacity Bloom-slip rows); not re-locked here.

## Sources
# | Source | What it feeds | Tag / notes
1 | /workspace/nebius/capacity/nebius_capacity.xlsx (v2) | All energized / connected / billing series; Sites; Basis; Capacity tranches | Primary model
2 | Tabs: Summary, Sites, Quarterly MW, Capacity tranches, Basis, Tags_Sources, Alt path | By_Site + Company_Totals inputs | Derived numbers tagged per Tags_Sources
3 | /workspace/nebius/capacity/site_list.csv + site_verification.md | Announced MW, ownership, GPU, customer cross-check | Reported where linked
4 | /workspace/nebius/capacity/uncontracted_split.csv | Contracted vs unsold / new-uncontracted flags | Estimated
5 | /workspace/nebius/capacity/vineland_watch.md (§0c, updated Oct 5 AM) | LOCKED billing ~258/284/475/645; Vineland risk | Derived team lock
6 | Q1'26 / Q2'26 shareholder letters; FY24/FY25 20-F; AIB 8-K Sep 30 2026 | Mgmt connected guide; lease notes; CLT1 50 MW IT | Reported
7 | This file stores STATIC copies of capacity workbook calculated values (openpyxl data_only). | If capacity model changes, rebuild this tracker. | No live workbook links