## Definitions
Term | Definition (one line for judges) | Tag | Source
connected | Power delivered into fully built and equipped DC halls (shell + fit-out ready; need not bill). NOT contracted land+power (~5 GW), NOT substation-only grid access, NOT active/billing IT. | R (defn) / E (941 site split) | Q1'26 letter; Q2'25 letter (active + fully provisioned); Q3'25 letter (power connected to built DCs); YE26 guide 800MW–1GW
active | Power consumed by installed operational IT. | R (defn) / D (site MW) | Q1'26 letter; nebius_capacity.xlsx
contracted (contrast) | Land plus power rights (~5 GW) — Filings language; NOT what "connected" means. | R | Filings / Q2 call framing
YE26 company connected | 941 MW base = Estimated reconstruction totaling inside mgmt 800MW–1GW guide; site splits Estimated. | E | unseen_capacity.md; ye26_active_vs_connected.md

## YE26 active vs connected
Site | Active/energized MW YE26 LOW | Active/energized MW YE26 BASE | Active/energized MW YE26 HIGH | Active IT-norm YE26 BASE (ref) | Connected/shell MW YE26 LOW | Connected/shell MW YE26 BASE | Connected/shell MW YE26 HIGH | Gap (conn base − active base) | Grade | Notes | Source | Number tags
Vineland NJ (DataOne) | 57 | 81.8 | 106.6 | 81.8 | 300 | 300 | 300 | 218.2 | Yellow/Red | Active = IT on gensets (T1–T4 ceiling ~107 IT). Connected = full shell gross 300 (mgmt: Vineland in 2026 connected power). T5–T9 wait on Bloom. Gap ~218. | nebius_capacity.xlsx; unseen_capacity.md §1; vineland_watch.md; Q2'26 call | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Independence MO (Eastgate) | 0 | 0 | 0 | 0 | 0 | 100 | 200 | 100 | Green | YE26 connected = utility feed / shell plug (~100 base; 0–200). Not revenue IT. Phase 1 IT ~Q3'27. | owned_campus_power_path.md; unseen_capacity.md §1 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Butler Twp PA (Highridge) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Red | Shell/earthworks only; permanent PPL feed late-27/2028. Not in YE26 connected plug. | owned_campus_power_path.md | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Birmingham AL (BHM01, Oxmoor) | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 50 | Yellow | YE26 connected = 115 kV feed + partial shell (0–100). Revenue IT 2027. | owned_campus_power_path.md; unseen_capacity.md §1 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Bethune FR (Azur) | 0 | 30 | 60 | 23.08 | 30 | 120 | 120 | 90 | Yellow | Mgmt 120 MW by YE26 (R, CCO); model energized base 30. Connected uses mgmt 120. | nebius_capacity.xlsx; unseen_capacity.md §1 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Lappeenranta FI (Pajarila) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Green | First building H1 2027. YE26 connected 0. | site_tracker_wed.xlsx | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Mantsala FI #1 | 75 | 75 | 75 | 68.18 | 75 | 75 | 75 | 0 | Green | 75 MW built early 2026 (R). Connected ≈ energized. | nebius_capacity.xlsx | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Mantsala FI #2 (Kapuli) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yellow | Capacity from 2027. YE26 connected 0. | site_tracker_wed.xlsx | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Kansas City MO (Patmos) | 5 | 20 | 35 | 20 | 20 | 40 | 40 | 20 | Green | Connected lifted to facility 40 MW (unseen 'KC to 40'). | unseen_capacity.md §1 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Paris (Equinix PA10) | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | Green | Operational; 5 MW = 3rd-party (low conf). | site_tracker_wed.xlsx | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Keflavik IS (Verne) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | Green | 10 MW live since Mar 2025 (R). | site_tracker_wed.xlsx | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
London Longcross (Ark LP01) | 16 | 17.5 | 19 | 13.46 | 16 | 19 | 19 | 1.5 | Green | Connected ≈ 19 contract. | site_tracker_wed.xlsx | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Harlow UK (Kao Data) | 0 | 2.2 | 4.4 | 2.2 | 2.2 | 22 | 22 | 19.8 | Green | 22 MW contract (R); connected at contract (E). | unseen_capacity.md §1 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Newport UK (Vantage CWL1) | 0 | 5 | 10 | 5 | 0 | 10 | 20 | 5 | Yellow | YE26 connected plug share ~10 of Newport+UK3 15 (E). | unseen_capacity.md §1–2 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
UK 3rd (lead: Green Mountain LON-East) | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 5 | Red | Lead only; YE26 connected plug share ~5 of 15 (E, low conf). | unseen_capacity.md §1–2 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Modi'in IL (Mega Or) | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | Green | 8 MW live Oct 2025 (R). | site_tracker_wed.xlsx | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Masmiyya IL (Mega DC) | 0 | 5.5 | 11 | 5.5 | 5.5 | 22 | 22 | 16.5 | Yellow | 22 MW contracted; connected at contract (E). | unseen_capacity.md §1 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Beit Shemesh IL (Mega DC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yellow | Landlord completion Q2'27; YE26 connected 0. | site_tracker_wed.xlsx | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Madrid-Getafe ES (Merlin) | 9 | 13.5 | 18 | 13.5 | 13.5 | 18 | 18 | 4.5 | Green | 18 MW contract; connected at contract (E). | unseen_capacity.md §1 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Tallinn EE (Greenergy Huuru) | 0 | 11 | 22 | 11 | 11 | 22 | 22 | 11 | Yellow | 22 MW first phase later 2026 (R); connected at 22 (E). | unseen_capacity.md §1 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Minnesota colo (Woodbury) | 5 | 10 | 15 | 10 | 15 | 15 | 15 | 5 | Yellow | Connected 15 (E; IronGate MSP01 inference). | unseen_capacity.md §1–2 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
Oklahoma colo (unnamed) | 10 | 25 | 40 | 25 | 50 | 100 | 150 | 75 | Yellow/Red | Map >100 MW (R). Connected 100 base / 50–150 (E). | unseen_capacity.md §1–2 | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
France 2nd colo (eu-west2 lead) | [8 empty] | Yellow | MW n/d — not invented. In company plug only. | unseen_capacity.md §2 | n/d
AIB CLT1 (Moore SC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Red | Halls ~2027; YE26 connected 0. | site_tracker_wed.xlsx; AIB 8-K | Active L/B/H: D (capacity/site_tracker); IT-norm: D; Connected: E (unseen bottom-up → 941)
TOTAL (excl. France 2nd n/d) | 200 | 319.5 | 439 |  | 561.2 | 941 | 1156 | 621.5 |  | Active stated/mixed ≈319.5 (D). Connected base ≈941 (E). Site connected high sum ~1156 vs company high 1195 — residual ~39 = France 2nd n/d + range. IT-norm YE26 company base ≈301.7 (D). | Company_Totals; Quarterly MW R126/R142; Billing_Lock | Active: D; Connected: E

## README
YE26 active vs connected MW by site — Nebius Capacity & Power (Point72)
Built: 2026-10-05 12:36 ET (Oct 5 2026 PM)
Public sources only. Tags: R=Reported, D=Derived, E=Estimated. No invented MW.
DEFINITIONS (Nebius Q1'26 letter, R): active≈energized IT; connected=power into fully built & equipped DCs.
LOCKED BILLING unchanged: YE26 ~258 base / ~284 high; FY27 avg ~475 / ~645.
Connected YE26 company ~941 (E) inside mgmt guide 800–1,000 (R).
ACTIVE: D from nebius_capacity.xlsx / site_tracker_wed.xlsx.
CONNECTED: E site attribution from unseen_capacity.md §1 + owned_campus_power_path.md summing to 941.
France 2nd MW n/d left blank. Site connected high sum ~1156 vs company 1195 (~39 residual).
Companion: ye26_active_vs_connected.md

## Company_lock
Item | Value | Tag | Source
YE26 active stated/mixed base | 319.5 | D | Quarterly MW R126
YE26 active IT-norm base / high | 301.72 / 413.95 | D | Company_Totals / Billing_Lock
YE26 connected L/B/H | 561 / 941 / 1195 | E | Quarterly MW R141–143
Mgmt connected guide YE26 | 800–1,000 | R | Q1/Q2'26 letters; Q2'26 call
LOCKED YE26 billing base / high | ~258 / ~284 | D | vineland_watch.md §0c
LOCKED FY27 avg billing base / high | ~475 / ~645 | D | vineland_watch.md §0c