## Sites
Peer | Site | MW basis | Announced MW | Contracted MW | Active low (MW) | Active base (MW) | Active high (MW) | Active basis (evidence) | YE26 low | YE26 base | YE26 high | H1'28 low | H1'28 base | H1'28 high | Energization-date evidence | Power / interconnection | Permits / filings / incentives | Imagery dates & observations | Thermal | Grade | Confidence | Key images
CoreWeave | Denton TX (Core Scientific campus, 8171 Jim Christal Rd) | IT (critical) MW | ~262 MW IT (394 MW grid) at full build | ~260 MW IT leased to CoreWeave (CORZ Q2-26 deck) | 250 | 260 | 262 | Landlord-reported billing: Bldgs D-G ~132 MW billing Mar-2026 (8-K Ex99.2 2026-04-21); ~260 MW leased & ~260 MW billing, "substantially complete" (Q2-26 deck 2026-07-28). Low = rounding haircut on "~260". | 260 | 262 | 262 | 260 | 262 | 262 | Pre-existing 297 MW grid load energized before 3/25/2022 (ERCOT "Base Load Pathway (a)", CORZ 8-K 2026-09-10); initial HPC billing H2-2025; +74 MW in ERCOT 2025 RTP still to energize | Denton Municipal Electric PPA (~394 MW potential); ERCOT: existing 297 MW conditionally approved Base Load Pathway (a) (energized pre-3/25/2022), outside Batch Zero; +74 MW validated in 2025 RTP, also outside Batch Zero (CORZ 8-K 2026-09-10). CORZ funds 2 new on-site substations; DME/ERCOT transmission upgrades by 2029 (City of Denton 2024-11-20) | City of Denton lease & PPA amendments approved 2024-11-19 (78.85 ac); no city tax incentives (state incentives applied for). TCEQ PBR Registration 179143 acknowledged 2025-02-11 under 30 TAC §106.511 (emergency/standby engines) for Core Scientific Data Center Site 1 And 2 Denton (RN111355798 / CN605945302; docs/denton_tceq_pbr_179143.pdf). No major NSR air permit found in this pass (grid-powered campus). T5 Construction GC | S2 2023-02-03..2026-09-15 (25 scenes). White-roof area in crop 6.8-9.8 ha (2023) -> 12.4 (Jul-25) -> 18.6-18.7 ha (Jun/Sep-26); new south pad from Oct-25 | Landsat: see Thermal tab (pre-existing mining load => cannot isolate AI conversion) | Green | High (landlord SEC filings; imagery consistent) | strips/denton_tx_strip.png; imagery/denton_tx/detail/denton_tx_2023-06-28_crop.png; imagery/denton_tx/detail/denton_tx_2026-09-15_crop.png
IREN | Childress TX (620 FM 1033) | IT MW for AI; grid MW for site | 750 MW grid site; Horizons 1-4 = 4 x 50 MW IT liquid-cooled (+H5-6 2027); 60 MW IT air-cooled for NVIDIA contract (from early 2027) | 200 MW IT Microsoft ($9.7B/5 yr) = Horizons 1-4; NVIDIA $3.4B within 60 MW of existing halls (ramp from early 2027) | 50 | 75 | 100 | Horizon 1 (50 MW IT) delivered/accepted by Microsoft 2026-08-13 (SEC Ex99.1); Horizon 2 commissioning underway (FY26 results 2026-08-27) => 50-100 MW IT AI. Legacy bitcoin load (650 MW "operating data centers" Aug-2025) separate and being wound down. | 100 | 150 | 200 | 100 | 150 | 200 | Site energized for mining since 2022-24 (Phases 1-5 = 650 MW, IREN Aug-2025 update); second bulk substation transformer energized for Horizon 1-2 (Aug-2025 update); grid raised 600->750 MW 2024-07-24 (AEP/ERCOT) | AEP/ERCOT 750 MW interconnection (amended connection agreement after ERCOT network studies; IREN PR 2024-07-24); IREN-owned on-site substations with dual feed; second bulk transformer energized for Horizon 1-2 (Aug-2025 update). Site already energized (mining Phases 1-5); not a Batch Zero new-interconnection story (contrast Sweetwater). Separate AEP Childress Area Transmission Improvement Project (ERCOT Tier 2, ~$77.3M, ISD Nov-2031) addresses county voltage/thermal reliability from load growth — regional upgrade, not the site's 750 MW interconnection itself (PUC 55999 Item 173 / docs/ercot_aep_childress_tier2_endorsement.pdf) | TCEQ Title V Operating Permit application #4951 (Ie US Development Holdings 3 Inc. — IREN SPV; Texas Comptroller DC list LD926028), Area Name Childress Data Center, received 2026-08-17, Administrative Complete (tceq.texas.gov Title V pending list, data updated 2026-10-05). Title V = operating consolidation, not a pending major NSR construction permit. No public NSR major / EGU standard-permit registration for on-site turbines found this pass (grid-connected campus). Childress County Chapter 312 tax abatements + Iris Reinvestment Zone for IE US Development Holdings 3 / IE US Hardware 1-4 (county notice Aug-2023; ~$1.4B improvements contemplated; amended/restated filings on childresstx.us/pages/tax-abatements). TDLR TABS2024024946 / TABS2026003980 confirm same SPV at 620 FM 1033. Search scope for air: TCEQ Title V pending list; public web/TCEQ records search for Childress Data Center / IE US / IREN PBR & standard permits — only Title V surfaced. | S2 2023-03-03..2026-09-28 (25 scenes). White-roof 0.5 ha (Mar-23) -> 10.8 (Feb-25) -> 17-18 (Jul/Aug-25) -> 19-25 ha (Mar-Jul-26); new west halls Oct-25..Mar-26; new grey facility SE + north halls by Sep-26 | Landsat: see Thermal tab (mining load dominates) | Green (H1-2) / Yellow (H3-4 by Q4-26) | High for 50 MW; Medium for 75-100 MW | strips/childress_tx_strip.png; imagery/childress_tx/detail/childress_tx_2024-07-30_crop.png; imagery/childress_tx/detail/childress_tx_2026-09-28_crop.png
Nscale | Kvandal (Narvik/Bjerkvik) NO - Stargate Norway | MW (grid allocation / IT not split) | 230 MW grid allocated (Statnett) + up to 290 MW more (paused); HENT KNB4-6 = 100 MW buildings | S-1: Norway owned sites 100 + 100 MW contracted (not active); Vattenfall PPA phase 1 2027-31 | 0 | 0 | 0 | Under construction: groundbreaking 2025-11-19 (NRK); HENT 2026-09-02 completion "during 2027"; Vattenfall PPA operations from 2027; imagery shows first shells only from Jun-2026. | 0 | 0 | 0 | 0 | 0 | 0 | None evidenced. Nordkraft/Statnett grid allocation 230 MW; Statnett paused new allocations in N. Norway Apr-2026 (phase 2 uncertain) | Statnett 230 MW allocated; Vattenfall PPA 2027-2031 | Kvandal North regulated to industry Apr-2024 (345.no); NVE notice 2026-09-29: construction started without required waste-heat analysis, deadline 2026-11-15 or coercive fines; Eksfin NOK 2.2B loan; Kvandal South DC Facility $725M + $65M VAT (S-1) | S2 2023-06-26..2026-10-03 (13 snow-free scenes). Graded pads, no buildings 2023-Oct-25; building shells on SW pad and NE pad from 2026-06-10; long halls by 2026-09-11 | Not run (pre-operational; high latitude/snow) | Yellow (2027 start; NVE/grid risks) | High that active = 0 | strips/kvandal_no_strip.png; imagery/kvandal_no/detail/kvandal_no_2025-10-04_crop.png; imagery/kvandal_no/detail/kvandal_no_2026-09-11_crop.png
Crusoe | Abilene TX (Lancium Clean Campus; Stargate - Oracle/OpenAI) | IT MW | 1.2 GW gross / 8 buildings (Crusoe JV PR 2025-05-21); ~824 MW IT implied (618 / 0.75, D; Epoch ~843 IT, P). Microsoft 900 MW (2 x 336 MW IT) adjacent campus 2027+ excluded | All 8 buildings leased to Oracle (for OpenAI); 600 MW expansion reportedly not proceeding (Mar-2026, secondary) | 421 | 618 | 618 | [D on R] Oracle FQ1 FY27 call (2026-09-10): 6 of 8 buildings, 618 MW and 75% of capacity delivered to the customer; 131k GPUs delivered there in the quarter. Delivered + accepted (R) read as active (D). IT vs gross basis unstated (read as IT, E). Low 421 = Epoch AI satellite model (Bldgs 1-4, ~2026-05-23; P). Billed ~618 (Oracle -> OpenAI; D); JV lease billing to Oracle n/d. History: Oct 5 view 200/421/421 (Oracle Apr-2026 "200MW is already operational"; Epoch 421). | 618 | 721 | 824 | 618 | 721 | 824 | 138 kV 200 MW substation (built May-2022, 3rd bay H2-2024; AEP interconnection / slack span to Abilene NW). 1 GW 345 kV greenfield substation (12.5 ac): first MPT energized 2025-12-19; all 5 MPTs by 2026-03-10 (3 temporary); permanent transformer swaps targeted by Oct-2026 (Mortenson). On-site generation: 10 gas turbines (~360.5 MW) under Std Permit 177263 + ~62 diesel gensets under minor PBR (Texas Tribune 2026-07-09) | ERCOT grid via Lancium 138 kV (200 MW) + 345 kV (1 GW) substations (Mortenson EPC; AEP interconnection). Behind-the-meter: Standard Permit Reg. 177263 — 5× Solar Titan 350 (38 MW) + 5× GE LM2500 (34.1 MW) = ~360.5 MW, 8,760 hrs/yr authorized, onsite use only, no grid export (TCEQ tech review Jan-2025; RN112029079 / CN606295137; docs/abilene_tceq_177263_tech_review.pdf). Crusoe has stated turbines are backup (Tribune) | Minor: Std Permit Reg. 177263 (originally 2024; mod approved ~2025-01-22) for 10 turbines; diesel backup gensets under PBR (reported Reg. 177262 / §106.511; Tribune: 62 units). Major pending: State AQ Permit 182126 + PSDTX1688 + GHGPSDTX263 (Crusoe Technologies / Crusoe Energy Systems; Longhorn Data Center RN112029061 @ 615 FM 2404); filed 2025-11-07; NORI 2025-11-19; NAPD + draft permit 2026-08-05 (docs/abilene_tceq_182126_*.pdf). Unit counts for expansion (41 turbines + 18 gensets) per Texas Tribune/Floodlight 2026-07-09 — NAPD does not enumerate units in the public notice. City of Abilene 85% / Taylor County 80% 10-yr abatements per building. Note: Gov. Abbott 2026 directive to halt new data-center TCEQ permits pending ERCOT/TWDB audits (update due 2026-10-19) is a process risk for the pending major, not for already-issued 177263. | S2 2023-01-22..2026-09-15 (25 scenes). Pre-construction Jul-23; N pair roofed + middle row pads Apr-25; 6 roofs Jul-25; chillers visible Oct-25; all 8 roofed Mar-26; new southern earthworks (Microsoft campus) Jun-Sep-26 | Landsat: see Thermal tab (daytime; bare red soil confounds) | Green (B1-6 delivered) / Yellow (B7-8 by YE26; expansion permit 182126 frozen) | Medium-High (618 MW company-stated delivered, R; active read D on R; IT vs gross basis unstated) | strips/abilene_tx_strip.png; imagery/abilene_tx/detail/abilene_tx_2025-04-10_crop.png; imagery/abilene_tx/detail/abilene_tx_2026-09-15_crop.png
Lambda | Kansas City MO (Project Blitz, 11155 N Airworld Dr) | IT MW | 24 MW early 2026; >100 MW potential (Lambda blog 2025-10-28) | Single customer (unnamed); >10,000 Blackwell Ultra GPUs | 0 | 12 | 24 | No public confirmation of operation. MO DNR letter 2026-04-15: commissioning from 2026-06-01 on 5 x 3 MW rental engines (prime, Jun-Oct) + up to 6 x 3 MW; Evergy full supply late summer 2026. Evergy (KSHB, Jun-2026): enough power "available today" to fully operate. Base = half of 24 MW. | 12 | 24 | 24 | 12 | 24 | 24 | Partial Evergy service expected Jun-2026, full late summer 2026 (MO DNR 2026-04-15); not confirmed | Evergy; temporary rental gensets (classed nonroad, no permit) | MO DNR de minimis construction permit 102025-010 issued 2025-10-29 (site ID 165-0051); MO DNR 2026-03-061 applicability letter 2026-04-15; Port KC bond application withdrawn Jun-2026; city building permits active (KC Star) | S2 2023-02-03..2026-10-02 (26 scenes). Existing ex-BofA building; white-roof 1.6-1.9 ha (2023-25) -> 2.1-2.5 ha (Apr-Oct-26): small rooftop/yard changes only (interior retrofit; 10 m too coarse) | Not run (crop ~5 x 4 Landsat TIRS pixels; meaningless) | Yellow (no go-live confirmation) | Low | strips/kcairworld_mo_strip.png; imagery/kcairworld_mo/detail/kcairworld_mo_2025-10-20_crop.png; imagery/kcairworld_mo/detail/kcairworld_mo_2026-10-02_crop.png
Oracle (OCI) | Port Washington WI (Vantage "Lighthouse"; Stargate) | IT MW (~902 MW IT of 1.3 GW electrical) | ~1.3 GW electrical / ~902 MW IT, 4 buildings, 672 ac, $15B (Ozaukee Press 2025-10-22) | Leased to Oracle for OpenAI (Stargate); handover from end-2027 | 0 | 0 | 0 | No grid power: ATC Ozaukee County interconnection (new Decker substation) construction Dec-2026..Dec-2027; PSC completeness revoked Aug-2026, refiled 2026-09-14/15; Aterio: partial power earliest Oct-2027, base Dec-2027. | 0 | 0 | 0 | 0 | 0 | 0 | None; earliest partial Oct-2027 (Aterio, third party) | We Energies VLC tariff / Oracle service agreement (PSC doc 593736); ATC $1.39-1.67B project (PSC doc 597276) | WDNR air construction permit 25-MIN-094 + operation permit 24618528A-F01 final 2026-06-12: up to 45 emergency diesel engines (15x1.5 + 18x1.75 + 12x2.75 MW = 87 MW backup); city TIF $458.6M | S2 2023-02-12..2026-09-11 (23 scenes). Farmland to Oct-25; mass earthworks Mar-26; large white roofs ~21.6 ha Jun-26 -> ~22.9 ha Sep-26 + dark roofs/foundations; 20-25% complete (Ozaukee Press 2026-09-23) | Landsat run as construction control (no load) - see Thermal tab | Yellow/Red (end-2027 handover vs grid timeline) | High that active = 0 | strips/portwash_wi_strip.png; imagery/portwash_wi/detail/portwash_wi_2025-10-04_crop.png; imagery/portwash_wi/detail/portwash_wi_2026-09-11_crop.png
Nscale | Monarch Compute Campus, Mason County WV (Point Pleasant) | IT MW | Phase 1: 2 GW gross / ~1.35-1.37 GW IT by H1'28 (S-1 / nscale.com); ~8 GW gross by 2031; $20B+ planned capex | 460 MW IT in S-1 facilities table (US Owned, Tier 3, Contracted). Anthropic GPU Services Agreements up to $44.6B (signed 2026-08-25; Vera Rubin NVL72; four tranches). Financing for Anthropic NOT committed as of S-1 date. Implied ACV ~$16.2M/IT MW-yr if 6-yr term (press). | 0 | 0 | 0 | Site prep / civil only as of 2026-09-25 Sentinel-2: ~85-100 ha bare ground, graded pads, no completed hall roofs (white-roof still ~2 ha = pre-existing hangars). Site manager (2026-09-20): still civil, about to go vertical. Active IT = 0. | 0 | 0 | 0 | 0 | 460 | 1370 | None. Off-grid gas microgrid (no AEP/FirstEnergy/PJM interconnection for primary load). Air permit app plans startup ~2027-01-01; S-1 targets H1'28 for 2 GW / 1.37 GW IT. Air construction permit R14-0042 still DRAFT as of 2026-09-29 (public comment into late Oct 2026). | Behind-the-meter: 864 x 2.5 MW natural-gas RICE = 2.16 GW nameplate (WVDEP R14-0042); peak site demand ~1.8 GW (permit app). Caterpillar partnership. 14-mile gas pipeline (Putnam/Mason; stormwater permit). Closed-loop cooling (no municipal drinking water). Not on public grid. | WVDEP air R14-0042 applied 2026-04-20, draft 2026-09-29 (not final). Stormwater enforcement order 2026-07-14. High Impact Data Center certification announced 2026-09-03 (Gov. Morrisey). $62.5M forgivable state loan to affiliate Mountaineer GigaSystem (press; $25M funded / $37.5M waived). Land: option on site at permit filing (app). | S2 2023-03-30..2026-09-25 (21 scenes). Pre-construction through Apr-2026 (airport runway intact). Bare-ha 5 -> 48 (May-28) -> 95-99 (Jun-Aug) -> 85 (Sep-25). White-roof flat ~1-2 ha. Graded pads / earthworks; no hall shells yet. | Landsat ST completed (construction control); Jun-Aug anomaly near 0 — not a power meter. thermal/monarch_wv_landsat_st.csv | Yellow (460 MW H1'28 path) / Yellow-Red (full 1.37 GW H1'28) | High that active=0; Medium that 460 MW contract is real; Low-Medium that 460 MW is on-track for H1'28 (financing + draft permit + early construction) | strips/monarch_wv_strip.png; imagery/monarch_wv/detail/monarch_wv_2026-04-08_crop.png; imagery/monarch_wv/detail/monarch_wv_2026-06-02_crop.png; imagery/monarch_wv/detail/monarch_wv_2026-09-25_crop.png
Notes: Active = evidence-supported energized and in service as of 2026-10-04 ET (Abilene updated 2026-10-08 to Oracle's Sep 10 statement: 618 MW delivered, D on R; IT vs gross basis unstated; Oct 5 view 200/421/421 is history). Low/Base/High follow Nebius site_verification.md convention. YE26 = estimate (see site_verification.md). Grades: Green = strong evidence; Yellow = partial/slippage; Red = contradictory/no evidence.

## Timeline
Site | Date | Evidence type | Observation | Source / image path | Confidence
Denton TX | 2023-06-28 | Imagery | Pre-conversion Core Scientific bitcoin campus: rows of mining sheds; white-roof in crop ~9.8 ha | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/denton_tx/detail/denton_tx_2023-06-28_crop.png | high
Denton TX | 2024-11-19 | Municipal | Denton City Council approves PPA + land-lease amendments (78.85 ac); CORZ pays interconnection incl. 2 new on-site substations; no city tax incentives; DME/ERCOT transmission fixes by 2029 | https://www.cityofdenton.com/CivicAlerts.aspx?AID=922 | high
Denton TX | 2025-02-26 | Company | CoreWeave +70 MW expansion -> critical IT just over 260 MW; CORZ funds ~$104M powered shell | https://www.businesswire.com/news/home/20250226866161/en/Core-Scientific-and-CoreWeave-Announce-%241.2-Billion-Expansion-at-Denton-TX-Site | high
Denton TX | 2025-07-22 | Imagery | New dark equipment yard E of campus and new building segments; white-roof ~12.4 ha | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/denton_tx/detail/denton_tx_2025-07-22_crop.png | medium
Denton TX | 2025-10-10 | Imagery | Large new L-shaped graded pad S of campus (expansion/laydown) | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/denton_tx/detail/denton_tx_2025-10-10_crop.png | medium
Denton TX | 2026-03 (as of) | Company (SEC) | Bldgs D-G (~132 MW) operational & billing (50% complete); 262 MW IT / 394 MW grid; 8 buildings A-H; 370,284 sf; PUE ~1.5; remainder H2-2026 | https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001193125-26-165121/d149019dex992.htm | high
Denton TX | 2026-06-07 | Imagery | New white roofs S/E; white-roof ~18.6 ha | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/denton_tx/detail/denton_tx_2026-06-07_crop.png | medium
Denton TX | 2026-07-28 | Company (SEC) | Denton ~260 MW leased, ~260 MW billing, "substantially complete" | https://www.sec.gov/Archives/edgar/data/1839341/000183934126000013/q2fy26earningsdeck728am.htm | high
Denton TX | 2026-09-10 | ERCOT | ERCOT conditionally approves existing 297 MW as Base Load Pathway (a) (energized pre-3/25/2022), outside Batch Zero; +74 MW to be energized in 2025 RTP | https://investors.corescientific.com/sec-filings/all-sec-filings/content/0001839341-26-000023/0001839341-26-000023.pdf | high
Denton TX | 2026-09-15 | Imagery | Campus fully roofed; white-roof ~18.7 ha (vs 9.8 ha 2023) | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/denton_tx/detail/denton_tx_2026-09-15_crop.png | medium
Childress TX | 2023-06-16 | Imagery | Early IREN site: substation yard + first mining building | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/childress_tx/detail/childress_tx_2023-06-16_crop.png | high
Childress TX | 2024-07-24 | Utility | Grid capacity raised 600 -> 750 MW (AEP/ERCOT amendments) | https://iren.com/data-centers/childress | high
Childress TX | 2023-08 / ongoing | Tax abatement | Childress County Chapter 312 tax abatements + Iris Reinvestment Zone for IE US Development Holdings 3 Inc. / IE US Hardware 1-4; ~$1.4B improvements contemplated (county notice Aug-2023); amended/restated agreements posted on county tax-abatements page | https://www.childresstx.us/pages/tax-abatements ; docs/childress_county_abatement_notice_2023-08.pdf | high
Childress TX | 2025-11-05/10 | Transmission (regional) | ERCOT endorses AEP Childress Area Transmission Improvement Project (Tier 2, ~$77.3M Option 1A, ISD Nov-2031) to fix Childress County voltage/thermal issues from load growth; CCN required — regional reliability, distinct from IREN site 750 MW interconnection | https://interchange.puc.texas.gov/Documents/55999_173_1556587.PDF ; docs/ercot_aep_childress_tier2_endorsement.pdf | high
Childress TX | 2026-08-17 | Air permit | TCEQ Title V Operating Permit app #4951 by Ie US Development Holdings 3 Inc. for Childress Data Center; Administrative Complete (TCEQ pending list updated 2026-10-05). No pending major NSR construction permit found this pass | https://www.tceq.texas.gov/assets/public/permitting/air/reports/applications/titlev-pending-permits.html | high
Childress TX | 2024-07-30 | Imagery | First large building block (mining halls); white-roof ~4.6 ha | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/childress_tx/detail/childress_tx_2024-07-30_crop.png | high
Childress TX | 2025-05-03 | Imagery | Second large block complete; white-roof ~13.2 ha | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/childress_tx/detail/childress_tx_2025-05-03_crop.png | high
Childress TX | 2025-08 | Company | 650 MW operating data centers (Phases 1-5 = 100+100+150+150+150); second bulk substation transformer energized for Horizon 1 & 2 (100 MW IT) | https://iren.gcs-web.com/static-files/ec8ec2a6-a1d1-4bb6-9cb9-bc2d436b9db9 | high
Childress TX | 2025-10-18 | Imagery | New halls under construction on W side of campus (likely Horizon liquid-cooled halls; attribution unconfirmed) | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/childress_tx/detail/childress_tx_2025-10-18_crop.png | low
Childress TX | 2026-03-12 | Imagery | W halls roofed; new pads N of campus | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/childress_tx/detail/childress_tx_2026-03-12_crop.png | medium
Childress TX | 2026-05-07 | Company | Q3 FY26: $3.4B NVIDIA contract, air-cooled Blackwell within 60 MW of existing Childress halls, ramp from early 2027; mining being decommissioned | IREN Q3 FY26 results (2026-05-07) | high
Childress TX | 2026-08-13 | Company (SEC) | Horizon 1 (50 MW IT, D2C liquid, GB300 NVL72) delivered and accepted by Microsoft | https://www.sec.gov/Archives/edgar/data/1878848/000114036126032638/ef20080141_ex99-1.htm | high
Childress TX | 2026-08-27 | Company (SEC) | FY26: Horizon 2 commissioning; Horizons 3-4 late-stage construction targeting Q4 2026; MSFT 200 MW IT $9.7B | https://www.sec.gov/Archives/edgar/data/1878848/000187884826000051/irenreportsfy26results.htm | high
Childress TX | 2026-09-28 | Imagery | New grey-roofed facility SE of campus and new halls N; white-roof 14.8 ha (scene haze; Jul ~19.7) | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/childress_tx/detail/childress_tx_2026-09-28_crop.png | medium
Kvandal NO | 2024-04 | Municipal | Kvandal North regulated to industrial use; Nordkraft transformer station nearby | https://www.345.no/2024/04/ett-steg-naermere-datasenter-i-narvik-kommune/ | high
Kvandal NO | 2025-10-04 | Imagery | Graded industrial pads, no buildings | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/kvandal_no/detail/kvandal_no_2025-10-04_crop.png | high
Kvandal NO | 2025-11-19 | Company/Press | Groundbreaking (foundation stone) for data centre at Kvandal | https://www.nrk.no/nordland/legger-ned-grunnstein-for-datasenter-pa-kvandal-1.17658846 | high
Kvandal NO | 2026-04/05 | Grid | 230 MW allocated by Statnett; Statnett paused new allocations in N. Norway -> phase 2 (+290 MW) uncertain; phase 1 32,000 m2, ~NOK 8B, full operation in about a year | https://www.nrk.no/nordland/nscale-sar-tvil-om-videre-satsing-pa-gigant-datasenter-i-narvik-1.17893773 | high
Kvandal NO | 2026 | PPA | Vattenfall PPA for phase 1, 2027-2031; operations start 2027 | https://group.vattenfall.com/press-and-media/pressreleases/2026/vattenfall-and-nscale-partner-to-support-ai-infrastructure-growth-in-norway/ | high
Kvandal NO | 2026-06-10 | Imagery | First building shells on SW pad + building on NE pad | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/kvandal_no/detail/kvandal_no_2026-06-10_crop.png | medium
Kvandal NO | 2026-07 | Financing (SEC S-1) | Kvandal South DC Facility: $725M term loan + $65M VAT facility; matures 6 yrs after construction completion | /workspace/nebius/comps_raw/nscale_s1.htm.txt (Nscale S-1) | high
Kvandal NO | 2026-09-02 | Contractor | HENT signs 2 more buildings (75 MW); HENT total KNB4-6 = 100 MW; completion during 2027 | https://www.hent.no/2026/09/02/hent-har-signert-kontrakt-for-utbygging-av-datasenteret-til-nscale-i-narvik-regionen/ | high
Kvandal NO | 2026-09-11 | Imagery | Long hall shells on SW pad; no cooling yards resolvable | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/kvandal_no/detail/kvandal_no_2026-09-11_crop.png | medium
Kvandal NO | 2026-09-29 | Regulator | NVE: construction started without required waste-heat analysis; deadline 2026-11-15 or coercive fines | https://www.nrk.no/nordland/nscale-varsles-om-tvangsmulkt-1.18039577 | high
Abilene TX | 2022-05..2024 H2 | Substation | 138 kV 200 MW substation built from May 2022; 3rd bay added H2-2024 | https://www.mortenson.com/projects/abilene-data-center-development | high
Abilene TX | 2023-07-18 | Imagery | Pre-construction (substation pad only) | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/abilene_tx/detail/abilene_tx_2023-07-18_crop.png | high
Abilene TX | 2024-08 / 2025-01-22 | Air permit (minor) | TCEQ Standard Permit Reg. 177263 (Abilene DC 1 LLC dba Crusoe; RN112029079): 5× Titan 350 (38 MW) + 5× GE LM2500 (34.1 MW) = ~360.5 MW, 8760 hrs/yr, onsite only. Orig. registered ~2024-08; mod tech-review approved Jan-2025. Diesel backup gensets under separate PBR (Tribune: 62 units) | docs/abilene_tceq_177263_tech_review.pdf ; https://www.texastribune.org/2026/07/09/texas-data-centers-ai-power-plants-pollution-state-permits/ | high
Abilene TX | 2025-11-07 | Air permit (major pending) | Crusoe files State AQ Permit 182126 + PSDTX1688 + GHGPSDTX263 for Longhorn Data Center additional generation (615 FM 2404; RN112029061). NORI 2025-11-19; NAPD + draft permit 2026-08-05. Expansion unit counts (41 turbines + 18 gensets) per Tribune/Floodlight — not enumerated in NAPD text | docs/abilene_tceq_182126_napd.pdf ; docs/abilene_tceq_182126_nori.pdf ; docs/abilene_tceq_182126_pls.pdf | high
Abilene TX | 2024-06 | Company | Construction began June 2024; first two buildings energized within a year | https://www.crusoe.ai/resources/newsroom/crusoe-announces-flagship-abilene-data-center-is-live | high
Abilene TX | 2025 (Apr) | Tax abatement | City of Abilene 85% / Taylor County 80% 10-yr abatements; separate agreement per building, starting as each completes | https://developabilene.com/2025/05/01/project-radiance-powering-the-future-of-ai-in-abilene-texas/ ; https://finance.yahoo.com/news/taylor-county-estimated-see-18-222915156.html | medium
Abilene TX | 2025-04-10 | Imagery | North pair (Bldgs 1-2) roofed; middle row pads and partial roofs | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/abilene_tx/detail/abilene_tx_2025-04-10_crop.png | high
Abilene TX | 2025-06 | Company | Oracle began delivering first GB200 racks June 2025 | https://www.crusoe.ai/resources/newsroom/crusoe-announces-flagship-abilene-data-center-is-live | high
Abilene TX | 2025-07-30 | Imagery | Six buildings roofed (N pair + middle row of 4); W pair under construction | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/abilene_tx/detail/abilene_tx_2025-07-30_crop.png | high
Abilene TX | 2025-09-30 | Company | Crusoe: first phase "live" on OCI | https://www.crusoe.ai/resources/newsroom/crusoe-announces-flagship-abilene-data-center-is-live | high
Abilene TX | 2025-10-03 | Imagery | Chiller/equipment rows (blue) visible on W buildings | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/abilene_tx/detail/abilene_tx_2025-10-03_crop.png | medium
Abilene TX | 2025-12-19 | Substation | 1 GW 345 kV substation: first transformer energized; all 5 MPTs energized by 2026-03-10 (3 temporary; permanent swaps by Oct-2026) | https://www.mortenson.com/projects/abilene-data-center-development | high
Abilene TX | 2025-12-24 | 3rd-party satellite | Epoch AI: Building 2 fully operational -> 211 MW IT (TDLR filing date) | https://epoch.ai/data/ai-data-centers/directory/openai-stargate-abilene | medium
Abilene TX | 2026-03-26 | Imagery | All 8 buildings roofed | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/abilene_tx/detail/abilene_tx_2026-03-26_crop.png | high
Abilene TX | 2026-03 (late) | Thermal (3rd party) | Thermal image shows an on-site gas turbine operating | https://www.texastribune.org/2026/07/09/texas-data-centers-ai-power-plants-pollution-state-permits/ | high
Abilene TX | 2026-04-22 | Company | Oracle post: "In Abilene, 200MW is already operational" | https://epoch.ai/data/ai-data-centers/directory/openai-stargate-abilene (quotes Oracle) | high
Abilene TX | 2026-05-23 | 3rd-party satellite | Epoch AI estimate: Bldgs 3-4 operational -> 421 MW IT; 320 Airedale chillers | https://epoch.ai/data/ai-data-centers/directory/openai-stargate-abilene | medium
Abilene TX | 2026-07-28 | 3rd-party satellite | Epoch AI: Bldgs 5-8 structurally complete, not confirmed operational; projected 843 MW IT ~2026-11-01 | https://epoch.ai/data/ai-data-centers/directory/openai-stargate-abilene | medium
Abilene TX | 2026-09-10 | Company | Oracle FQ1 FY27 call: 6 of 8 buildings, 618 MW, 75% of capacity delivered to the customer; 131k GPUs delivered in the quarter (IT vs gross basis unstated). Replaces 421 MW (Epoch) as the active base | https://www.fool.com/earnings/call-transcripts/2026/09/11/oracle-orcl-q1-2027-earnings-call-transcript/ | high
Abilene TX | 2026-09-15 | Imagery | Campus complete externally; major new earthworks/structures to S (Microsoft 900 MW campus) | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/abilene_tx/detail/abilene_tx_2026-09-15_crop.png | high
Kansas City MO (Lambda) | 2025-10-28 | Company | Lambda: 24 MW early 2026, >100 MW potential, >10k Blackwell Ultra, single customer | https://lambda.ai/blog/lambda-to-build-a-100mw-ai-factory-in-kansas-city-mo | high
Kansas City MO (Lambda) | 2025-10-29 | Air permit | MO DNR de minimis construction permit 102025-010 (Airworld Data Center) | https://dnr.mo.gov/air/business-industry/air-permits/airworld-data-center-kansas-city-102025-010 | high
Kansas City MO (Lambda) | 2026-04-15 | Regulator | MO DNR: Russell close to turnover; commissioning from 2026-06-01; Evergy partial power Jun 1, full late summer 2026; 5 x 3 MW rental prime engines Jun-Oct + up to 6 x 3 MW (nonroad, no permit) | https://dnr.mo.gov/sites/dnr/files/vfc/2026/04/main/airworld-blitz-data-center-kansas-city-2026-03-061.pdf | high
Kansas City MO (Lambda) | 2026-06 | Incentive | Port KC bond application withdrawn; Evergy: site has enough power available today to fully operate; Lambda no comment | https://www.kshb.com/news/local-news/data-centers/northland-ai-data-center-withdraws-bond-application-with-port-kc | high
Kansas City MO (Lambda) | 2023-2026 | Imagery | Existing building; only minor rooftop/yard brightening Apr-Oct 2026 (white-roof 1.6-1.9 -> 2.1-2.5 ha); retrofit not resolvable at 10 m | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/kcairworld_mo/detail/kcairworld_mo_2026-10-02_crop.png | medium
Kansas City MO (Lambda) | 2026-10-04 | Gap | No public confirmation found that Blitz is operational / billing | searches 2026-10-04 (Lambda blog, DCD, KC Star, KSHB) | medium
Port Washington WI | 2025-10-04 | Imagery | Farmland (pre-construction) | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/portwash_wi/detail/portwash_wi_2025-10-04_crop.png | high
Port Washington WI | 2025-10-22 | Press | 1.3 GW electrical / ~902 MW IT, 4 buildings, 672 ac, $15B, complete 2028; TIF $458.6M | https://www.ozaukeepress.com/content/openai-oracle-run-stargate-port-data-center | high
Port Washington WI | 2026-03-27 | Imagery | Mass earthworks across campus | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/portwash_wi/detail/portwash_wi_2026-03-27_crop.png | high
Port Washington WI | 2026-06-12 | Air permit | WDNR final 25-MIN-094 / 24618528A-F01: up to 45 emergency diesel engines (87 MW total) | https://www.wpr.org/wp-content/uploads/2026/07/dnr.state_.wi_.us_Apps_AM_WARP_Documents_PROD_Final_63297.pdf ; docs/wi_dnr_vantage_25-MIN-094_final.pdf | high
Port Washington WI | 2026-06-23 | Imagery | Large white building roofs; white-roof ~21.6 ha | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/portwash_wi/detail/portwash_wi_2026-06-23_crop.png | high
Port Washington WI | 2026-08/09 | Utility | PSC revoked completeness of ATC Ozaukee County interconnection (Aug); ATC refiled 2026-09-14/15; project $1.39-1.67B, construction Dec-2026..Dec-2027, new Decker substation | https://wisconsinwatch.org/2026/09/wisconsin-port-washington-data-center-atc-restarts-push-grid-upgrades-transmission-utility/ ; https://apps.psc.wi.gov/ERF/ERFview/viewdoc.aspx?docid=597276 | high
Port Washington WI | 2026-09-11 | Imagery | More roofs closed, dark roofing; white-roof ~22.9 ha | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/portwash_wi/detail/portwash_wi_2026-09-11_crop.png | high
Port Washington WI | 2026-09-23 | Press | 20-25% complete; 2,800-3,000 workers; first building topped May 12; handover to Oracle/OpenAI from end-2027 | https://www.ozaukeepress.com/content/data-center-size-%E2%80%98-insane%E2%80%99 | high
Port Washington WI | 2026-10-01 | 3rd party | Aterio: 2 of 4 halls enclosed; partial power earliest Oct-2027, base Dec-2027, extended Jun-2028 | https://constructionreviewonline.com/project-lighthouse-delays-threaten-oracles-2027-wisconsin-data-center-launch/ | medium
Monarch WV | 2026-03-31 | Acquisition (SEC) | Nscale acquires AIPCorp / Monarch Compute Campus, Mason County WV: ~2,250 ac; initial 2 GW gross (1.37 GW IT) expected online H1 2028; ~8 GW gross planned 2031. Consideration ~$793M (cash + Series C shares) | Nscale S-1 (/workspace/nebius/comps_raw/nscale_s1.htm.txt); private_peers N25 | high
Monarch WV | 2026-04-08 | Imagery | Pre/early construction: Mason County Airport runway and hangars intact; forest/fields; white-roof ~1.3 ha | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/monarch_wv/detail/monarch_wv_2026-04-08_crop.png | high
Monarch WV | 2026-04-20 | Air permit | Monarch Cloud Campus LLC files WVDEP major-source construction permit R14-0042: 2.16 GW off-grid gas RICE (864 x 2.5 MW) + auxiliaries; 3 H-shaped halls / 12 power nodes; peak demand ~1.8 GW; site option (not deeded); planned startup ~2027-01-01 | docs/monarch_r14_application.pdf ; https://ukozvhzgrcnkcatjqfoo.supabase.co/storage/v1/object/public/03-00-air-construction/2026.04.20_Monarch_Compute_Campus_Power_Plant_R14-0042_Application_c514f1ef | high
Monarch WV | 2026-05-28 | Imagery | Mass grading begins: bare ground in crop jumps to ~48 ha (from ~5 ha Apr) | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/monarch_wv/detail/monarch_wv_2026-05-28_crop.png | high
Monarch WV | 2026-06-02 | Imagery | Campus-scale earthworks ~95 ha bare; graded pads west of runway; no hall roofs | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/monarch_wv/detail/monarch_wv_2026-06-02_crop.png | high
Monarch WV | 2026-06 | Utility (gas) | 14-mile natural-gas pipeline proposed through Putnam and Mason counties to fuel the microgrid (WVDEP stormwater/general permit process) | https://www.wsaz.com/2026/06/16/pipeline-project-proposed-power-mason-county-data-center/ | high
Monarch WV | 2026-07-14 | Regulatory | WVDEP unilateral enforcement order: stormwater/mud left site into neighboring properties; stop land-disturbing work in one drainage area lacking controls | https://www.wvnews.com/news/wvnews/public-hearings-set-for-monarch-cloud-campus-air-permit-in-mason-county/article_e2d06911-0746-4a33-a9ba-aaa8e1bf01c0.html | high
Monarch WV | 2026-08-25 | Contract (SEC) | Anthropic GPU Services Agreements (four tranches) for dedicated Vera Rubin NVL72 infrastructure at Monarch; aggregate payments up to ~$44.6B. Best-efforts financing covenant; as of S-1 date, no binding financing commitments | Nscale S-1; https://www.datacenterfrontier.com/machine-learning/news/55407627/anthropic-openai-keep-expanding-the-ai-data-center-map-and-the-financing-gets-harder | high
Monarch WV | 2026-08-31 | Contracted MW (SEC) | S-1 facilities table lists United States Owned 460 MW Tier 3 Contracted (Monarch Anthropic slice). Full Phase 1 1.37 GW IT is announced, not all contracted — do not add 1.37 GW into the 1.37 GW company-wide active+contracted total | Nscale S-1 facilities table; private_peers N22/N25 note | high
Monarch WV | 2026-09-03 | Incentive | Gov. Morrisey announces WV High Impact Data Center certification for Monarch; claims total client investment $69.2B (Anthropic + undisclosed $24.2B — MW for the add-on not disclosed) | https://wvpublic.org/story/energy-environment/second-certified-data-center-announced-for-mason-county/ | medium
Monarch WV | 2026-09-20 | Construction (press) | Site manager: civil work continuing, about to go vertical; ~900 workers on site + pipeline | https://wvmetronews.com/2026/09/20/monarch-compute-campus-to-go-vertical-soon/ | high
Monarch WV | 2026-09-25 | Imagery | Still grading/pads; bare ~85 ha; white-roof ~2.0 ha (hangars); no completed DC halls | Sentinel-2 L2A (Element84 Earth Search STAC); imagery/monarch_wv/detail/monarch_wv_2026-09-25_crop.png | high
Monarch WV | 2026-09-29 | Air permit | WVDEP issues DRAFT R14-0042 (not final). Address: 30 Monarch Way, Ohio River Rd (WV-62) & Airport Rd; Lat/Lon 38.914258/-82.100935. Public hearings/comments into late Oct 2026 | docs/monarch_r14_draft_permit.pdf ; https://www.publicnow.com/view/0138C564AC6E5357F14FFC0F7637030F6CAC29FB | high
Monarch WV | n/a | Interconnection | No utility/ISO queue: campus is designed as a state-certified AI microgrid, fully behind-the-meter / off public grid (Nscale site; Caterpillar generation). Primary power risk is gas supply + air permit + engine delivery, not PJM | https://www.nscale.com/ai-infrastructure/monarch | high
Denton TX | 2023-2026 | Thermal (Landsat) | Daytime ST campus-minus-3km-background, Jun-Aug mean: 2023 -1.56C (n=5); 2024 -1.34C (n=4); 2025 -0.66C (n=5); 2026 -0.76C (n=5). 100 m TIRS, ~10:30 overpass; albedo/bare soil confound; not a power meter | thermal/denton_tx_landsat_st.csv (Planetary Computer landsat-c2-l2) | low
Childress TX | 2023-2026 | Thermal (Landsat) | Daytime ST campus-minus-3km-background, Jun-Aug mean: 2023 -0.43C (n=7); 2024 -1.84C (n=6); 2025 -0.65C (n=7); 2026 -1.97C (n=4). 100 m TIRS, ~10:30 overpass; albedo/bare soil confound; not a power meter | thermal/childress_tx_landsat_st.csv (Planetary Computer landsat-c2-l2) | low
Abilene TX | 2023-2026 | Thermal (Landsat) | Daytime ST campus-minus-3km-background, Jun-Aug mean: 2025 +0.40C (n=13); 2026 -0.41C (n=13). 100 m TIRS, ~10:30 overpass; albedo/bare soil confound; not a power meter | thermal/abilene_tx_landsat_st.csv (Planetary Computer landsat-c2-l2) | low
Port Washington WI | 2023-2026 | Thermal (Landsat) | Daytime ST campus-minus-3km-background, Jun-Aug mean: 2023 +0.59C (n=6); 2024 +0.91C (n=2); 2025 -0.23C (n=4); 2026 -0.50C (n=2). 100 m TIRS, ~10:30 overpass; albedo/bare soil confound; not a power meter | thermal/portwash_wi_landsat_st.csv (Planetary Computer landsat-c2-l2) | low
Monarch WV | 2023-2026 | Thermal (Landsat) | Daytime ST campus-minus-3km-background, Jun-Aug mean: 2023 +0.21C (n=4); 2024 -0.39C (n=5); 2025 +0.12C (n=2); 2026 +1.28C (n=1). 100 m TIRS, ~10:30 overpass; albedo/bare soil confound; not a power meter | thermal/monarch_wv_landsat_st.csv (Planetary Computer landsat-c2-l2) | low

## Imagery_metrics
site | date | scene | crop_ha | roof_white_ha | roof_grey_ha | bare_ha | ndvi_mean | png
denton_tx | 2023-02-03 | S2B_14SPB_20230203_0_L2A | 141.8 | 6.77 | 1.94 | 12.09 | 0.346 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2023-02-03_crop.png
denton_tx | 2023-06-28 | S2A_14SPB_20230628_0_L2A | 141.8 | 9.84 | 0.0 | 19.13 | 0.359 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2023-06-28_crop.png
denton_tx | 2023-09-01 | S2B_14SPB_20230901_0_L2A | 141.8 | 9.04 | 0.0 | 40.83 | 0.283 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2023-09-01_crop.png
denton_tx | 2023-10-06 | S2A_14SPB_20231006_0_L2A | 141.8 | 10.13 | 0.1 | 13.87 | 0.369 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2023-10-06_crop.png
denton_tx | 2024-03-19 | S2B_14SPB_20240319_0_L2A | 141.8 | 11.21 | 0.13 | 8.28 | 0.559 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2024-03-19_crop.png
denton_tx | 2024-04-03 | S2A_14SPB_20240403_0_L2A | 141.8 | 9.61 | 0.01 | 10.83 | 0.601 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2024-04-03_crop.png
denton_tx | 2024-09-10 | S2A_14SPB_20240910_0_L2A | 141.8 | 9.94 | 0.01 | 12.23 | 0.449 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2024-09-10_crop.png
denton_tx | 2024-10-20 | S2A_14SPB_20241020_0_L2A | 141.8 | 8.53 | 0.04 | 14.8 | 0.351 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2024-10-20_crop.png
denton_tx | 2025-01-03 | S2B_14SPB_20250103_0_L2A | 141.8 | 9.43 | 0.62 | 14.35 | 0.407 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2025-01-03_crop.png
denton_tx | 2025-04-08 | S2C_14SPB_20250408_0_L2A | 141.8 | 8.82 | 0.17 | 18.82 | 0.533 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2025-04-08_crop.png
denton_tx | 2025-07-22 | S2B_14SPB_20250722_0_L2A | 141.8 | 12.43 | 0.94 | 28.31 | 0.426 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2025-07-22_crop.png
denton_tx | 2025-08-08 | S2A_14SPB_20250808_1_L2A | 141.8 | 8.61 | 0.29 | 34.57 | 0.374 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2025-08-08_crop.png
denton_tx | 2025-09-10 | S2B_14SPB_20250910_0_L2A | 141.8 | 10.1 | 0.71 | 42.73 | 0.367 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2025-09-10_crop.png
denton_tx | 2025-10-10 | S2B_14SPB_20251010_0_L2A | 141.8 | 11.24 | 0.29 | 45.14 | 0.367 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2025-10-10_crop.png
denton_tx | 2025-11-09 | S2B_14SPB_20251109_0_L2A | 141.8 | 9.4 | 0.35 | 47.61 | 0.322 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2025-11-09_crop.png
denton_tx | 2025-12-09 | S2B_14SPB_20251209_0_L2A | 141.8 | 11.19 | 0.6 | 43.7 | 0.279 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2025-12-09_crop.png
denton_tx | 2026-01-03 | S2C_14SPB_20260103_0_L2A | 141.8 | 9.54 | 0.24 | 51.99 | 0.245 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2026-01-03_crop.png
denton_tx | 2026-02-27 | S2B_14SPB_20260227_0_L2A | 141.8 | 11.87 | 0.16 | 51.51 | 0.253 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2026-02-27_crop.png
denton_tx | 2026-03-19 | S2B_14SPB_20260319_1_L2A | 141.8 | 12.69 | 0.16 | 47.37 | 0.299 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2026-03-19_crop.png
denton_tx | 2026-04-08 | S2B_14SPB_20260408_0_L2A | 141.8 | 13.49 | 0.02 | 44.2 | 0.398 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2026-04-08_crop.png
denton_tx | 2026-05-03 | S2C_14SPB_20260503_0_L2A | 141.8 | 12.43 | 0.0 | 43.34 | 0.442 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2026-05-03_crop.png
denton_tx | 2026-06-07 | S2B_14SPB_20260607_1_L2A | 141.8 | 18.63 | 0.53 | 33.66 | 0.386 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2026-06-07_crop.png
denton_tx | 2026-07-22 | S2C_14SPB_20260722_0_L2A | 141.8 | 14.93 | 0.0 | 41.86 | 0.325 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2026-07-22_crop.png
denton_tx | 2026-08-16 | S2B_14SPB_20260816_0_L2A | 141.8 | 17.33 | 0.0 | 39.98 | 0.279 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2026-08-16_crop.png
denton_tx | 2026-09-15 | S2B_14SPB_20260915_0_L2A | 141.8 | 18.73 | 0.01 | 44.19 | 0.249 | /workspace/nebius/peers/sites/imagery/denton_tx/detail/denton_tx_2026-09-15_crop.png
childress_tx | 2023-03-03 | S2A_14SMD_20230303_0_L2A | 220.6 | 0.52 | 0.0 | 76.49 | 0.194 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2023-03-03_crop.png
childress_tx | 2023-06-16 | S2B_14SLD_20230616_0_L2A | 220.6 | 2.57 | 0.0 | 31.05 | 0.403 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2023-06-16_crop.png
childress_tx | 2023-09-09 | S2A_14SMD_20230909_0_L2A | 220.6 | 0.99 | 0.02 | 111.94 | 0.205 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2023-09-09_crop.png
childress_tx | 2023-10-19 | S2A_14SMD_20231019_0_L2A | 220.6 | 1.52 | 0.25 | 69.53 | 0.193 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2023-10-19_crop.png
childress_tx | 2024-01-17 | S2A_14SLD_20240117_0_L2A | 220.6 | 1.27 | 0.42 | 34.61 | 0.198 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2024-01-17_crop.png
childress_tx | 2024-04-11 | S2B_14SMD_20240411_0_L2A | 220.6 | 2.54 | 0.75 | 18.59 | 0.356 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2024-04-11_crop.png
childress_tx | 2024-07-30 | S2B_14SLD_20240730_0_L2A | 220.6 | 4.64 | 0.0 | 74.44 | 0.228 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2024-07-30_crop.png
childress_tx | 2024-12-02 | S2A_14SLD_20241202_0_L2A | 220.6 | 4.71 | 0.19 | 63.85 | 0.224 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2024-12-02_crop.png
childress_tx | 2025-02-25 | S2B_14SLD_20250225_0_L2A | 220.6 | 10.75 | 0.03 | 80.08 | 0.178 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2025-02-25_crop.png
childress_tx | 2025-05-03 | S2A_14SLD_20250503_0_L2A | 220.6 | 13.17 | 0.3 | 61.58 | 0.338 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2025-05-03_crop.png
childress_tx | 2025-07-30 | S2C_14SMD_20250730_0_L2A | 220.6 | 17.02 | 0.0 | 77.22 | 0.251 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2025-07-30_crop.png
childress_tx | 2025-08-14 | S2B_14SLD_20250814_0_L2A | 220.6 | 18.15 | 0.0 | 73.51 | 0.271 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2025-08-14_crop.png
childress_tx | 2025-09-03 | S2B_14SLD_20250903_0_L2A | 220.6 | 15.92 | 0.12 | 63.86 | 0.305 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2025-09-03_crop.png
childress_tx | 2025-10-18 | S2C_14SLD_20251018_0_L2A | 220.6 | 15.83 | 0.24 | 66.42 | 0.227 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2025-10-18_crop.png
childress_tx | 2025-11-17 | S2C_14SLD_20251117_0_L2A | 220.6 | 14.44 | 0.03 | 93.87 | 0.169 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2025-11-17_crop.png
childress_tx | 2025-12-22 | S2B_14SMD_20251222_0_L2A | 220.6 | 17.23 | 0.53 | 87.27 | 0.144 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2025-12-22_crop.png
childress_tx | 2026-01-11 | S2B_14SMD_20260111_0_L2A | 220.6 | 16.03 | 1.57 | 80.92 | 0.149 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2026-01-11_crop.png
childress_tx | 2026-02-20 | S2A_14SLD_20260220_0_L2A | 220.6 | 13.12 | 0.81 | 108.49 | 0.139 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2026-02-20_crop.png
childress_tx | 2026-03-12 | S2B_14SMD_20260312_0_L2A | 220.6 | 19.05 | 0.24 | 135.16 | 0.136 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2026-03-12_crop.png
childress_tx | 2026-04-06 | S2C_14SMD_20260406_0_L2A | 220.6 | 19.43 | 0.42 | 127.32 | 0.142 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2026-04-06_crop.png
childress_tx | 2026-05-11 | S2B_14SLD_20260511_0_L2A | 220.6 | 24.67 | 0.06 | 119.78 | 0.156 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2026-05-11_crop.png
childress_tx | 2026-06-17 | S2A_14SLD_20260617_0_L2A | 220.6 | 19.13 | 0.0 | 139.1 | 0.151 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2026-06-17_crop.png
childress_tx | 2026-07-10 | S2B_14SLD_20260710_0_L2A | 220.6 | 19.65 | 0.02 | 130.3 | 0.167 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2026-07-10_crop.png
childress_tx | 2026-08-09 | S2B_14SLD_20260809_0_L2A | 220.6 | 17.56 | 0.06 | 136.13 | 0.164 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2026-08-09_crop.png
childress_tx | 2026-09-28 | S2B_14SMD_20260928_0_L2A | 220.6 | 14.82 | 0.77 | 135.35 | 0.134 | /workspace/nebius/peers/sites/imagery/childress_tx/detail/childress_tx_2026-09-28_crop.png
kvandal_no | 2023-06-26 | S2B_33WWS_20230626_0_L2A | 213.4 | 0.11 | 7.9 | 4.2 | 0.695 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2023-06-26_crop.png
kvandal_no | 2023-07-01 | S2A_33WXS_20230701_0_L2A | 213.4 | 3.06 | 4.72 | 13.11 | 0.712 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2023-07-01_crop.png
kvandal_no | 2024-07-15 | S2A_33WXS_20240715_1_L2A | 213.4 | 4.16 | 7.68 | 8.61 | 0.743 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2024-07-15_crop.png
kvandal_no | 2024-10-19 | S2A_33WWS_20241019_0_L2A | 213.4 | 0.01 | 19.03 | 0.01 | 0.376 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2024-10-19_crop.png
kvandal_no | 2025-07-18 | S2B_33WWS_20250718_0_L2A | 213.4 | 3.4 | 6.58 | 8.57 | 0.768 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2025-07-18_crop.png
kvandal_no | 2025-08-29 | S2C_33WWS_20250829_0_L2A | 213.4 | 0.52 | 5.18 | 5.99 | 0.78 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2025-08-29_crop.png
kvandal_no | 2025-09-09 | S2B_33WWS_20250909_1_L2A | 213.4 | 0.53 | 6.71 | 3.9 | 0.752 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2025-09-09_crop.png
kvandal_no | 2025-10-04 | S2C_33WXS_20251004_0_L2A | 213.4 | 0.7 | 5.53 | 4.07 | 0.552 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2025-10-04_crop.png
kvandal_no | 2026-05-31 | S2A_33WWS_20260531_1_L2A | 213.4 | 5.09 | 23.09 | 3.57 | 0.518 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2026-05-31_crop.png
kvandal_no | 2026-06-10 | S2A_33WWS_20260610_1_L2A | 213.4 | 12.16 | 5.3 | 17.27 | 0.637 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2026-06-10_crop.png
kvandal_no | 2026-08-06 | S2A_33WWS_20260806_0_L2A | 213.4 | 3.04 | 12.13 | 5.75 | 0.667 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2026-08-06_crop.png
kvandal_no | 2026-09-11 | S2A_33WXS_20260911_1_L2A | 213.4 | 2.03 | 7.2 | 4.66 | 0.6 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2026-09-11_crop.png
kvandal_no | 2026-10-03 | S2C_33WWS_20261003_0_L2A | 213.4 | 1.19 | 5.26 | 1.74 | 0.541 | /workspace/nebius/peers/sites/imagery/kvandal_no/detail/kvandal_no_2026-10-03_crop.png
abilene_tx | 2023-01-22 | S2A_14SMA_20230122_1_L2A | 734.3 | 0.57 | 0.03 | 60.2 | 0.232 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2023-01-22_crop.png
abilene_tx | 2023-04-29 | S2A_14SMB_20230429_0_L2A | 734.3 | 0.69 | 0.02 | 28.64 | 0.382 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2023-04-29_crop.png
abilene_tx | 2023-07-18 | S2A_14SMB_20230718_0_L2A | 734.3 | 0.52 | 0.03 | 36.17 | 0.408 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2023-07-18_crop.png
abilene_tx | 2023-10-19 | S2A_14SMB_20231019_1_L2A | 734.3 | 0.53 | 0.02 | 35.6 | 0.385 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2023-10-19_crop.png
abilene_tx | 2024-01-27 | S2A_14SMA_20240127_0_L2A | 734.3 | 0.53 | 0.2 | 9.61 | 0.296 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2024-01-27_crop.png
abilene_tx | 2024-04-11 | S2B_14SMA_20240411_0_L2A | 734.3 | 0.54 | 0.04 | 7.08 | 0.454 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2024-04-11_crop.png
abilene_tx | 2024-09-28 | S2B_14SMA_20240928_0_L2A | 734.3 | 2.42 | 0.02 | 80.6 | 0.321 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2024-09-28_crop.png
abilene_tx | 2024-10-23 | S2A_14SMA_20241023_0_L2A | 734.3 | 1.18 | 0.03 | 95.5 | 0.305 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2024-10-23_crop.png
abilene_tx | 2025-01-06 | S2B_14SMA_20250106_0_L2A | 734.3 | 1.89 | 0.11 | 92.24 | 0.305 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2025-01-06_crop.png
abilene_tx | 2025-04-10 | S2A_14SMA_20250410_0_L2A | 734.3 | 0.41 | 0.0 | 271.49 | 0.263 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2025-04-10_crop.png
abilene_tx | 2025-07-30 | S2C_14SMB_20250730_0_L2A | 734.3 | 7.19 | 0.81 | 287.45 | 0.288 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2025-07-30_crop.png
abilene_tx | 2025-08-28 | S2A_14SMB_20250828_0_L2A | 734.3 | 6.07 | 0.73 | 321.77 | 0.232 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2025-08-28_crop.png
abilene_tx | 2025-09-10 | S2B_14SMA_20250910_0_L2A | 734.3 | 4.79 | 3.25 | 316.63 | 0.232 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2025-09-10_crop.png
abilene_tx | 2025-10-03 | S2B_14SMB_20251003_0_L2A | 734.3 | 3.37 | 2.36 | 314.94 | 0.238 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2025-10-03_crop.png
abilene_tx | 2025-11-12 | S2B_14SMA_20251112_0_L2A | 734.3 | 1.67 | 2.38 | 326.37 | 0.197 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2025-11-12_crop.png
abilene_tx | 2025-12-12 | S2B_14SMA_20251212_0_L2A | 734.3 | 1.17 | 1.54 | 341.77 | 0.17 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2025-12-12_crop.png
abilene_tx | 2026-01-21 | S2B_14SMB_20260121_0_L2A | 734.3 | 0.98 | 0.75 | 340.45 | 0.159 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2026-01-21_crop.png
abilene_tx | 2026-02-15 | S2C_14SMA_20260215_0_L2A | 734.3 | 1.61 | 0.08 | 271.61 | 0.161 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2026-02-15_crop.png
abilene_tx | 2026-03-26 | S2A_14SMB_20260326_0_L2A | 734.3 | 0.71 | 0.03 | 467.77 | 0.155 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2026-03-26_crop.png
abilene_tx | 2026-04-08 | S2B_14SMB_20260408_0_L2A | 734.3 | 2.61 | 0.88 | 438.25 | 0.182 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2026-04-08_crop.png
abilene_tx | 2026-05-13 | S2C_14SMB_20260513_0_L2A | 734.3 | 2.64 | 0.05 | 449.12 | 0.188 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2026-05-13_crop.png
abilene_tx | 2026-06-17 | S2B_14SMB_20260617_1_L2A | 734.3 | 7.24 | 0.38 | 432.69 | 0.188 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2026-06-17_crop.png
abilene_tx | 2026-07-27 | S2B_14SMA_20260727_0_L2A | 734.3 | 6.63 | 3.83 | 430.61 | 0.184 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2026-07-27_crop.png
abilene_tx | 2026-08-16 | S2B_14SMA_20260816_0_L2A | 734.3 | 6.1 | 0.48 | 495.36 | 0.148 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2026-08-16_crop.png
abilene_tx | 2026-09-15 | S2B_14SMB_20260915_0_L2A | 734.3 | 5.52 | 3.88 | 504.22 | 0.138 | /workspace/nebius/peers/sites/imagery/abilene_tx/detail/abilene_tx_2026-09-15_crop.png
kcairworld_mo | 2023-02-03 | S2B_15SUD_20230203_0_L2A | 17.6 | 1.07 | 0.49 | 3.29 | 0.222 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2023-02-03_crop.png
kcairworld_mo | 2023-06-20 | S2B_15SUD_20230620_0_L2A | 17.6 | 1.45 | 0.57 | 2.12 | 0.45 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2023-06-20_crop.png
kcairworld_mo | 2023-07-10 | S2B_15SUD_20230710_0_L2A | 17.6 | 1.45 | 0.46 | 2.34 | 0.452 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2023-07-10_crop.png
kcairworld_mo | 2023-11-12 | S2A_15SUD_20231112_0_L2A | 17.6 | 1.09 | 0.16 | 2.74 | 0.352 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2023-11-12_crop.png
kcairworld_mo | 2024-03-19 | S2B_15SUD_20240319_0_L2A | 17.6 | 1.77 | 0.5 | 1.7 | 0.352 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2024-03-19_crop.png
kcairworld_mo | 2024-04-08 | S2B_15SUD_20240408_0_L2A | 17.6 | 1.8 | 0.46 | 1.61 | 0.387 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2024-04-08_crop.png
kcairworld_mo | 2024-09-10 | S2A_15SUD_20240910_0_L2A | 17.6 | 1.28 | 0.12 | 1.43 | 0.376 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2024-09-10_crop.png
kcairworld_mo | 2024-10-07 | S2A_15SUD_20241007_0_L2A | 17.6 | 1.65 | 0.21 | 2.44 | 0.413 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2024-10-07_crop.png
kcairworld_mo | 2025-02-27 | S2C_15SUD_20250227_0_L2A | 17.6 | 1.56 | 0.3 | 2.61 | 0.246 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2025-02-27_crop.png
kcairworld_mo | 2025-04-07 | S2A_15SUD_20250407_0_L2A | 17.6 | 1.86 | 0.21 | 2.07 | 0.378 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2025-04-07_crop.png
kcairworld_mo | 2025-07-27 | S2C_15SUD_20250727_0_L2A | 17.6 | 1.79 | 0.34 | 1.79 | 0.473 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2025-07-27_crop.png
kcairworld_mo | 2025-08-08 | S2A_15SUD_20250808_1_L2A | 17.6 | 1.66 | 0.29 | 1.93 | 0.452 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2025-08-08_crop.png
kcairworld_mo | 2025-09-07 | S2B_15SUD_20250907_0_L2A | 17.6 | 1.89 | 0.57 | 1.97 | 0.409 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2025-09-07_crop.png
kcairworld_mo | 2025-10-20 | S2B_15SUD_20251020_0_L2A | 17.6 | 1.66 | 0.72 | 1.83 | 0.414 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2025-10-20_crop.png
kcairworld_mo | 2025-11-03 | S2A_15SUD_20251103_0_L2A | 17.6 | 1.65 | 0.32 | 2.22 | 0.417 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2025-11-03_crop.png
kcairworld_mo | 2025-12-16 | S2B_15SUD_20251216_0_L2A | 17.6 | 1.69 | 0.97 | 1.94 | 0.289 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2025-12-16_crop.png
kcairworld_mo | 2026-01-12 | S2A_15SUD_20260112_0_L2A | 17.6 | 1.63 | 0.76 | 2.42 | 0.246 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-01-12_crop.png
kcairworld_mo | 2026-02-27 | S2B_15SUD_20260227_0_L2A | 17.6 | 1.75 | 0.74 | 2.62 | 0.229 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-02-27_crop.png
kcairworld_mo | 2026-03-09 | S2B_15SUD_20260309_0_L2A | 17.6 | 1.88 | 1.1 | 2.35 | 0.257 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-03-09_crop.png
kcairworld_mo | 2026-04-20 | S2C_15SUD_20260420_0_L2A | 17.6 | 2.32 | 0.26 | 2.4 | 0.399 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-04-20_crop.png
kcairworld_mo | 2026-05-13 | S2C_15SUD_20260513_0_L2A | 17.6 | 2.22 | 0.28 | 2.54 | 0.427 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-05-13_crop.png
kcairworld_mo | 2026-06-12 | S2C_15SUD_20260612_0_L2A | 17.6 | 2.27 | 0.22 | 2.86 | 0.446 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-06-12_crop.png
kcairworld_mo | 2026-07-11 | S2A_15SUD_20260711_0_L2A | 17.6 | 2.52 | 0.24 | 2.46 | 0.428 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-07-11_crop.png
kcairworld_mo | 2026-08-28 | S2C_15SUD_20260828_0_L2A | 17.6 | 2.06 | 0.59 | 2.44 | 0.406 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-08-28_crop.png
kcairworld_mo | 2026-09-02 | S2B_15SUD_20260902_0_L2A | 17.6 | 2.32 | 0.88 | 1.95 | 0.388 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-09-02_crop.png
kcairworld_mo | 2026-10-02 | S2B_15SUD_20261002_0_L2A | 17.6 | 2.11 | 0.87 | 1.66 | 0.454 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/detail/kcairworld_mo_2026-10-02_crop.png
portwash_wi | 2023-02-12 | S2A_16TDP_20230212_0_L2A | 595.5 | 18.17 | 4.04 | 72.0 | 0.259 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2023-02-12_crop.png
portwash_wi | 2023-05-20 | S2A_16TDP_20230520_0_L2A | 595.5 | 3.24 | 0.08 | 177.75 | 0.425 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2023-05-20_crop.png
portwash_wi | 2023-07-14 | S2B_16TDP_20230714_0_L2A | 595.5 | 6.15 | 0.27 | 8.61 | 0.636 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2023-07-14_crop.png
portwash_wi | 2023-11-19 | S2A_16TDP_20231119_0_L2A | 595.5 | 3.69 | 0.47 | 20.86 | 0.326 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2023-11-19_crop.png
portwash_wi | 2024-03-28 | S2A_16TDP_20240328_0_L2A | 595.5 | 3.08 | 0.26 | 26.92 | 0.279 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2024-03-28_crop.png
portwash_wi | 2024-04-14 | S2A_16TDP_20240414_0_L2A | 595.5 | 3.73 | 0.08 | 300.53 | 0.283 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2024-04-14_crop.png
portwash_wi | 2024-09-04 | S2A_16TDP_20240904_0_L2A | 595.5 | 2.64 | 0.22 | 12.57 | 0.694 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2024-09-04_crop.png
portwash_wi | 2024-10-09 | S2B_16TDP_20241009_0_L2A | 595.5 | 3.37 | 0.32 | 68.24 | 0.386 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2024-10-09_crop.png
portwash_wi | 2025-03-25 | S2A_16TDP_20250325_1_L2A | 595.5 | 3.52 | 0.37 | 60.07 | 0.249 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2025-03-25_crop.png
portwash_wi | 2025-06-23 | S2B_16TDP_20250623_0_L2A | 595.5 | 6.33 | 0.23 | 89.87 | 0.483 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2025-06-23_crop.png
portwash_wi | 2025-07-18 | S2C_16TDP_20250718_0_L2A | 595.5 | 4.73 | 0.15 | 7.57 | 0.705 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2025-07-18_crop.png
portwash_wi | 2025-08-02 | S2B_16TDP_20250802_0_L2A | 595.5 | 4.64 | 0.15 | 22.79 | 0.684 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2025-08-02_crop.png
portwash_wi | 2025-09-14 | S2B_16TDP_20250914_0_L2A | 595.5 | 3.4 | 0.52 | 6.47 | 0.63 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2025-09-14_crop.png
portwash_wi | 2025-10-04 | S2B_16TDP_20251004_0_L2A | 595.5 | 3.92 | 0.63 | 49.79 | 0.406 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2025-10-04_crop.png
portwash_wi | 2025-11-03 | S2B_16TDP_20251103_0_L2A | 595.5 | 3.05 | 0.52 | 79.19 | 0.394 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2025-11-03_crop.png
portwash_wi | 2026-02-13 | S2C_16TDP_20260213_0_L2A | 595.5 | 17.39 | 3.01 | 252.2 | 0.165 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2026-02-13_crop.png
portwash_wi | 2026-03-27 | S2A_16TDP_20260327_0_L2A | 595.5 | 3.79 | 1.89 | 246.76 | 0.165 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2026-03-27_crop.png
portwash_wi | 2026-04-22 | S2B_16TDP_20260422_0_L2A | 595.5 | 7.68 | 4.08 | 332.58 | 0.164 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2026-04-22_crop.png
portwash_wi | 2026-05-27 | S2C_16TDP_20260527_0_L2A | 595.5 | 13.16 | 4.01 | 350.57 | 0.229 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2026-05-27_crop.png
portwash_wi | 2026-06-23 | S2C_16TDP_20260623_0_L2A | 595.5 | 21.57 | 2.53 | 279.22 | 0.262 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2026-06-23_crop.png
portwash_wi | 2026-07-06 | S2C_16TDP_20260706_0_L2A | 595.5 | 21.66 | 5.29 | 263.58 | 0.334 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2026-07-06_crop.png
portwash_wi | 2026-08-25 | S2C_16TDP_20260825_0_L2A | 595.5 | 19.84 | 8.65 | 220.89 | 0.388 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2026-08-25_crop.png
portwash_wi | 2026-09-11 | S2C_16TDP_20260911_0_L2A | 595.5 | 22.85 | 8.92 | 219.6 | 0.381 | /workspace/nebius/peers/sites/imagery/portwash_wi/detail/portwash_wi_2026-09-11_crop.png
monarch_wv | 2023-03-30 | S2B_17SLD_20230330_0_L2A | 771.8 | 1.13 | 0.3 | 5.59 | 0.436 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2023-03-30_crop.png
monarch_wv | 2023-05-24 | S2A_17SMD_20230524_0_L2A | 771.8 | 0.94 | 0.09 | 3.52 | 0.702 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2023-05-24_crop.png
monarch_wv | 2023-09-01 | S2A_17SLD_20230901_1_L2A | 771.8 | 1.32 | 0.27 | 5.34 | 0.773 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2023-09-01_crop.png
monarch_wv | 2023-12-15 | S2B_17SMD_20231215_0_L2A | 771.8 | 1.01 | 0.43 | 4.52 | 0.416 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2023-12-15_crop.png
monarch_wv | 2024-03-24 | S2B_17SLD_20240324_0_L2A | 771.8 | 1.15 | 0.26 | 5.22 | 0.457 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2024-03-24_crop.png
monarch_wv | 2024-04-13 | S2B_17SMD_20240413_0_L2A | 771.8 | 1.45 | 0.3 | 5.9 | 0.566 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2024-04-13_crop.png
monarch_wv | 2024-09-05 | S2A_17SLD_20240905_0_L2A | 771.8 | 1.11 | 0.26 | 5.43 | 0.721 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2024-09-05_crop.png
monarch_wv | 2024-10-27 | S2B_17SMD_20241027_0_L2A | 771.8 | 1.48 | 0.36 | 4.44 | 0.53 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2024-10-27_crop.png
monarch_wv | 2025-03-11 | S2C_17SMD_20250311_0_L2A | 771.8 | 1.26 | 3.04 | 9.54 | 0.351 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2025-03-11_crop.png
monarch_wv | 2025-04-23 | S2C_17SLD_20250423_0_L2A | 771.8 | 1.43 | 0.31 | 5.12 | 0.625 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2025-04-23_crop.png
monarch_wv | 2025-08-31 | S2C_17SLD_20250831_0_L2A | 771.8 | 1.56 | 1.16 | 6.09 | 0.76 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2025-08-31_crop.png
monarch_wv | 2025-09-12 | S2B_17SLD_20250912_0_L2A | 771.8 | 1.47 | 0.59 | 5.41 | 0.704 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2025-09-12_crop.png
monarch_wv | 2025-10-05 | S2B_17SMD_20251005_0_L2A | 771.8 | 0.99 | 0.64 | 10.47 | 0.639 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2025-10-05_crop.png
monarch_wv | 2025-11-06 | S2C_17SLD_20251106_0_L2A | 771.8 | 1.22 | 0.25 | 4.28 | 0.501 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2025-11-06_crop.png
monarch_wv | 2026-03-09 | S2C_17SLD_20260309_0_L2A | 771.8 | 1.21 | 0.47 | 5.87 | 0.417 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2026-03-09_crop.png
monarch_wv | 2026-04-08 | S2C_17SLD_20260408_0_L2A | 771.8 | 1.3 | 0.3 | 5.28 | 0.534 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2026-04-08_crop.png
monarch_wv | 2026-05-28 | S2C_17SMD_20260528_0_L2A | 771.8 | 1.37 | 0.55 | 48.43 | 0.623 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2026-05-28_crop.png
monarch_wv | 2026-06-02 | S2B_17SLD_20260602_0_L2A | 771.8 | 2.07 | 12.35 | 94.66 | 0.62 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2026-06-02_crop.png
monarch_wv | 2026-07-14 | S2C_17SLD_20260714_0_L2A | 771.8 | 2.95 | 0.38 | 95.56 | 0.646 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2026-07-14_crop.png
monarch_wv | 2026-08-25 | S2A_17SLD_20260825_0_L2A | 771.8 | 1.72 | 2.58 | 99.49 | 0.631 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2026-08-25_crop.png
monarch_wv | 2026-09-25 | S2C_17SMD_20260925_0_L2A | 771.8 | 1.96 | 0.67 | 85.14 | 0.635 | /workspace/nebius/peers/sites/imagery/monarch_wv/detail/monarch_wv_2026-09-25_crop.png

## Imagery_AOI_metrics
site | date | scene | aoi_cloud | valid_frac | ndvi_mean | ndbi_mean | bsi_mean | builtbare_ha | brightroof_ha | chip
denton_tx | 2023-02-03 | S2B_14SPB_20230203_0_L2A | 0 | 0.997 | 0.4104 | -0.0184 | 0.0478 | 34.56 | 5.63 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2023-02-03.png
denton_tx | 2023-06-28 | S2A_14SPB_20230628_0_L2A | 0 | 1 | 0.4156 | 0.094 | 0.1094 | 47.69 | 16.64 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2023-06-28.png
denton_tx | 2023-09-01 | S2B_14SPB_20230901_0_L2A | 0 | 1 | 0.3096 | 0.122 | 0.15 | 236.08 | 17.6 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2023-09-01.png
denton_tx | 2023-10-06 | S2A_14SPB_20231006_0_L2A | 0 | 1 | 0.4055 | 0.1449 | 0.1592 | 49.38 | 11.87 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2023-10-06.png
denton_tx | 2024-03-19 | S2B_14SPB_20240319_0_L2A | 0 | 1 | 0.6607 | -0.1576 | -0.1222 | 30.32 | 12.48 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2024-03-19.png
denton_tx | 2024-04-03 | S2A_14SPB_20240403_0_L2A | 0 | 1 | 0.7175 | -0.2275 | -0.1859 | 30.22 | 14.06 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2024-04-03.png
denton_tx | 2024-09-10 | S2A_14SPB_20240910_0_L2A | 0 | 1 | 0.4629 | 0.0683 | 0.0919 | 53.15 | 14.6 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2024-09-10.png
denton_tx | 2024-10-20 | S2A_14SPB_20241020_0_L2A | 0 | 1 | 0.3825 | 0.1215 | 0.1478 | 71.24 | 11.8 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2024-10-20.png
denton_tx | 2025-01-03 | S2B_14SPB_20250103_0_L2A | 0 | 1 | 0.5288 | -0.0046 | 0.0174 | 41.16 | 7.77 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2025-01-03.png
denton_tx | 2025-04-08 | S2C_14SPB_20250408_0_L2A | 0 | 1 | 0.6495 | -0.1437 | -0.1068 | 39.58 | 11.17 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2025-04-08.png
denton_tx | 2025-07-22 | S2B_14SPB_20250722_0_L2A | 0 | 1 | 0.5173 | -0.0136 | 0.0183 | 59.31 | 25.33 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2025-07-22.png
denton_tx | 2025-08-08 | S2A_14SPB_20250808_1_L2A | 0 | 1 | 0.4329 | 0.0594 | 0.0855 | 79.5 | 18.07 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2025-08-08.png
denton_tx | 2025-09-10 | S2B_14SPB_20250910_0_L2A | 0 | 1 | 0.5099 | 0.007 | 0.0259 | 71.15 | 14.23 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2025-09-10.png
denton_tx | 2025-10-10 | S2B_14SPB_20251010_0_L2A | 0 | 1 | 0.5253 | 0.0118 | 0.0371 | 89.95 | 20.23 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2025-10-10.png
denton_tx | 2025-11-09 | S2B_14SPB_20251109_0_L2A | 0.0003 | 1 | 0.4883 | 0.0293 | 0.0676 | 76.97 | 23.76 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2025-11-09.png
denton_tx | 2025-12-09 | S2B_14SPB_20251209_0_L2A | 0 | 1 | 0.4159 | 0.1059 | 0.1318 | 81.99 | 15.37 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2025-12-09.png
denton_tx | 2026-01-03 | S2C_14SPB_20260103_0_L2A | 0 | 1 | 0.3769 | 0.145 | 0.1628 | 91.85 | 17.8 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2026-01-03.png
denton_tx | 2026-02-27 | S2B_14SPB_20260227_0_L2A | 0 | 1 | 0.3939 | 0.1102 | 0.1344 | 85.94 | 22.71 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2026-02-27.png
denton_tx | 2026-03-19 | S2B_14SPB_20260319_1_L2A | 0 | 1 | 0.4693 | 0.0411 | 0.0657 | 78.92 | 21.38 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2026-03-19.png
denton_tx | 2026-04-08 | S2B_14SPB_20260408_0_L2A | 0 | 1 | 0.6039 | -0.1142 | -0.0812 | 76.3 | 24.42 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2026-04-08.png
denton_tx | 2026-05-03 | S2C_14SPB_20260503_0_L2A | 0 | 1 | 0.6544 | -0.163 | -0.1272 | 66.76 | 28.42 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2026-05-03.png
denton_tx | 2026-06-07 | S2B_14SPB_20260607_1_L2A | 0.0014 | 0.999 | 0.5799 | -0.1444 | -0.0915 | 66.82 | 20.32 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2026-06-07.png
denton_tx | 2026-07-22 | S2C_14SPB_20260722_0_L2A | 0 | 1 | 0.4503 | 0.0453 | 0.0737 | 94.77 | 32.73 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2026-07-22.png
denton_tx | 2026-08-16 | S2B_14SPB_20260816_0_L2A | 0 | 1 | 0.3512 | 0.062 | 0.1025 | 145.44 | 34.67 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2026-08-16.png
denton_tx | 2026-09-15 | S2B_14SPB_20260915_0_L2A | 0 | 1 | 0.3212 | 0.1163 | 0.1509 | 200.08 | 31.33 | /workspace/nebius/peers/sites/imagery/denton_tx/denton_tx_2026-09-15.png
childress_tx | 2023-03-03 | S2A_14SMD_20230303_0_L2A | 0 | 1 | 0.2486 | 0.184 | 0.235 | 965.98 | 4.19 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2023-03-03.png
childress_tx | 2023-06-16 | S2B_14SLD_20230616_0_L2A | 0 | 1 | 0.4272 | 0.0397 | 0.0941 | 385.69 | 7.38 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2023-06-16.png
childress_tx | 2023-09-09 | S2A_14SMD_20230909_0_L2A | 0 | 1 | 0.218 | 0.1351 | 0.2046 | 1235.05 | 9.02 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2023-09-09.png
childress_tx | 2023-10-19 | S2A_14SMD_20231019_0_L2A | 0 | 1 | 0.2104 | 0.1993 | 0.2431 | 1344.51 | 6.03 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2023-10-19.png
childress_tx | 2024-01-17 | S2A_14SLD_20240117_0_L2A | 0 | 1 | 0.2311 | 0.195 | 0.2404 | 1098.78 | 3.72 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2024-01-17.png
childress_tx | 2024-04-11 | S2B_14SMD_20240411_0_L2A | 0 | 1 | 0.4357 | 0.0042 | 0.0529 | 270.71 | 3.66 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2024-04-11.png
childress_tx | 2024-07-30 | S2B_14SLD_20240730_0_L2A | 0 | 1 | 0.2492 | 0.1616 | 0.2029 | 947.53 | 13.09 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2024-07-30.png
childress_tx | 2024-12-02 | S2A_14SLD_20241202_0_L2A | 0 | 1 | 0.296 | 0.1267 | 0.1867 | 581.56 | 7 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2024-12-02.png
childress_tx | 2025-02-25 | S2B_14SLD_20250225_0_L2A | 0 | 1 | 4.1631 | 0.2856 | 0.5098 | 88.94 | 1.17 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2025-02-25.png
childress_tx | 2025-05-03 | S2A_14SLD_20250503_0_L2A | 0 | 1 | 0.4885 | -0.068 | 0.0018 | 262.63 | 12.64 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2025-05-03.png
childress_tx | 2025-07-30 | S2C_14SMD_20250730_0_L2A | 0 | 1 | 0.3433 | 0.0892 | 0.1394 | 496.38 | 19.42 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2025-07-30.png
childress_tx | 2025-08-14 | S2B_14SLD_20250814_0_L2A | 0 | 1 | 0.3715 | 0.078 | 0.1251 | 465.88 | 20.09 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2025-08-14.png
childress_tx | 2025-09-03 | S2B_14SLD_20250903_0_L2A | 0 | 1 | 0.4187 | 0.0474 | 0.0948 | 332.56 | 15.32 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2025-09-03.png
childress_tx | 2025-10-18 | S2C_14SLD_20251018_0_L2A | 0 | 1 | 0.3152 | 0.1296 | 0.1888 | 608.82 | 14.33 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2025-10-18.png
childress_tx | 2025-11-17 | S2C_14SLD_20251117_0_L2A | 0 | 1 | 0.2273 | 0.1952 | 0.2476 | 1013.59 | 14 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2025-11-17.png
childress_tx | 2025-12-22 | S2B_14SMD_20251222_0_L2A | 0 | 1 | 0.1955 | 0.2239 | 0.2596 | 1374.38 | 13.93 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2025-12-22.png
childress_tx | 2026-01-11 | S2B_14SMD_20260111_0_L2A | 0 | 1 | 0.2004 | 0.2157 | 0.2557 | 1269.51 | 14.56 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2026-01-11.png
childress_tx | 2026-02-20 | S2A_14SLD_20260220_0_L2A | 0 | 1 | 0.1922 | 0.2074 | 0.2547 | 1548.99 | 16.81 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2026-02-20.png
childress_tx | 2026-03-12 | S2B_14SMD_20260312_0_L2A | 0 | 1 | 0.1958 | 0.1866 | 0.2237 | 1402.91 | 27.67 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2026-03-12.png
childress_tx | 2026-04-06 | S2C_14SMD_20260406_0_L2A | 0 | 1 | 0.2143 | 0.1785 | 0.2224 | 1091.9 | 26.69 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2026-04-06.png
childress_tx | 2026-05-11 | S2B_14SLD_20260511_0_L2A | 0 | 1 | 0.2587 | 0.1246 | 0.1777 | 931.35 | 40.38 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2026-05-11.png
childress_tx | 2026-06-17 | S2A_14SLD_20260617_0_L2A | 0 | 1 | 0.2943 | 0.1167 | 0.1682 | 821.65 | 50.15 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2026-06-17.png
childress_tx | 2026-07-10 | S2B_14SLD_20260710_0_L2A | 0 | 1 | 0.3085 | 0.095 | 0.1474 | 741.27 | 51.83 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2026-07-10.png
childress_tx | 2026-08-09 | S2B_14SLD_20260809_0_L2A | 0 | 1 | 0.2852 | 0.1 | 0.1571 | 824.79 | 51.84 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2026-08-09.png
childress_tx | 2026-09-28 | S2B_14SMD_20260928_0_L2A | 0 | 1 | 0.2486 | 0.1344 | 0.1961 | 1051.24 | 33.92 | /workspace/nebius/peers/sites/imagery/childress_tx/childress_tx_2026-09-28.png
kvandal_no | 2023-06-26 | S2B_33WWS_20230626_0_L2A | 0 | 0.917 | 0.656 | -0.1523 | -0.195 | 281.61 | 11.65 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2023-06-26.png
kvandal_no | 2023-07-01 | S2A_33WXS_20230701_0_L2A | 0 | 0.944 | 0.6928 | -0.1961 | -0.1925 | 198.16 | 7.36 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2023-07-01.png
kvandal_no | 2024-07-15 | S2A_33WXS_20240715_1_L2A | 0 | 0.998 | 0.7103 | -0.2162 | -0.2233 | 228.83 | 2.91 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2024-07-15.png
kvandal_no | 2024-10-19 | S2A_33WWS_20241019_0_L2A | 0.0006 | 0.973 | 0.3367 | -0.1324 | -0.1266 | 185.44 | 50.09 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2024-10-19.png
kvandal_no | 2025-07-18 | S2B_33WWS_20250718_0_L2A | 0 | 0.944 | 0.7014 | -0.2208 | -0.273 | 299.27 | 7.55 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2025-07-18.png
kvandal_no | 2025-08-29 | S2C_33WWS_20250829_0_L2A | 0 | 0.997 | 0.761 | -0.2058 | -0.1972 | 228.49 | 1.95 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2025-08-29.png
kvandal_no | 2025-09-09 | S2B_33WWS_20250909_1_L2A | 0 | 0.998 | 0.7203 | -0.205 | -0.2378 | 272.72 | 1.34 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2025-09-09.png
kvandal_no | 2025-10-04 | S2C_33WXS_20251004_0_L2A | 0.0343 | 0.965 | 0.5724 | -0.0684 | -0.0366 | 173.25 | 1.2 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2025-10-04.png
kvandal_no | 2026-05-31 | S2A_33WWS_20260531_1_L2A | 0.0126 | 0.798 | 0.5425 | -0.0726 | -0.0868 | 323.97 | 17.8 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2026-05-31.png
kvandal_no | 2026-06-10 | S2A_33WWS_20260610_1_L2A | 0.0426 | 0.865 | 0.6457 | -0.1665 | -0.1883 | 304.47 | 12.66 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2026-06-10.png
kvandal_no | 2026-08-06 | S2A_33WWS_20260806_0_L2A | 0.0219 | 0.977 | 0.7372 | -0.2489 | -0.2534 | 204.19 | 2.87 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2026-08-06.png
kvandal_no | 2026-09-11 | S2A_33WXS_20260911_1_L2A | 0 | 1 | 0.6446 | -0.1009 | -0.0479 | 343.39 | 1.59 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2026-09-11.png
kvandal_no | 2026-10-03 | S2C_33WWS_20261003_0_L2A | 0 | 1 | 0.5878 | 0.0253 | 0.0533 | 311.94 | 1.16 | /workspace/nebius/peers/sites/imagery/kvandal_no/kvandal_no_2026-10-03.png
abilene_tx | 2023-01-22 | S2A_14SMA_20230122_1_L2A | 0 | 1 | 0.2302 | 0.1719 | 0.2184 | 363.92 | 2.97 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2023-01-22.png
abilene_tx | 2023-04-29 | S2A_14SMB_20230429_0_L2A | 0 | 1 | 0.3624 | 0.0532 | 0.1205 | 101.03 | 10.16 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2023-04-29.png
abilene_tx | 2023-07-18 | S2A_14SMB_20230718_0_L2A | 0 | 1 | 0.3863 | 0.0403 | 0.1005 | 104.33 | 7.64 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2023-07-18.png
abilene_tx | 2023-10-19 | S2A_14SMB_20231019_1_L2A | 0 | 1 | 0.3553 | 0.0644 | 0.1347 | 121.32 | 3.25 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2023-10-19.png
abilene_tx | 2024-01-27 | S2A_14SMA_20240127_0_L2A | 0 | 1 | 0.2897 | 0.1383 | 0.1803 | 162.16 | 0.77 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2024-01-27.png
abilene_tx | 2024-04-11 | S2B_14SMA_20240411_0_L2A | 0 | 1 | 0.4351 | 0.0174 | 0.0717 | 48.54 | 2.75 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2024-04-11.png
abilene_tx | 2024-09-28 | S2B_14SMA_20240928_0_L2A | 0 | 1 | 0.3223 | 0.1232 | 0.1678 | 170.79 | 14.24 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2024-09-28.png
abilene_tx | 2024-10-23 | S2A_14SMA_20241023_0_L2A | 0 | 1 | 0.3076 | 0.1241 | 0.177 | 197.82 | 21.69 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2024-10-23.png
abilene_tx | 2025-01-06 | S2B_14SMA_20250106_0_L2A | 0 | 1 | 0.3119 | 0.1022 | 0.1603 | 177.19 | 21.29 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2025-01-06.png
abilene_tx | 2025-04-10 | S2A_14SMA_20250410_0_L2A | 0 | 1 | 0.2911 | 0.0686 | 0.1385 | 371.16 | 70.9 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2025-04-10.png
abilene_tx | 2025-07-30 | S2C_14SMB_20250730_0_L2A | 0 | 1 | 0.3194 | 0.0388 | 0.1172 | 395 | 124.98 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2025-07-30.png
abilene_tx | 2025-08-28 | S2A_14SMB_20250828_0_L2A | 0 | 1 | 0.2564 | 0.1047 | 0.1685 | 486.7 | 127.14 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2025-08-28.png
abilene_tx | 2025-09-10 | S2B_14SMA_20250910_0_L2A | 0 | 1 | 0.2529 | 0.0951 | 0.149 | 459.96 | 100.52 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2025-09-10.png
abilene_tx | 2025-10-03 | S2B_14SMB_20251003_0_L2A | 0 | 1 | 0.2649 | 0.0776 | 0.1463 | 452.26 | 83.62 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2025-10-03.png
abilene_tx | 2025-11-12 | S2B_14SMA_20251112_0_L2A | 0 | 1 | 0.229 | 0.0787 | 0.1585 | 489.68 | 80.22 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2025-11-12.png
abilene_tx | 2025-12-12 | S2B_14SMA_20251212_0_L2A | 0 | 1 | 0.1953 | 0.1193 | 0.1949 | 619.58 | 76.97 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2025-12-12.png
abilene_tx | 2026-01-21 | S2B_14SMB_20260121_0_L2A | 0 | 1 | 0.181 | 0.113 | 0.1964 | 670.58 | 87.87 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2026-01-21.png
abilene_tx | 2026-02-15 | S2C_14SMA_20260215_0_L2A | 0 | 1 | 0.1863 | 0.1234 | 0.2101 | 603.4 | 59.89 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2026-02-15.png
abilene_tx | 2026-03-26 | S2A_14SMB_20260326_0_L2A | 0 | 1 | 0.1873 | 0.1102 | 0.1853 | 643 | 155.68 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2026-03-26.png
abilene_tx | 2026-04-08 | S2B_14SMB_20260408_0_L2A | 0 | 1 | 0.2172 | 0.0976 | 0.1724 | 600.89 | 155.92 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2026-04-08.png
abilene_tx | 2026-05-13 | S2C_14SMB_20260513_0_L2A | 0 | 1 | 0.2264 | 0.0806 | 0.1566 | 617.31 | 191.32 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2026-05-13.png
abilene_tx | 2026-06-17 | S2B_14SMB_20260617_1_L2A | 0 | 1 | 0.2436 | 0.0658 | 0.1388 | 559.85 | 217.65 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2026-06-17.png
abilene_tx | 2026-07-27 | S2B_14SMA_20260727_0_L2A | 0 | 1 | 0.2341 | 0.0632 | 0.1396 | 575.71 | 202.6 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2026-07-27.png
abilene_tx | 2026-08-16 | S2B_14SMA_20260816_0_L2A | 0 | 0.999 | 0.1811 | 0.0909 | 0.1633 | 777.87 | 191.95 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2026-08-16.png
abilene_tx | 2026-09-15 | S2B_14SMB_20260915_0_L2A | 0 | 1 | 0.1655 | 0.1101 | 0.1831 | 884.76 | 165.79 | /workspace/nebius/peers/sites/imagery/abilene_tx/abilene_tx_2026-09-15.png
kcairworld_mo | 2023-02-03 | S2B_15SUD_20230203_0_L2A | 0 | 1 | 0.2006 | 0.1088 | 0.1495 | 57.48 | 17.92 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2023-02-03.png
kcairworld_mo | 2023-06-20 | S2B_15SUD_20230620_0_L2A | 0 | 1 | 0.4607 | -0.1331 | -0.0894 | 24.98 | 19.07 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2023-06-20.png
kcairworld_mo | 2023-07-10 | S2B_15SUD_20230710_0_L2A | 0 | 1 | 0.4745 | -0.1406 | -0.0961 | 27.18 | 20.91 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2023-07-10.png
kcairworld_mo | 2023-11-12 | S2A_15SUD_20231112_0_L2A | 0 | 1 | 0.3196 | 0.0422 | 0.0975 | 41.57 | 16.62 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2023-11-12.png
kcairworld_mo | 2024-03-19 | S2B_15SUD_20240319_0_L2A | 0 | 1 | 0.305 | 0.039 | 0.0773 | 35.86 | 18.07 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2024-03-19.png
kcairworld_mo | 2024-04-08 | S2B_15SUD_20240408_0_L2A | 0 | 1 | 0.3487 | -0.0082 | 0.0376 | 32 | 18.92 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2024-04-08.png
kcairworld_mo | 2024-09-10 | S2A_15SUD_20240910_0_L2A | 0 | 1 | 0.3614 | -0.0768 | -0.0281 | 19.43 | 14.54 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2024-09-10.png
kcairworld_mo | 2024-10-07 | S2A_15SUD_20241007_0_L2A | 0 | 1 | 0.3699 | -0.0261 | 0.0287 | 30.38 | 18.17 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2024-10-07.png
kcairworld_mo | 2025-02-27 | S2C_15SUD_20250227_0_L2A | 0 | 1 | 17.4861 | 0.1799 | 14.735 | 28.04 | 14.73 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2025-02-27.png
kcairworld_mo | 2025-04-07 | S2A_15SUD_20250407_0_L2A | 0 | 1 | 0.3557 | -0.0254 | 0.0297 | 30.2 | 19.79 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2025-04-07.png
kcairworld_mo | 2025-07-27 | S2C_15SUD_20250727_0_L2A | 0 | 1 | 0.4816 | -0.1356 | -0.0935 | 29.13 | 19.43 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2025-07-27.png
kcairworld_mo | 2025-08-08 | S2A_15SUD_20250808_1_L2A | 0 | 1 | 0.4702 | -0.1272 | -0.0824 | 29.48 | 18 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2025-08-08.png
kcairworld_mo | 2025-09-07 | S2B_15SUD_20250907_0_L2A | 0 | 1 | 0.4362 | -0.1025 | -0.0601 | 29.12 | 18.13 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2025-09-07.png
kcairworld_mo | 2025-10-20 | S2B_15SUD_20251020_0_L2A | 0 | 1 | 0.3871 | -0.0287 | 0.0176 | 30.09 | 17.12 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2025-10-20.png
kcairworld_mo | 2025-11-03 | S2A_15SUD_20251103_0_L2A | 0 | 1 | 0.3799 | -0.0179 | 0.0368 | 29.26 | 17.24 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2025-11-03.png
kcairworld_mo | 2025-12-16 | S2B_15SUD_20251216_0_L2A | 0 | 1 | 0.2693 | 0.07 | 0.0993 | 43.31 | 17.42 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2025-12-16.png
kcairworld_mo | 2026-01-12 | S2A_15SUD_20260112_0_L2A | 0 | 1 | 0.2305 | 0.0986 | 0.1398 | 46.54 | 17.52 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-01-12.png
kcairworld_mo | 2026-02-27 | S2B_15SUD_20260227_0_L2A | 0 | 1 | 0.2144 | 0.1134 | 0.1443 | 51.31 | 17.7 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-02-27.png
kcairworld_mo | 2026-03-09 | S2B_15SUD_20260309_0_L2A | 0 | 1 | 0.2409 | 0.097 | 0.1255 | 45.64 | 18.45 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-03-09.png
kcairworld_mo | 2026-04-20 | S2C_15SUD_20260420_0_L2A | 0 | 1 | 0.3857 | -0.0442 | 0.0039 | 29.27 | 19.88 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-04-20.png
kcairworld_mo | 2026-05-13 | S2C_15SUD_20260513_0_L2A | 0 | 1 | 0.4131 | -0.0863 | -0.0336 | 26.87 | 20.2 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-05-13.png
kcairworld_mo | 2026-06-12 | S2C_15SUD_20260612_0_L2A | 0 | 1 | 0.4854 | -0.137 | -0.0851 | 27.29 | 21.24 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-06-12.png
kcairworld_mo | 2026-07-11 | S2A_15SUD_20260711_0_L2A | 0 | 1 | 0.4819 | -0.1304 | -0.0835 | 29.2 | 21.55 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-07-11.png
kcairworld_mo | 2026-08-28 | S2C_15SUD_20260828_0_L2A | 0 | 1 | 0.4454 | -0.1015 | -0.0589 | 29.86 | 17.21 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-08-28.png
kcairworld_mo | 2026-09-02 | S2B_15SUD_20260902_0_L2A | 0 | 1 | 0.4201 | -0.0739 | -0.0385 | 32.42 | 17.57 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-09-02.png
kcairworld_mo | 2026-10-02 | S2B_15SUD_20261002_0_L2A | 0 | 1 | 0.4511 | -0.1024 | -0.0577 | 26.76 | 17.3 | /workspace/nebius/peers/sites/imagery/kcairworld_mo/kcairworld_mo_2026-10-02.png
portwash_wi | 2023-02-12 | S2A_16TDP_20230212_0_L2A | 0.0004 | 0.939 | 0.2594 | 0.0208 | 0.1326 | 554.82 | 24.23 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2023-02-12.png
portwash_wi | 2023-05-20 | S2A_16TDP_20230520_0_L2A | 0.0001 | 1 | 0.4716 | -0.0795 | -0.0323 | 791.48 | 6.35 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2023-05-20.png
portwash_wi | 2023-07-14 | S2B_16TDP_20230714_0_L2A | 0.0002 | 1 | 0.6741 | -0.1992 | -0.1588 | 69.83 | 8.14 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2023-07-14.png
portwash_wi | 2023-11-19 | S2A_16TDP_20231119_0_L2A | 0.0021 | 0.96 | 0.3695 | 0.0563 | 0.1103 | 588.18 | 3.73 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2023-11-19.png
portwash_wi | 2024-03-28 | S2A_16TDP_20240328_0_L2A | 0.0047 | 0.966 | 0.3009 | 0.0468 | 0.1119 | 682.13 | 5.22 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2024-03-28.png
portwash_wi | 2024-04-14 | S2A_16TDP_20240414_0_L2A | 0 | 1 | 0.3224 | 0.0607 | 0.1061 | 1048.17 | 7.34 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2024-04-14.png
portwash_wi | 2024-09-04 | S2A_16TDP_20240904_0_L2A | 0 | 0.968 | 0.7159 | -0.2377 | -0.1927 | 36.56 | 4.9 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2024-09-04.png
portwash_wi | 2024-10-09 | S2B_16TDP_20241009_0_L2A | 0 | 0.989 | 0.4867 | -0.0132 | 0.0273 | 485.78 | 4.71 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2024-10-09.png
portwash_wi | 2025-03-25 | S2A_16TDP_20250325_1_L2A | 0.0045 | 0.996 | 0.2381 | 0.0886 | 0.1535 | 858.29 | 5.7 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2025-03-25.png
portwash_wi | 2025-06-23 | S2B_16TDP_20250623_0_L2A | 0.0093 | 0.991 | 0.5497 | -0.1173 | -0.0795 | 234.75 | 8.5 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2025-06-23.png
portwash_wi | 2025-07-18 | S2C_16TDP_20250718_0_L2A | 0 | 1 | 0.7599 | -0.3039 | -0.2621 | 58.35 | 7.18 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2025-07-18.png
portwash_wi | 2025-08-02 | S2B_16TDP_20250802_0_L2A | 0.0001 | 1 | 0.7031 | -0.2817 | -0.2511 | 100.34 | 7.66 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2025-08-02.png
portwash_wi | 2025-09-14 | S2B_16TDP_20250914_0_L2A | 0 | 0.959 | 0.7188 | -0.2559 | -0.207 | 69.69 | 4 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2025-09-14.png
portwash_wi | 2025-10-04 | S2B_16TDP_20251004_0_L2A | 0 | 0.978 | 0.4859 | 0.0039 | 0.0275 | 556.43 | 3.99 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2025-10-04.png
portwash_wi | 2025-11-03 | S2B_16TDP_20251103_0_L2A | 0 | 0.999 | 0.4617 | -0.0027 | 0.0382 | 507.56 | 3.67 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2025-11-03.png
portwash_wi | 2026-02-13 | S2C_16TDP_20260213_0_L2A | 0 | 0.927 | 0.198 | 0.0369 | 0.1134 | 1128.05 | 65.63 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2026-02-13.png
portwash_wi | 2026-03-27 | S2A_16TDP_20260327_0_L2A | 0.0267 | 0.973 | 0.2317 | 0.0681 | 0.1313 | 912.39 | 12.1 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2026-03-27.png
portwash_wi | 2026-04-22 | S2B_16TDP_20260422_0_L2A | 0 | 0.971 | 0.3199 | 0.0414 | 0.0857 | 1034.03 | 66.38 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2026-04-22.png
portwash_wi | 2026-05-27 | S2C_16TDP_20260527_0_L2A | 0.0001 | 0.994 | 0.3874 | -0.008 | 0.0346 | 1081.63 | 154.89 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2026-05-27.png
portwash_wi | 2026-06-23 | S2C_16TDP_20260623_0_L2A | 0.0001 | 1 | 0.5006 | -0.1165 | -0.0695 | 418.67 | 190.32 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2026-06-23.png
portwash_wi | 2026-07-06 | S2C_16TDP_20260706_0_L2A | 0 | 0.976 | 0.6183 | -0.1805 | -0.1329 | 342.81 | 170.91 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2026-07-06.png
portwash_wi | 2026-08-25 | S2C_16TDP_20260825_0_L2A | 0.0008 | 0.975 | 0.6692 | -0.2435 | -0.2058 | 307.86 | 134.94 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2026-08-25.png
portwash_wi | 2026-09-11 | S2C_16TDP_20260911_0_L2A | 0 | 1 | 0.6636 | -0.236 | -0.1935 | 307.51 | 134.6 | /workspace/nebius/peers/sites/imagery/portwash_wi/portwash_wi_2026-09-11.png
monarch_wv | 2023-03-30 | S2B_17SLD_20230330_0_L2A | 0.0003 | 1 | 0.4072 | 0.0396 | 0.0917 | 133.75 | 4.03 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2023-03-30.png
monarch_wv | 2023-05-24 | S2A_17SMD_20230524_0_L2A | 0 | 1 | 0.7057 | -0.302 | -0.248 | 47.28 | 1.87 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2023-05-24.png
monarch_wv | 2023-09-01 | S2A_17SLD_20230901_1_L2A | 0 | 1 | 0.7406 | -0.2757 | -0.2337 | 116.21 | 4.7 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2023-09-01.png
monarch_wv | 2023-12-15 | S2B_17SMD_20231215_0_L2A | 0 | 1 | 0.39 | 0.1422 | 0.1541 | 246.43 | 8.8 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2023-12-15.png
monarch_wv | 2024-03-24 | S2B_17SLD_20240324_0_L2A | 0.0007 | 0.999 | 0.4235 | 0.0587 | 0.0981 | 154.57 | 7.18 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2024-03-24.png
monarch_wv | 2024-04-13 | S2B_17SMD_20240413_0_L2A | 0.0011 | 0.999 | 0.5348 | -0.1133 | -0.0277 | 114.79 | 3.7 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2024-04-13.png
monarch_wv | 2024-09-05 | S2A_17SLD_20240905_0_L2A | 0 | 1 | 0.6979 | -0.1998 | -0.165 | 111.58 | 3.3 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2024-09-05.png
monarch_wv | 2024-10-27 | S2B_17SMD_20241027_0_L2A | 0 | 1 | 0.5148 | 0.0249 | 0.0208 | 231.6 | 7.51 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2024-10-27.png
monarch_wv | 2025-03-11 | S2C_17SMD_20250311_0_L2A | 0.0003 | 1 | 0.3198 | 0.1407 | 0.1666 | 226.18 | 7.76 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2025-03-11.png
monarch_wv | 2025-04-23 | S2C_17SLD_20250423_0_L2A | 0 | 1 | 0.6182 | -0.129 | -0.0919 | 227.85 | 5.61 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2025-04-23.png
monarch_wv | 2025-08-31 | S2C_17SLD_20250831_0_L2A | 0 | 1 | 0.7315 | -0.2332 | -0.1988 | 218.16 | 4.54 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2025-08-31.png
monarch_wv | 2025-09-12 | S2B_17SLD_20250912_0_L2A | 0.0265 | 0.973 | 0.6915 | -0.2035 | -0.1724 | 71.77 | 3.16 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2025-09-12.png
monarch_wv | 2025-10-05 | S2B_17SMD_20251005_0_L2A | 0 | 1 | 0.6319 | -0.0796 | -0.0589 | 181.29 | 3.55 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2025-10-05.png
monarch_wv | 2025-11-06 | S2C_17SLD_20251106_0_L2A | 0.0124 | 0.988 | 0.4866 | 0.0973 | 0.1187 | 220.13 | 5.94 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2025-11-06.png
monarch_wv | 2026-03-09 | S2C_17SLD_20260309_0_L2A | 0 | 1 | 0.3833 | 0.1115 | 0.1838 | 151.7 | 6.54 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2026-03-09.png
monarch_wv | 2026-04-08 | S2C_17SLD_20260408_0_L2A | 0 | 1 | 0.522 | -0.0602 | 0.007 | 119.28 | 5.87 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2026-04-08.png
monarch_wv | 2026-05-28 | S2C_17SMD_20260528_0_L2A | 0 | 1 | 0.6777 | -0.2938 | -0.2259 | 134.31 | 8.18 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2026-05-28.png
monarch_wv | 2026-06-02 | S2B_17SLD_20260602_0_L2A | 0.0003 | 1 | 0.6802 | -0.257 | -0.2164 | 226.91 | 10.24 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2026-06-02.png
monarch_wv | 2026-07-14 | S2C_17SLD_20260714_0_L2A | 0.0313 | 0.969 | 0.6972 | -0.2272 | -0.2077 | 270.76 | 11.35 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2026-07-14.png
monarch_wv | 2026-08-25 | S2A_17SLD_20260825_0_L2A | 0.0349 | 0.965 | 0.6967 | -0.2654 | -0.2018 | 167.8 | 15.15 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2026-08-25.png
monarch_wv | 2026-09-25 | S2C_17SMD_20260925_0_L2A | 0 | 1 | 0.6788 | -0.2148 | -0.1346 | 181.85 | 5.79 | /workspace/nebius/peers/sites/imagery/monarch_wv/monarch_wv_2026-09-25.png

## Thermal
site | date | id | campus_C | background_C | anomaly_C
denton_tx | 2023-01-23 | LC09_L2SP_027037_20230123_02_T1 | 14.82 | 16.1 | -1.28
denton_tx | 2023-04-13 | LC09_L2SP_027037_20230413_02_T1 | 33.1 | 33.83 | -0.72
denton_tx | 2023-05-23 | LC08_L2SP_027037_20230523_02_T1 | 41.64 | 42.59 | -0.95
denton_tx | 2023-06-24 | LC08_L2SP_027037_20230624_02_T1 | 45.79 | 46.89 | -1.09
denton_tx | 2023-07-18 | LC09_L2SP_027037_20230718_02_T1 | 55.36 | 57.27 | -1.91
denton_tx | 2023-07-26 | LC08_L2SP_027037_20230726_02_T1 | 47.71 | 49.1 | -1.39
denton_tx | 2023-08-03 | LC09_L2SP_027037_20230803_02_T1 | 51.1 | 52.82 | -1.72
denton_tx | 2023-08-19 | LC09_L2SP_027037_20230819_02_T1 | 55.09 | 56.78 | -1.7
denton_tx | 2023-09-04 | LC09_L2SP_027037_20230904_02_T1 | 47.46 | 48.91 | -1.45
denton_tx | 2023-10-06 | LC09_L2SP_027037_20231006_02_T1 | 34.59 | 35.52 | -0.93
denton_tx | 2023-10-14 | LC08_L2SP_027037_20231014_02_T1 | 16.22 | 16.9 | -0.68
denton_tx | 2023-11-07 | LC09_L2SP_027037_20231107_02_T1 | 29.35 | 29.93 | -0.58
denton_tx | 2023-11-15 | LC08_L2SP_027037_20231115_02_T1 | 24.06 | 24.87 | -0.81
denton_tx | 2023-12-01 | LC08_L2SP_027037_20231201_02_T1 | 14.66 | 15.08 | -0.42
denton_tx | 2024-01-18 | LC08_L2SP_027037_20240118_02_T1 | 14.26 | 14.5 | -0.25
denton_tx | 2024-07-04 | LC09_L2SP_027037_20240704_02_T1 | 47.73 | 48.89 | -1.15
denton_tx | 2024-08-05 | LC09_L2SP_027037_20240805_02_T1 | 43.97 | 45.8 | -1.82
denton_tx | 2024-08-13 | LC08_L2SP_027037_20240813_02_T1 | 49.69 | 50.95 | -1.26
denton_tx | 2024-08-21 | LC09_L2SP_027037_20240821_02_T1 | 45.84 | 46.97 | -1.13
denton_tx | 2024-09-30 | LC08_L2SP_027037_20240930_02_T1 | 40.15 | 41.83 | -1.68
denton_tx | 2024-10-08 | LC09_L2SP_027037_20241008_02_T1 | 35.54 | 36.91 | -1.37
denton_tx | 2024-10-16 | LC08_L2SP_027037_20241016_02_T1 | 26.33 | 27.29 | -0.95
denton_tx | 2024-10-24 | LC09_L2SP_027037_20241024_02_T1 | 36.89 | 37.49 | -0.59
denton_tx | 2024-11-09 | LC09_L2SP_027037_20241109_02_T1 | 21.9 | 22.64 | -0.74
denton_tx | 2024-12-03 | LC08_L2SP_027037_20241203_02_T1 | 14.28 | 15.25 | -0.97
denton_tx | 2025-04-10 | LC08_L2SP_027037_20250410_02_T1 | 30.71 | 31.3 | -0.6
denton_tx | 2025-05-04 | LC09_L2SP_027037_20250504_02_T1 | 28.3 | 29.1 | -0.79
denton_tx | 2025-05-12 | LC08_L2SP_027037_20250512_02_T1 | 32.68 | 33.27 | -0.6
denton_tx | 2025-05-20 | LC09_L2SP_027037_20250520_02_T1 | 30.86 | 31.7 | -0.84
denton_tx | 2025-06-29 | LC08_L2SP_027037_20250629_02_T1 | 46.18 | 45.11 | 1.07
denton_tx | 2025-07-23 | LC09_L2SP_027037_20250723_02_T1 | 45.15 | 45.93 | -0.78
denton_tx | 2025-07-31 | LC08_L2SP_027037_20250731_02_T1 | 49.09 | 50.06 | -0.97
denton_tx | 2025-08-08 | LC09_L2SP_027037_20250808_02_T1 | 45.66 | 46.87 | -1.21
denton_tx | 2025-08-24 | LC09_L2SP_027037_20250824_02_T1 | 44.65 | 46.08 | -1.43
denton_tx | 2025-09-09 | LC09_L2SP_027037_20250909_02_T1 | 35.08 | 35.61 | -0.53
denton_tx | 2025-09-17 | LC08_L2SP_027037_20250917_02_T1 | 40.85 | 41.29 | -0.44
denton_tx | 2025-09-25 | LC09_L2SP_027037_20250925_02_T1 | 33.34 | 34.37 | -1.04
denton_tx | 2025-10-03 | LC08_L2SP_027037_20251003_02_T1 | 37.83 | 37.85 | -0.02
denton_tx | 2025-10-11 | LC09_L2SP_027037_20251011_02_T1 | 35.73 | 36.24 | -0.51
denton_tx | 2025-10-19 | LC08_L2SP_027037_20251019_02_T1 | 25.83 | 26.68 | -0.85
denton_tx | 2025-11-04 | LC08_L2SP_027037_20251104_02_T1 | 24.95 | 25.4 | -0.45
denton_tx | 2025-12-30 | LC09_L2SP_027037_20251230_02_T1 | 12.18 | 13.63 | -1.45
denton_tx | 2026-01-15 | LC09_L2SP_027037_20260115_02_T1 | 14.82 | 16.09 | -1.27
denton_tx | 2026-02-16 | LC09_L2SP_027037_20260216_02_T1 | 20.89 | 21.68 | -0.79
denton_tx | 2026-02-24 | LC08_L2SP_027037_20260224_02_T1 | 15.42 | 15.64 | -0.23
denton_tx | 2026-04-05 | LC09_L2SP_027037_20260405_02_T1 | 19.9 | 20.56 | -0.66
denton_tx | 2026-05-31 | LC08_L2SP_027037_20260531_02_T1 | 41.51 | 41.59 | -0.08
denton_tx | 2026-07-02 | LC08_L2SP_027037_20260702_02_T1 | 42.27 | 41.27 | 1.0
denton_tx | 2026-07-10 | LC09_L2SP_027037_20260710_02_T1 | 42.73 | 42.51 | 0.22
denton_tx | 2026-07-26 | LC09_L2SP_027037_20260726_02_T1 | 44.11 | 44.74 | -0.62
denton_tx | 2026-08-11 | LC09_L2SP_027037_20260811_02_T1 | 46.99 | 48.41 | -1.42
denton_tx | 2026-08-19 | LC08_L2SP_027037_20260819_02_T1 | 40.97 | 43.95 | -2.97
denton_tx | 2026-09-12 | LC09_L2SP_027037_20260912_02_T1 | 44.74 | 47.13 | -2.39
childress_tx | 2023-01-13 | LC08_L2SP_029036_20230113_02_T1 | 19.39 | 20.16 | -0.77
childress_tx | 2023-01-21 | LC09_L2SP_029036_20230121_02_T1 | 16.52 | 17.33 | -0.81
childress_tx | 2023-02-14 | LC08_L2SP_029036_20230214_02_T1 | 15.23 | 15.67 | -0.44
childress_tx | 2023-02-22 | LC09_L2SP_029036_20230222_02_T1 | 25.49 | 26.05 | -0.56
childress_tx | 2023-03-26 | LC09_L2SP_029036_20230326_02_T1 | 28.54 | 29.21 | -0.67
childress_tx | 2023-04-03 | LC08_L2SP_029036_20230403_02_T1 | 42.69 | 43.37 | -0.68
childress_tx | 2023-05-05 | LC08_L2SP_029036_20230505_02_T1 | 41.82 | 42.57 | -0.74
childress_tx | 2023-05-29 | LC09_L2SP_029036_20230529_02_T1 | 35.53 | 35.92 | -0.39
childress_tx | 2023-06-06 | LC08_L2SP_029036_20230606_02_T1 | 33.36 | 33.63 | -0.27
childress_tx | 2023-06-14 | LC09_L2SP_029036_20230614_02_T1 | 42.8 | 42.84 | -0.04
childress_tx | 2023-07-16 | LC09_L2SP_029036_20230716_02_T1 | 40.63 | 40.58 | 0.05
childress_tx | 2023-07-24 | LC08_L2SP_029036_20230724_02_T1 | 49.93 | 50.23 | -0.3
childress_tx | 2023-08-01 | LC09_L2SP_029036_20230801_02_T1 | 55.63 | 56.17 | -0.54
childress_tx | 2023-08-17 | LC09_L2SP_029036_20230817_02_T1 | 59.28 | 60.19 | -0.92
childress_tx | 2023-08-25 | LC08_L2SP_029036_20230825_02_T1 | 53.44 | 54.4 | -0.97
childress_tx | 2023-09-02 | LC09_L2SP_029036_20230902_02_T1 | 51.87 | 52.66 | -0.78
childress_tx | 2023-09-10 | LC08_L2SP_029036_20230910_02_T1 | 50.18 | 50.77 | -0.59
childress_tx | 2023-09-18 | LC09_L2SP_029036_20230918_02_T1 | 41.79 | 42.3 | -0.52
childress_tx | 2023-09-26 | LC08_L2SP_029036_20230926_02_T1 | 45.94 | 46.99 | -1.05
childress_tx | 2023-10-12 | LC08_L2SP_029036_20231012_02_T1 | 38.58 | 39.42 | -0.84
childress_tx | 2023-10-20 | LC09_L2SP_029036_20231020_02_T1 | 40.75 | 41.83 | -1.08
childress_tx | 2023-11-21 | LC09_L2SP_029036_20231121_02_T1 | 18.73 | 19.52 | -0.79
childress_tx | 2023-12-07 | LC09_L2SP_029036_20231207_02_T1 | 20.61 | 21.33 | -0.72
childress_tx | 2024-01-16 | LC08_L2SP_029036_20240116_02_T1 | 3.94 | 5.04 | -1.1
childress_tx | 2024-02-01 | LC08_L2SP_029036_20240201_02_T1 | 19.45 | 19.89 | -0.44
childress_tx | 2024-02-25 | LC09_L2SP_029036_20240225_02_T1 | 30.88 | 31.15 | -0.27
childress_tx | 2024-03-20 | LC08_L2SP_029036_20240320_02_T1 | 32.77 | 33.09 | -0.31
childress_tx | 2024-03-28 | LC09_L2SP_029036_20240328_02_T1 | 29.59 | 29.95 | -0.36
childress_tx | 2024-04-05 | LC08_L2SP_029036_20240405_02_T1 | 37.0 | 37.52 | -0.52
childress_tx | 2024-04-13 | LC09_L2SP_029036_20240413_02_T1 | 31.72 | 32.35 | -0.63
childress_tx | 2024-04-29 | LC09_L2SP_029036_20240429_02_T1 | 38.77 | 39.09 | -0.32
childress_tx | 2024-05-07 | LC08_L2SP_029036_20240507_02_T1 | 37.33 | 38.17 | -0.84
childress_tx | 2024-05-31 | LC09_L2SP_029036_20240531_02_T1 | 38.73 | 39.38 | -0.65
childress_tx | 2024-06-08 | LC08_L2SP_029036_20240608_02_T1 | 37.82 | 39.21 | -1.39
childress_tx | 2024-06-16 | LC09_L2SP_029036_20240616_02_T1 | 45.23 | 46.99 | -1.76
childress_tx | 2024-06-24 | LC08_L2SP_029036_20240624_02_T1 | 51.34 | 53.33 | -1.99
childress_tx | 2024-07-02 | LC09_L2SP_029036_20240702_02_T1 | 55.26 | 57.24 | -1.98
childress_tx | 2024-08-03 | LC09_L2SP_029036_20240803_02_T1 | 53.9 | 55.72 | -1.82
childress_tx | 2024-08-19 | LC09_L2SP_029036_20240819_02_T1 | 57.19 | 59.31 | -2.12
childress_tx | 2024-09-20 | LC09_L2SP_029036_20240920_02_T1 | 49.31 | 50.79 | -1.48
childress_tx | 2024-09-28 | LC08_L2SP_029036_20240928_02_T1 | 39.85 | 40.83 | -0.98
childress_tx | 2024-10-06 | LC09_L2SP_029036_20241006_02_T1 | 42.74 | 43.63 | -0.89
childress_tx | 2024-10-22 | LC09_L2SP_029036_20241022_02_T1 | 37.45 | 38.42 | -0.97
childress_tx | 2024-10-30 | LC08_L2SP_029036_20241030_02_T1 | 34.62 | 35.7 | -1.08
childress_tx | 2024-11-15 | LC08_L2SP_029036_20241115_02_T1 | 21.04 | 21.34 | -0.3
childress_tx | 2024-11-23 | LC09_L2SP_029036_20241123_02_T1 | 18.28 | 18.58 | -0.3
childress_tx | 2024-12-01 | LC08_L2SP_029036_20241201_02_T1 | 14.55 | 14.73 | -0.18
childress_tx | 2025-01-02 | LC08_L2SP_029036_20250102_02_T1 | 15.1 | 15.77 | -0.66
childress_tx | 2025-02-03 | LC08_L2SP_029036_20250203_02_T1 | 29.99 | 30.84 | -0.85
childress_tx | 2025-02-27 | LC09_L2SP_029036_20250227_02_T1 | 27.61 | 28.44 | -0.83
childress_tx | 2025-03-07 | LC08_L2SP_029036_20250307_02_T1 | 27.17 | 27.84 | -0.67
childress_tx | 2025-04-08 | LC08_L2SP_029036_20250408_02_T1 | 27.11 | 27.63 | -0.52
childress_tx | 2025-04-16 | LC09_L2SP_029036_20250416_02_T1 | 36.3 | 36.74 | -0.44
childress_tx | 2025-05-10 | LC08_L2SP_029036_20250510_02_T1 | 31.06 | 30.81 | 0.26
childress_tx | 2025-06-03 | LC09_L2SP_029036_20250603_02_T1 | 44.28 | 44.33 | -0.05
childress_tx | 2025-06-19 | LC09_L2SP_029036_20250619_02_T1 | 39.57 | 40.5 | -0.94
childress_tx | 2025-07-21 | LC09_L2SP_029036_20250721_02_T1 | 50.65 | 51.55 | -0.9
childress_tx | 2025-07-29 | LC08_L2SP_029036_20250729_02_T1 | 51.76 | 52.36 | -0.6
childress_tx | 2025-08-06 | LC09_L2SP_029036_20250806_02_T1 | 46.58 | 48.24 | -1.65
childress_tx | 2025-08-14 | LC08_L2SP_029036_20250814_02_T1 | 42.42 | 43.13 | -0.71
childress_tx | 2025-08-22 | LC09_L2SP_029036_20250822_02_T1 | 39.39 | 39.07 | 0.32
childress_tx | 2025-09-07 | LC09_L2SP_029036_20250907_02_T1 | 38.67 | 38.8 | -0.13
childress_tx | 2025-09-15 | LC08_L2SP_029036_20250915_02_T1 | 36.33 | 36.41 | -0.08
childress_tx | 2025-09-23 | LC09_L2SP_029036_20250923_02_T1 | 41.46 | 42.3 | -0.85
childress_tx | 2025-10-01 | LC08_L2SP_029036_20251001_02_T1 | 41.52 | 42.76 | -1.24
childress_tx | 2025-10-09 | LC09_L2SP_029036_20251009_02_T1 | 33.02 | 33.52 | -0.5
childress_tx | 2025-10-17 | LC08_L2SP_029036_20251017_02_T1 | 36.65 | 37.84 | -1.19
childress_tx | 2025-11-02 | LC08_L2SP_029036_20251102_02_T1 | 24.56 | 25.6 | -1.03
childress_tx | 2025-11-10 | LC09_L2SP_029036_20251110_02_T1 | 19.32 | 20.45 | -1.13
childress_tx | 2025-12-12 | LC09_L2SP_029036_20251212_02_T1 | 18.63 | 19.64 | -1.01
childress_tx | 2025-12-28 | LC09_L2SP_029036_20251228_02_T1 | 20.16 | 21.04 | -0.88
childress_tx | 2026-02-06 | LC08_L2SP_029036_20260206_02_T1 | 26.41 | 28.61 | -2.21
childress_tx | 2026-02-22 | LC08_L2SP_029036_20260222_02_T1 | 18.9 | 20.6 | -1.7
childress_tx | 2026-03-10 | LC08_L2SP_029036_20260310_02_T1 | 35.85 | 37.98 | -2.14
childress_tx | 2026-03-26 | LC08_L2SP_029036_20260326_02_T1 | 40.24 | 43.71 | -3.47
childress_tx | 2026-04-27 | LC08_L2SP_029036_20260427_02_T1 | 40.23 | 43.7 | -3.47
childress_tx | 2026-05-13 | LC08_L2SP_029036_20260513_02_T1 | 49.48 | 53.49 | -4.01
childress_tx | 2026-07-08 | LC09_L2SP_029036_20260708_02_T1 | 47.48 | 49.41 | -1.93
childress_tx | 2026-08-01 | LC08_L2SP_029036_20260801_02_T1 | 37.49 | 38.03 | -0.54
childress_tx | 2026-08-09 | LC09_L2SP_029036_20260809_02_T1 | 50.01 | 52.64 | -2.63
childress_tx | 2026-08-17 | LC08_L2SP_029036_20260817_02_T1 | 50.85 | 53.62 | -2.77
childress_tx | 2026-09-02 | LC08_L2SP_029036_20260902_02_T1 | 49.16 | 52.64 | -3.48
childress_tx | 2026-09-26 | LC09_L2SP_029036_20260926_02_T1 | 33.29 | 34.25 | -0.95
abilene_tx | 2024-11-07 | LC09_L2SP_029037_20241107_02_T2 | 16.87 | 17.15 | -0.28
abilene_tx | 2024-11-08 | LC08_L2SP_028038_20241108_02_T2 | -7.82 | -6.36 | -1.47
abilene_tx | 2024-11-15 | LC08_L2SP_029037_20241115_02_T1 | 23.13 | 22.85 | 0.28
abilene_tx | 2024-11-16 | LC09_L2SP_028037_20241116_02_T1 | 22.77 | 22.04 | 0.74
abilene_tx | 2024-11-23 | LC09_L2SP_029037_20241123_02_T1 | 21.81 | 21.69 | 0.12
abilene_tx | 2024-11-24 | LC08_L2SP_028037_20241124_02_T1 | 24.38 | 24.19 | 0.19
abilene_tx | 2024-11-24 | LC08_L2SP_028038_20241124_02_T1 | 24.38 | 24.24 | 0.14
abilene_tx | 2024-12-01 | LC08_L2SP_029037_20241201_02_T1 | 18.23 | 18.21 | 0.02
abilene_tx | 2024-12-18 | LC09_L2SP_028037_20241218_02_T1 | 13.6 | 13.53 | 0.07
abilene_tx | 2024-12-18 | LC09_L2SP_028038_20241218_02_T1 | 13.63 | 13.8 | -0.18
abilene_tx | 2025-01-02 | LC08_L2SP_029037_20250102_02_T1 | 16.2 | 16.78 | -0.58
abilene_tx | 2025-01-11 | LC08_L2SP_028037_20250111_02_T1 | 10.38 | 10.44 | -0.07
abilene_tx | 2025-01-11 | LC08_L2SP_028038_20250111_02_T1 | 10.39 | 10.52 | -0.13
abilene_tx | 2025-01-18 | LC08_L2SP_029037_20250118_02_T1 | 12.29 | 12.64 | -0.35
abilene_tx | 2025-01-19 | LC09_L2SP_028037_20250119_02_T1 | 5.29 | 5.64 | -0.35
abilene_tx | 2025-01-19 | LC09_L2SP_028038_20250119_02_T1 | 5.29 | 5.67 | -0.39
abilene_tx | 2025-01-27 | LC08_L2SP_028037_20250127_02_T1 | 12.81 | 12.71 | 0.09
abilene_tx | 2025-02-03 | LC08_L2SP_029037_20250203_02_T1 | 30.08 | 30.42 | -0.34
abilene_tx | 2025-02-20 | LC09_L2SP_028037_20250220_02_T1 | 8.16 | 8.58 | -0.43
abilene_tx | 2025-02-20 | LC09_L2SP_028038_20250220_02_T1 | 8.16 | 8.6 | -0.44
abilene_tx | 2025-02-27 | LC09_L2SP_029037_20250227_02_T1 | 25.85 | 26.78 | -0.93
abilene_tx | 2025-02-28 | LC08_L2SP_028038_20250228_02_T1 | 30.68 | 31.4 | -0.73
abilene_tx | 2025-03-07 | LC08_L2SP_029037_20250307_02_T1 | 30.87 | 31.39 | -0.52
abilene_tx | 2025-03-08 | LC09_L2SP_028037_20250308_02_T2 | 3.96 | 4.11 | -0.15
abilene_tx | 2025-03-16 | LC08_L2SP_028037_20250316_02_T1 | 28.67 | 28.98 | -0.3
abilene_tx | 2025-03-16 | LC08_L2SP_028038_20250316_02_T1 | 28.74 | 29.31 | -0.57
abilene_tx | 2025-03-23 | LC08_L2SP_029037_20250323_02_T1 | 32.07 | 32.74 | -0.68
abilene_tx | 2025-03-24 | LC09_L2SP_028037_20250324_02_T1 | 35.01 | 35.57 | -0.56
abilene_tx | 2025-03-24 | LC09_L2SP_028038_20250324_02_T1 | 35.08 | 35.93 | -0.85
abilene_tx | 2025-03-31 | LC09_L2SP_029037_20250331_02_T1 | 32.34 | 33.0 | -0.66
abilene_tx | 2025-04-08 | LC08_L2SP_029037_20250408_02_T1 | 29.59 | 30.11 | -0.53
abilene_tx | 2025-04-09 | LC09_L2SP_028037_20250409_02_T1 | 32.71 | 33.43 | -0.72
abilene_tx | 2025-04-09 | LC09_L2SP_028038_20250409_02_T1 | 32.72 | 33.45 | -0.73
abilene_tx | 2025-04-16 | LC09_L2SP_029037_20250416_02_T1 | 37.49 | 37.96 | -0.47
abilene_tx | 2025-05-10 | LC08_L2SP_029037_20250510_02_T1 | 33.29 | 32.98 | 0.32
abilene_tx | 2025-05-11 | LC09_L2SP_028037_20250511_02_T1 | 33.66 | 33.1 | 0.55
abilene_tx | 2025-05-11 | LC09_L2SP_028038_20250511_02_T1 | 33.67 | 33.14 | 0.53
abilene_tx | 2025-06-03 | LC09_L2SP_029037_20250603_02_T1 | 42.35 | 42.06 | 0.28
abilene_tx | 2025-06-19 | LC09_L2SP_029037_20250619_02_T1 | 43.63 | 42.43 | 1.21
abilene_tx | 2025-06-20 | LC08_L2SP_028038_20250620_02_T1 | 42.91 | 42.26 | 0.64
abilene_tx | 2025-06-28 | LC09_L2SP_028037_20250628_02_T1 | 47.24 | 46.46 | 0.78
abilene_tx | 2025-06-28 | LC09_L2SP_028038_20250628_02_T1 | 47.25 | 46.62 | 0.63
abilene_tx | 2025-07-21 | LC09_L2SP_029037_20250721_02_T1 | 43.95 | 43.54 | 0.41
abilene_tx | 2025-07-29 | LC08_L2SP_029037_20250729_02_T1 | 45.55 | 45.0 | 0.54
abilene_tx | 2025-07-30 | LC09_L2SP_028038_20250730_02_T1 | 48.85 | 48.26 | 0.6
abilene_tx | 2025-08-06 | LC09_L2SP_029037_20250806_02_T1 | 47.27 | 47.51 | -0.24
abilene_tx | 2025-08-07 | LC08_L2SP_028038_20250807_02_T1 | 47.31 | 47.29 | 0.02
abilene_tx | 2025-08-14 | LC08_L2SP_029037_20250814_02_T1 | 46.7 | 46.3 | 0.39
abilene_tx | 2025-08-15 | LC09_L2SP_028037_20250815_02_T1 | 43.19 | 43.43 | -0.25
abilene_tx | 2025-08-15 | LC09_L2SP_028038_20250815_02_T1 | 43.16 | 42.93 | 0.23
abilene_tx | 2025-09-15 | LC08_L2SP_029037_20250915_02_T1 | 44.43 | 44.39 | 0.03
abilene_tx | 2025-09-16 | LC09_L2SP_028037_20250916_02_T1 | 42.27 | 42.53 | -0.26
abilene_tx | 2025-09-16 | LC09_L2SP_028038_20250916_02_T1 | 42.31 | 42.66 | -0.34
abilene_tx | 2025-09-23 | LC09_L2SP_029037_20250923_02_T1 | 44.25 | 44.45 | -0.2
abilene_tx | 2025-10-01 | LC08_L2SP_029037_20251001_02_T1 | 39.46 | 39.33 | 0.13
abilene_tx | 2025-10-02 | LC09_L2SP_028038_20251002_02_T1 | 41.06 | 40.59 | 0.48
abilene_tx | 2025-10-09 | LC09_L2SP_029037_20251009_02_T1 | 41.13 | 40.88 | 0.25
abilene_tx | 2025-10-10 | LC08_L2SP_028037_20251010_02_T1 | 39.17 | 38.96 | 0.21
abilene_tx | 2025-10-10 | LC08_L2SP_028038_20251010_02_T1 | 39.19 | 39.08 | 0.11
abilene_tx | 2025-10-17 | LC08_L2SP_029037_20251017_02_T1 | 36.51 | 36.93 | -0.42
abilene_tx | 2025-10-26 | LC08_L2SP_028038_20251026_02_T1 | 28.1 | 27.76 | 0.35
abilene_tx | 2025-11-02 | LC08_L2SP_029037_20251102_02_T1 | 26.04 | 26.11 | -0.07
abilene_tx | 2025-11-03 | LC09_L2SP_028037_20251103_02_T1 | 27.54 | 27.5 | 0.04
abilene_tx | 2025-11-03 | LC09_L2SP_028038_20251103_02_T1 | 27.59 | 27.75 | -0.16
abilene_tx | 2025-11-10 | LC09_L2SP_029037_20251110_02_T1 | 21.7 | 20.85 | 0.85
abilene_tx | 2025-11-11 | LC08_L2SP_028038_20251111_02_T1 | 24.29 | 24.55 | -0.26
abilene_tx | 2025-11-18 | LC08_L2SP_029037_20251118_02_T1 | 32.69 | 32.31 | 0.38
abilene_tx | 2025-11-26 | LC09_L2SP_029037_20251126_02_T1 | 15.55 | 15.23 | 0.32
abilene_tx | 2025-11-27 | LC08_L2SP_028037_20251127_02_T1 | 17.56 | 17.43 | 0.13
abilene_tx | 2025-12-12 | LC09_L2SP_029037_20251212_02_T1 | 21.86 | 21.91 | -0.05
abilene_tx | 2025-12-28 | LC09_L2SP_029037_20251228_02_T1 | 24.75 | 25.02 | -0.27
abilene_tx | 2026-01-05 | LC08_L2SP_029037_20260105_02_T1 | 24.76 | 25.35 | -0.58
abilene_tx | 2026-01-06 | LC09_L2SP_028037_20260106_02_T1 | 22.79 | 23.2 | -0.41
abilene_tx | 2026-01-06 | LC09_L2SP_028038_20260106_02_T1 | 22.83 | 23.66 | -0.83
abilene_tx | 2026-01-14 | LC08_L2SP_028038_20260114_02_T1 | 18.05 | 18.96 | -0.91
abilene_tx | 2026-01-21 | LC08_L2SP_029037_20260121_02_T1 | 16.58 | 17.32 | -0.74
abilene_tx | 2026-01-29 | LC09_L2SP_029037_20260129_02_T1 | 5.42 | 6.22 | -0.8
abilene_tx | 2026-02-06 | LC08_L2SP_029037_20260206_02_T1 | 25.53 | 26.39 | -0.86
abilene_tx | 2026-02-07 | LC09_L2SP_028037_20260207_02_T1 | 24.35 | 25.11 | -0.76
abilene_tx | 2026-02-07 | LC09_L2SP_028038_20260207_02_T1 | 24.35 | 25.28 | -0.93
abilene_tx | 2026-02-15 | LC08_L2SP_028037_20260215_02_T1 | 20.33 | 20.82 | -0.48
abilene_tx | 2026-02-15 | LC08_L2SP_028038_20260215_02_T1 | 20.34 | 20.86 | -0.52
abilene_tx | 2026-02-22 | LC08_L2SP_029037_20260222_02_T1 | 21.37 | 22.11 | -0.74
abilene_tx | 2026-02-23 | LC09_L2SP_028037_20260223_02_T1 | 22.17 | 22.76 | -0.59
abilene_tx | 2026-02-23 | LC09_L2SP_028038_20260223_02_T1 | 22.17 | 22.98 | -0.81
abilene_tx | 2026-03-10 | LC08_L2SP_029037_20260310_02_T1 | 32.08 | 32.31 | -0.23
abilene_tx | 2026-03-11 | LC09_L2SP_028037_20260311_02_T1 | 23.32 | 23.25 | 0.07
abilene_tx | 2026-03-11 | LC09_L2SP_028038_20260311_02_T1 | 23.36 | 23.41 | -0.05
abilene_tx | 2026-03-19 | LC08_L2SP_028037_20260319_02_T1 | 36.64 | 37.85 | -1.21
abilene_tx | 2026-03-19 | LC08_L2SP_028038_20260319_02_T1 | 36.64 | 37.97 | -1.33
abilene_tx | 2026-03-26 | LC08_L2SP_029037_20260326_02_T1 | 37.01 | 38.11 | -1.1
abilene_tx | 2026-04-04 | LC08_L2SP_028037_20260404_02_T1 | 22.74 | 22.54 | 0.2
abilene_tx | 2026-04-19 | LC09_L2SP_029037_20260419_02_T1 | 29.64 | 29.1 | 0.54
abilene_tx | 2026-04-27 | LC08_L2SP_029037_20260427_02_T1 | 43.01 | 43.0 | 0.01
abilene_tx | 2026-05-13 | LC08_L2SP_029037_20260513_02_T1 | 48.51 | 48.87 | -0.36
abilene_tx | 2026-05-14 | LC09_L2SP_028037_20260514_02_T1 | 45.36 | 46.19 | -0.83
abilene_tx | 2026-05-14 | LC09_L2SP_028038_20260514_02_T1 | 45.37 | 46.21 | -0.85
abilene_tx | 2026-05-22 | LC08_L2SP_028037_20260522_02_T1 | 36.51 | 35.7 | 0.81
abilene_tx | 2026-06-23 | LC08_L2SP_028038_20260623_02_T1 | 49.49 | 49.91 | -0.42
abilene_tx | 2026-06-30 | LC08_L2SP_029037_20260630_02_T1 | 44.49 | 44.92 | -0.42
abilene_tx | 2026-07-01 | LC09_L2SP_028037_20260701_02_T1 | 36.68 | 39.41 | -2.72
abilene_tx | 2026-07-08 | LC09_L2SP_029037_20260708_02_T1 | 45.21 | 44.11 | 1.09
abilene_tx | 2026-07-09 | LC08_L2SP_028038_20260709_02_T1 | 46.14 | 45.83 | 0.31
abilene_tx | 2026-07-24 | LC09_L2SP_029037_20260724_02_T1 | 51.26 | 50.44 | 0.82
abilene_tx | 2026-08-02 | LC09_L2SP_028037_20260802_02_T1 | 50.45 | 49.8 | 0.66
abilene_tx | 2026-08-02 | LC09_L2SP_028038_20260802_02_T1 | 50.47 | 50.47 | 0.0
abilene_tx | 2026-08-09 | LC09_L2SP_029037_20260809_02_T1 | 50.9 | 51.18 | -0.28
abilene_tx | 2026-08-10 | LC08_L2SP_028038_20260810_02_T1 | 48.25 | 49.11 | -0.87
abilene_tx | 2026-08-17 | LC08_L2SP_029037_20260817_02_T1 | 51.53 | 52.77 | -1.23
abilene_tx | 2026-08-18 | LC09_L2SP_028038_20260818_02_T1 | 53.35 | 54.4 | -1.04
abilene_tx | 2026-08-25 | LC09_L2SP_029037_20260825_02_T1 | 45.39 | 46.65 | -1.26
abilene_tx | 2026-09-02 | LC08_L2SP_029037_20260902_02_T1 | 51.4 | 51.0 | 0.4
abilene_tx | 2026-09-03 | LC09_L2SP_028038_20260903_02_T1 | 53.24 | 54.17 | -0.93
abilene_tx | 2026-09-18 | LC08_L2SP_029037_20260918_02_T1 | 47.37 | 48.34 | -0.97
abilene_tx | 2026-09-19 | LC09_L2SP_028038_20260919_02_T1 | 52.38 | 53.59 | -1.21
abilene_tx | 2026-09-26 | LC09_L2SP_029037_20260926_02_T1 | 43.45 | 44.52 | -1.07
portwash_wi | 2023-02-04 | LC08_L2SP_023030_20230204_02_T1 | -5.74 | -6.5 | 0.76
portwash_wi | 2023-02-12 | LC09_L2SP_023030_20230212_02_T1 | 7.44 | 6.56 | 0.88
portwash_wi | 2023-04-09 | LC08_L2SP_023030_20230409_02_T1 | 18.41 | 18.5 | -0.09
portwash_wi | 2023-05-27 | LC08_L2SP_023030_20230527_02_T1 | 32.75 | 31.69 | 1.06
portwash_wi | 2023-06-12 | LC08_L2SP_023030_20230612_02_T1 | 28.42 | 27.25 | 1.17
portwash_wi | 2023-06-20 | LC09_L2SP_023030_20230620_02_T1 | 38.74 | 36.5 | 2.24
portwash_wi | 2023-07-14 | LC08_L2SP_023030_20230714_02_T1 | 31.5 | 31.51 | -0.01
portwash_wi | 2023-07-22 | LC09_L2SP_023030_20230722_02_T1 | 32.71 | 31.81 | 0.9
portwash_wi | 2023-08-15 | LC08_L2SP_023030_20230815_02_T1 | 27.56 | 27.83 | -0.27
portwash_wi | 2023-08-31 | LC08_L2SP_023030_20230831_02_T1 | 26.11 | 26.61 | -0.5
portwash_wi | 2023-10-02 | LC08_L2SP_023030_20231002_02_T1 | 28.5 | 27.93 | 0.57
portwash_wi | 2023-11-11 | LC09_L2SP_023030_20231111_02_T1 | 9.51 | 9.38 | 0.13
portwash_wi | 2023-11-19 | LC08_L2SP_023030_20231119_02_T1 | 10.92 | 10.6 | 0.31
portwash_wi | 2024-03-02 | LC09_L2SP_023030_20240302_02_T1 | 14.02 | 14.45 | -0.43
portwash_wi | 2024-03-10 | LC08_L2SP_023030_20240310_02_T1 | 7.13 | 6.81 | 0.32
portwash_wi | 2024-05-05 | LC09_L2SP_023030_20240505_02_T1 | 22.72 | 22.44 | 0.29
portwash_wi | 2024-05-29 | LC08_L2SP_023030_20240529_02_T1 | 24.34 | 23.37 | 0.98
portwash_wi | 2024-06-14 | LC08_L2SP_023030_20240614_02_T1 | 31.91 | 30.78 | 1.13
portwash_wi | 2024-08-25 | LC09_L2SP_023030_20240825_02_T1 | 31.22 | 30.52 | 0.7
portwash_wi | 2024-09-10 | LC09_L2SP_023030_20240910_02_T1 | 28.96 | 28.66 | 0.3
portwash_wi | 2024-09-18 | LC08_L2SP_023030_20240918_02_T1 | 30.19 | 29.79 | 0.41
portwash_wi | 2024-09-26 | LC09_L2SP_023030_20240926_02_T1 | 27.69 | 27.08 | 0.61
portwash_wi | 2024-10-04 | LC08_L2SP_023030_20241004_02_T1 | 22.29 | 21.51 | 0.78
portwash_wi | 2024-10-20 | LC08_L2SP_023030_20241020_02_T1 | 27.1 | 26.02 | 1.08
portwash_wi | 2025-01-24 | LC08_L2SP_023030_20250124_02_T1 | -5.42 | -5.93 | 0.5
portwash_wi | 2025-02-25 | LC08_L2SP_023030_20250225_02_T1 | 9.94 | 9.3 | 0.65
portwash_wi | 2025-04-06 | LC09_L2SP_023030_20250406_02_T1 | 16.07 | 15.57 | 0.49
portwash_wi | 2025-05-08 | LC09_L2SP_023030_20250508_02_T1 | 23.91 | 22.36 | 1.55
portwash_wi | 2025-06-01 | LC08_L2SP_023030_20250601_02_T1 | 24.26 | 24.82 | -0.56
portwash_wi | 2025-06-17 | LC08_L2SP_023030_20250617_02_T1 | 35.84 | 36.74 | -0.9
portwash_wi | 2025-07-03 | LC08_L2SP_023030_20250703_02_T1 | 33.31 | 33.21 | 0.1
portwash_wi | 2025-07-27 | LC09_L2SP_023030_20250727_02_T1 | 34.25 | 33.83 | 0.43
portwash_wi | 2025-09-29 | LC09_L2SP_023030_20250929_02_T1 | 27.73 | 28.32 | -0.59
portwash_wi | 2025-10-07 | LC08_L2SP_023030_20251007_02_T1 | 22.27 | 21.63 | 0.64
portwash_wi | 2025-10-31 | LC09_L2SP_023030_20251031_02_T1 | 14.7 | 14.87 | -0.17
portwash_wi | 2025-11-16 | LC09_L2SP_023030_20251116_02_T1 | 8.33 | 8.42 | -0.09
portwash_wi | 2026-04-09 | LC09_L2SP_023030_20260409_02_T1 | 20.16 | 17.84 | 2.32
portwash_wi | 2026-07-14 | LC09_L2SP_023030_20260714_02_T1 | 37.29 | 37.8 | -0.51
portwash_wi | 2026-07-30 | LC09_L2SP_023030_20260730_02_T1 | 31.92 | 32.41 | -0.49
monarch_wv | 2023-01-15 | LC09_L2SP_019033_20230115_02_T1 | 1.54 | 1.43 | 0.1
monarch_wv | 2023-03-20 | LC09_L2SP_019033_20230320_02_T1 | 11.84 | 11.48 | 0.36
monarch_wv | 2023-03-29 | LC09_L2SP_018033_20230329_02_T1 | 18.41 | 17.91 | 0.49
monarch_wv | 2023-04-13 | LC08_L2SP_019033_20230413_02_T1 | 29.42 | 28.7 | 0.72
monarch_wv | 2023-05-24 | LC08_L2SP_018033_20230524_02_T1 | 29.24 | 28.53 | 0.71
monarch_wv | 2023-06-09 | LC08_L2SP_018033_20230609_02_T1 | 30.01 | 29.08 | 0.93
monarch_wv | 2023-07-11 | LC08_L2SP_018033_20230711_02_T1 | 32.74 | 32.63 | 0.12
monarch_wv | 2023-07-26 | LC09_L2SP_019033_20230726_02_T1 | 32.08 | 32.09 | -0.01
monarch_wv | 2023-08-20 | LC09_L2SP_018033_20230820_02_T1 | 29.25 | 29.45 | -0.2
monarch_wv | 2023-09-04 | LC08_L2SP_019033_20230904_02_T1 | 30.85 | 31.07 | -0.22
monarch_wv | 2023-09-05 | LC09_L2SP_018033_20230905_02_T1 | 32.36 | 32.62 | -0.26
monarch_wv | 2023-09-20 | LC08_L2SP_019033_20230920_02_T1 | 25.68 | 25.6 | 0.07
monarch_wv | 2023-09-21 | LC09_L2SP_018033_20230921_02_T1 | 27.42 | 27.28 | 0.14
monarch_wv | 2023-10-23 | LC09_L2SP_018033_20231023_02_T1 | 16.51 | 16.19 | 0.32
monarch_wv | 2023-11-15 | LC09_L2SP_019033_20231115_02_T1 | 17.05 | 16.59 | 0.46
monarch_wv | 2024-01-11 | LC09_L2SP_018033_20240111_02_T1 | 7.59 | 7.54 | 0.05
monarch_wv | 2024-02-03 | LC09_L2SP_019033_20240203_02_T1 | 8.35 | 8.1 | 0.25
monarch_wv | 2024-02-04 | LC08_L2SP_018033_20240204_02_T1 | 10.37 | 9.94 | 0.42
monarch_wv | 2024-02-19 | LC09_L2SP_019033_20240219_02_T1 | 8.89 | 8.52 | 0.37
monarch_wv | 2024-02-20 | LC08_L2SP_018033_20240220_02_T1 | 9.27 | 9.04 | 0.22
monarch_wv | 2024-04-07 | LC09_L2SP_019033_20240407_02_T1 | 20.08 | 19.43 | 0.66
monarch_wv | 2024-04-15 | LC08_L2SP_019033_20240415_02_T1 | 27.86 | 27.29 | 0.57
monarch_wv | 2024-04-23 | LC09_L2SP_019033_20240423_02_T1 | 23.19 | 22.7 | 0.49
monarch_wv | 2024-05-02 | LC09_L2SP_018033_20240502_02_T1 | 32.15 | 31.11 | 1.04
monarch_wv | 2024-07-12 | LC09_L2SP_019033_20240712_02_T1 | 33.79 | 33.82 | -0.03
monarch_wv | 2024-07-28 | LC09_L2SP_019033_20240728_02_T1 | 35.02 | 35.35 | -0.33
monarch_wv | 2024-08-22 | LC09_L2SP_018033_20240822_02_T1 | 28.36 | 28.94 | -0.58
monarch_wv | 2024-08-29 | LC09_L2SP_019033_20240829_02_T1 | 37.68 | 38.15 | -0.47
monarch_wv | 2024-08-30 | LC08_L2SP_018033_20240830_02_T1 | 37.38 | 37.92 | -0.55
monarch_wv | 2024-09-06 | LC08_L2SP_019033_20240906_02_T1 | 31.57 | 31.82 | -0.25
monarch_wv | 2024-09-14 | LC09_L2SP_019033_20240914_02_T1 | 29.23 | 29.26 | -0.03
monarch_wv | 2024-09-15 | LC08_L2SP_018033_20240915_02_T1 | 28.95 | 28.96 | -0.01
monarch_wv | 2024-09-22 | LC08_L2SP_019033_20240922_02_T1 | 30.7 | 30.57 | 0.13
monarch_wv | 2024-10-08 | LC08_L2SP_019033_20241008_02_T1 | 21.57 | 21.4 | 0.17
monarch_wv | 2024-10-09 | LC09_L2SP_018033_20241009_02_T1 | 21.74 | 21.41 | 0.34
monarch_wv | 2024-10-17 | LC08_L2SP_018033_20241017_02_T1 | 16.25 | 15.97 | 0.28
monarch_wv | 2024-11-01 | LC09_L2SP_019033_20241101_02_T1 | 19.52 | 19.08 | 0.44
monarch_wv | 2024-11-02 | LC08_L2SP_018033_20241102_02_T1 | 16.98 | 16.29 | 0.69
monarch_wv | 2024-12-12 | LC09_L2SP_018033_20241212_02_T1 | 0.61 | 0.42 | 0.19
monarch_wv | 2025-03-09 | LC09_L2SP_019033_20250309_02_T1 | 15.44 | 15.17 | 0.27
monarch_wv | 2025-03-10 | LC08_L2SP_018033_20250310_02_T1 | 19.52 | 19.04 | 0.48
monarch_wv | 2025-03-18 | LC09_L2SP_018033_20250318_02_T1 | 20.74 | 20.14 | 0.6
monarch_wv | 2025-04-18 | LC08_L2SP_019033_20250418_02_T1 | 27.95 | 27.31 | 0.64
monarch_wv | 2025-04-27 | LC08_L2SP_018033_20250427_02_T1 | 21.3 | 20.72 | 0.57
monarch_wv | 2025-08-08 | LC08_L2SP_019033_20250808_02_T1 | 30.98 | 30.84 | 0.14
monarch_wv | 2025-08-09 | LC09_L2SP_018033_20250809_02_T1 | 31.9 | 31.8 | 0.11
monarch_wv | 2025-09-01 | LC09_L2SP_019033_20250901_02_T1 | 29.66 | 30.03 | -0.36
monarch_wv | 2025-09-02 | LC08_L2SP_018033_20250902_02_T1 | 29.4 | 29.62 | -0.21
monarch_wv | 2025-09-09 | LC08_L2SP_019033_20250909_02_T1 | 25.08 | 25.19 | -0.1
monarch_wv | 2025-09-18 | LC08_L2SP_018033_20250918_02_T1 | 29.74 | 29.85 | -0.11
monarch_wv | 2025-10-03 | LC09_L2SP_019033_20251003_02_T1 | 26.32 | 25.83 | 0.5
monarch_wv | 2025-10-04 | LC08_L2SP_018033_20251004_02_T1 | 27.79 | 27.27 | 0.52
monarch_wv | 2025-10-11 | LC08_L2SP_019033_20251011_02_T1 | 22.14 | 21.68 | 0.46
monarch_wv | 2025-10-20 | LC08_L2SP_018033_20251020_02_T1 | 17.49 | 17.28 | 0.21
monarch_wv | 2025-11-12 | LC08_L2SP_019033_20251112_02_T1 | 11.61 | 11.15 | 0.46
monarch_wv | 2025-11-13 | LC09_L2SP_018033_20251113_02_T1 | 13.46 | 13.16 | 0.3
monarch_wv | 2026-01-23 | LC09_L2SP_019033_20260123_02_T1 | -0.59 | -0.76 | 0.17
monarch_wv | 2026-03-29 | LC08_L2SP_018033_20260329_02_T1 | 20.9 | 20.07 | 0.83
monarch_wv | 2026-04-06 | LC09_L2SP_018033_20260406_02_T1 | 20.38 | 19.63 | 0.75
monarch_wv | 2026-04-21 | LC08_L2SP_019033_20260421_02_T1 | 24.14 | 22.83 | 1.31
monarch_wv | 2026-08-28 | LC09_L2SP_018033_20260828_02_T1 | 32.76 | 31.48 | 1.28
monarch_wv | 2026-09-04 | LC09_L2SP_019033_20260904_02_T1 | 38.53 | 37.03 | 1.5

## Sites_AOI
site | lat | lon | half_m | cadence | detail crop [W,S,E,N] | basis
denton_tx | 33.215 | -97.211 | 1300 | Q (2023-01..2026-10) + monthly 2025-07..2026-10 | [-97.215, 33.208, -97.204, 33.22] | Nominatim/OSM: Jim Christal Rd west segment (33.2207,-97.2088) + Denton Energy Center (33.2149,-97.2098); campus at 8171 Jim Christal Rd per Core Scientific 8-K 2026-04-21; mining-shed rows located visually W/SW of DEC
childress_tx | 34.392 | -100.045 | 2500 | Q (2023-01..2026-10) + monthly 2025-07..2026-10 | [-100.0575, 34.3815, -100.039, 34.393] | located visually in a 10 km search AOI (34.40,-100.10): building rows E of Childress near FM 1033 (address 620 FM 1033 per ColoMap/Texas AI Docket)
kvandal_no | 68.565 | 17.565 | 3000 | Q (2023-01..2026-10) + monthly 2025-07..2026-10 | [17.575, 68.569, 17.6, 68.586] | approx: north Bjerkvik, NW side of E6 (Kvandal North industrial plan, 345.no 2024-04); refined visually
abilene_tx | 32.5029 | -99.7834 | 1800 | Q (2023-01..2026-10) + monthly 2025-07..2026-10 | [-99.798, 32.487, -99.769, 32.511] | Nominatim/OSM: Lancium Clean Campus, Abilene TX
kcairworld_mo | 39.296 | -94.6762 | 600 | Q (2023-01..2026-10) + monthly 2025-07..2026-10 | [-94.677, 39.294, -94.672, 39.2975] | Nominatim: 11155 N Airworld Dr, Kansas City MO (Lambda Project Blitz; ex-Bank of America DC)
portwash_wi | 43.435 | -87.875 | 2500 | Q (2023-01..2026-10) + monthly 2025-07..2026-10 | [-87.87, 43.414, -87.848, 43.4435] | approx: north Port Washington between I-43 / Dixie Rd / Interurban Trail; tour address 1374 Lake Dr geocodes 43.4420,-87.8546; refined visually
monarch_wv | 38.9143 | -82.1009 | 2500 | Q (2023-01..2026-10) + monthly 2025-07..2026-10 | [-82.122, 38.902, -82.088, 38.925] | WVDEP draft air permit R14-0042 (2026-09-29): 30 Monarch Way, Ohio River Rd (WV-62) & Airport Rd, Point Pleasant, Mason County WV; Lat/Lon 38.914258/-82.100935; former Mason County Airport runway